## Sheet1
Sr. No.	Route Type	LMC/Route	IP1 / Co-built	DN receipient	Project Name	Site ID	UID	Contract type	Build Type	Category type	Survey ID	PO Number	PO Length	Route ID/LMC ID	Parent Route	Route/LMC ID	Route/LMC Section ID	Route/LMC Subsection ID	Application Number	Application Length (Mtr)	Application Date	From	To	Authority	Ward	Survey Done (Mtr)	DN Number	DN Length (Mtr)	DN Received date	Type	Trench Type	OT /HDD	PIT	Surface	RI Rate (GO) / (Rs.)	DN RI Amount	Multiplying / factor	Ground Rent	Administrative Charge	Supervision Charges	Chamber Fee	GST	Deposit	Total DN amount	RI Budget amount per meter (for the section)	Projected Budget RI amount for DN	Actual Total Non Refundable Amount (RI+Ground+Admin+Supervision)	Non refundable Actual Amount/mtr	Non Refundable Savings/Mtr	Deposit	Total DN amount	ROW Network ID	Route Network ID	New Revised DN Number	New Revised DN against	Internal approval start date	Internal approval end date	Ticket raised date	DN payment date	TAT (ticket raised and DN Payment)	Civil Completion date
1	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_50	MUM_Route_50	IP-1	Sify - Common	Strategic	AIR52K24R050001	10004765	6030	MUM_Route_50	NA	MUMUR050	MUMUR050NIMI	MUMUR050NMMI250129D4C4L0001	I96966	4766	29-Jan-25	A SIFY Rabale	F Mahape	MIDC	MIDC	Yes	I96966	4766	10-Feb-25	Legal	Open Trench			Embankment Soil	41	1,95,406	0	-	4,766			36,031	2,50,000	4,86,203	19,200	9,15,07,200	2,00,172	42	19,158	2,50,000	4,86,203	MUM-ROW000000060	MUM-RTE002			1-Feb-25	6-Feb-25	6-Feb-25	12-Feb-25	6
2	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_50	MUM_Route_50	IP-1	Sify - Common	Strategic	AIR52K24R050002	10004765	6030	MUM_Route_50	NA	MUMUR050	MUMUR050NIMI	MUMUR050NMMI250212D4C4L0001	I99340	600		F Mahape Police Chowky	G CNTRL S Mahape	MIDC	MIDC	Yes	I99340	600	12-Feb-25	Legal	Open Trench			Embankment Soil+CC Crossing	41/1797	59,720	0	-	600			10,858	60,000	1,31,178	3,000	18,00,000	60,320	101	2,899	60,000	1,31,178	MUM-ROW000000069	MUM-RTE002			18-Feb-25	19-Feb-25	23-Feb-25	13-Mar-25	18
3	Additional Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	MUM_Route_131	MUM_Route_131	Co-build	New-build	Non-Strategic		10004641	200	MUM_Route_131	NA	MUMU25R131	MUMU25R131MCWA	MUMU25R131MCWA250328D3C3	783339212	145	28-Mar-25	NEAR SUCHITA BUILDING	NEAR HOTEL VICTORIA	MCGM	A	Yes	783339212	155	04-Apr-25	Legal	Open Trench			Carriageway+footpath/Passages	10187/10454	16,13,962	0	310	155				8,06,981	24,21,408	8,413	13,04,015	16,14,427	10,416	-2,003	8,06,981	24,21,408	MUM-ROW000000082				15-Apr-25	16-Apr-25	16-Apr-25	17-Apr-25	1
4	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project		MU-MA6295	Co-build	New-build	Non-Strategic		10004641	30	NA	MUMU25R010	MUMU25NL002	MUMU25NL002MCWA	MUMU25NL002MCWA250404D3C3L0003	783339141	20	27-Mar-25	NEAR EP NO-F/R-9 HOTEL POPULAR PALACE	NEAR MINT ROAD	MCGM	A	Yes	783339141	27	04-Apr-25	Legal	Open Trench			Carriageway	10187	2,75,049	0	54	27				1,37,525	4,12,655	12,469	3,36,663	2,75,130	10,190	2,279	1,37,525	4,12,655	MUM-ROW000000080				4-Apr-25	11-Apr-25	11-Apr-25	15-Apr-25	4
5	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA4226	MU-MA4226	Co-build	New-build	Non-Strategic		10004641	20	NA	MUMU25R010	MUMU25NL003	MUMU25NL003MCWA	MUMU25NL003MCWA250404D3C3L0004	783339100	8	27-Mar-25	NEAR HOTEL CASTLE IN HIRA BLDG	NEAR HOTEL CASTLE IN HIRA BLDG	MCGM	A	Yes	783339100	8	04-Apr-25	Legal	Open Trench			Footpath/Passages(Finished in / Stencil)	11211	4,48,440	5	16	8				-	4,48,464	12,469	99,752	4,48,464	56,058	-43,589		4,48,464	MUM-ROW000000081				4-Apr-25	11-Apr-25	11-Apr-25	15-Apr-25	4
6	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_48	MUM_Route_48	IP-1	Sify - Common	Strategic	AIR52K24R048008	10004681	3300	MUM_Route_48	NA	MUMU25R048	MUMUR048NMKK	MUMUR048NMKK250220D4C5L0011	ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/01	975	18-Mar-25	TTC Industrial area Bharti Airtel Office	Gami Industrial Park Pawne	NMMC	KK	Yes	NMMC/Z-2/265/2025	975	18-Mar-25	Legal	Open Trench/HDD	975	144000	Asphalt	9600	6,24,000	0	1,95,000	-	93,600			71,760	9,84,360	3,000	29,25,000	9,12,600	936	2,064	71,760	9,84,360	MUM-ROW000000057	MUM-RTE004			25-Mar-25	1-Apr-25	1-Apr-25	9-Apr-25	8
7	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_48	MUM_Route_48	IP-1	Sify - Common	Strategic	AIR52K24R048008	10004681	3300	MUM_Route_48	NA	MUMU25R048	MUMUR048NMKK	MUMUR048NMKK250220D4C5L0010	ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/02	820	18-Mar-25	Gami Industrial Park Pawne	Ashwini Infra Development	NMMC	KK	Yes	NMMC/Z-2/264/2025	820	18-Mar-25	Legal	Open Trench/HDD	820	144000	Asphalt	9600	6,24,000	0	1,64,000	-	93,600			71,760	9,53,360	3,000	24,60,000	8,81,600	1,075	1,925	71,760	9,53,360	MUM-ROW000000051	MUM-RTE004			25-Mar-25	1-Apr-25	1-Apr-25	9-Apr-25	8
8	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_48	MUM_Route_48	IP-1	Sify - Common	Strategic	AIR52K24R048008	10004681	3300	MUM_Route_48	NA	MUMU25R048	MUMUR048NMKK	MUMUR048NMKK250220D4C5L0009	ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/03	825	18-Mar-25	Ashwini Infra Development	CTRL S Data Center	NMMC	KK	Yes	NMMC/Z-2/266/2025	825	18-Mar-25	Legal	Open Trench/HDD	825	144000	Asphalt	9600	6,24,000	0	1,65,000	-	93,600			71,760	9,54,360	3,000	24,75,000	8,82,600	1,070	1,930	71,760	9,54,360	MUM-ROW000000046	MUM-RTE004			25-Mar-25	1-Apr-25	1-Apr-25	9-Apr-25	8
9	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_10	MUM_Route_10	IP-1	Existing	Strategic		10004633	10280	MUM_Route_10	NA	MUMU25R010	MUMU25R010MCWA	MUMU25R010MCWA250408D3C3L0020	783339910	42	08-Apr-25	PNB HOUSE (PNB BANK)	APNA BAZAR (GREAT SOCIAL BLDG	MCGM	A	Yes	783339910	52	08-Apr-25	Legal	Open Trench			Mastic Asphalt 40 m+Concrete Finished	14936/28	6,51,176		104	52				3,25,588	9,76,920	8,413	4,37,476	6,51,332	12,526	-4,113	3,25,588	9,76,920	MUM-ROW000000070				9-Apr-25	20-Apr-25	20-Apr-25	25-Apr-25	5
10	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	6195	MU-6195	Co-Build	New-build	Non-Strategic		10004835	242	NA	NA	MUMU25FL004	MUMU25FL004MCRS	MUMU25FL004MCRS250415D33L0005	783341287	65	09-Apr-25	AVERSHINE MILLENIUM PAIRADISE	THAKUR SHYAM NARAYAN SCHOOL	MCGM	RS	Yes	783341287	75	15-Apr-25	Legal	Open Trench			Carriageway	11378	8,53,350	1	150	75				4,26,675	12,80,250	14,936	11,20,200	8,53,575	11,381		4,26,675	12,80,250	MUM-ROW000000077				15-Apr-25	17-Apr-25	18-Apr-25	29-Apr-25	11
11	DC Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	MUM_Route_90	MUM_Route_90	Co-build	Sify - Common	Strategic	AIR52K24R090010	10004960	14270	MUM_Route_90	NA	MUMU25R090	MUMU25R090MCME	MUMU25R090MCME250412D3C3L0023	783339980	156	08-Apr-25	NR ASHTVINAYAK CHS	POLE NO. YJS/005/023	MCGM	ME	Yes	783339980	156	12-Apr-25	Legal	Open Trench			Carriageway	6711	10,46,916	0	312	156				5,23,458	15,70,842	-	-	10,47,384	6,714	-6,714	5,23,458	15,70,842	MUM-ROW000000074				18-Apr-25	21-Apr-25	21-Apr-25	23-Apr-25	2
12	DC Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	MUM_Route_90	MUM_Route_90	Co-build	Sify - Common	Strategic	AIR52K24R090010	10004960	14270	MUM_Route_90	NA	MUMU25R090	MUMU25R090MCME	MUMU25R090MCME250412D3C3L0024	783340005	126	08-Apr-25	POLE NO. YJS/005/023	MCGM MOTOR LODER CHOWKY( AAGARWADI JN.)	MCGM	ME	Yes	783340005	136	12-Apr-25	Legal	Open Trench			Carriageway	6711	9,12,696	0	272	136				4,56,348	13,69,452	-	-	9,13,104	6,714	-6,714	4,56,348	13,69,452	MUM-ROW000000073				18-Apr-25	21-Apr-25	21-Apr-25	23-Apr-25	2
13	Additional Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	Mumbai_Coverage_Route7	Mumbai_Coverage_Route7	Co-build	New-build	Non-Strategic	Entire route DN achieved in single go.	10004531	2590	Mumbai_Coverage_Route7	NA	MUMU25RC07	MUMU25RC07KDWI	MUMU25RC07KDWI250325D3C3L0025	AIRTEL/OSP/2024-25/Open Trench-HDD/kdmc/01	2128	25-Mar-25	Hanuman Road	Nr jankalayan multispeciality hospital	KDMC	KD	Yes	KDMC/Ex.Engg/Construction/K-W/10	2128	15-Apr-25	Legal	Open Trench	2128		Paverblock+Asphalt	9269.27/12326.53	2,43,01,725		4,25,600		36,45,259			24,30,172	3,08,02,756	11,600	2,46,84,800	2,83,72,584	13,333	-1,733	24,30,172	3,08,02,756	MUM-ROW000000078				18-Apr-25	20-Apr-25	20-Apr-25	2-May-25	12
14	Additional Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	Mumbai_Coverage_Route13	Mumbai_Coverage_Route13	Co-build	New-build	Non-Strategic	AIR52K24RC13007	10004545	3030	Mumbai_Coverage_Route13	NA	MUMU25RC13	MUMU25RC13KDKD	MUMU25RC13KDKD250325D3C3L0026	AIRTEL/OSP/2024-25/Open Trench-HDD/kdmc/02	80	25-Mar-25	Jhulelal Chowk	Gold Gym	KDMC	KD	Yes	KDMC/Ex.Engg/Construction/K-W/06	80	11-Apr-25	Legal	Open Trench	80		Paverblock	9269.27	7,41,542		160	-				74,170	8,15,872			7,41,702			74,170	8,15,872	MUM-ROW000000079								0
15	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	5831	MU-5831	Co-Build	New-build	Non-Strategic		10004791	67	NA	NA	MUMU25FL005	MUMU25FL005MCRN	MUMU25FL005MCRN250401D3C30027	783339323	116	01-Apr-25	JAYWANT SAWANT MARG	SAI AMRUT CHS	MCGM	RN	Yes	783339323	136	17-Apr-25	Legal	Open Trench			Carriageway(PB 80(OnlyGrey+Use of Existing Duct)	8246/2900	10,67,996	0	272	136				5,33,998	16,02,402	7487	10,18,232	10,68,404	7,856	-369	5,33,998	16,02,402	MUM-ROW000000086				18-Apr-25	20-Apr-25	20-Apr-25	23-Apr-25	3
16	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB6370	MU-MB6370	Co-Build	New-build	Non-Strategic		10004838	33	NA	NA	MUMU25FL005	MUMU25FL005MCRN	MUMU25FL005MCRN250409D3C30028	783340181	81	09-Apr-25	RAJ HERITAGE TOWER	MARY JAMMACULATE GIRLS SCHOOL	MCGM	RN	Yes	783340181	91	17-Apr-25	Legal	Open Trench			Carriageway(Bituminous / Concrete)	11378	10,35,398	1	182	91				5,17,699	15,53,370	14,936	13,59,176	10,35,671	11,381	3,555	5,17,699	15,53,370	MUM-ROW000000088				18-Apr-25	20-Apr-25	20-Apr-25	23-Apr-25	3
17	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_10	MUM_Route_10	IP-1	Existing	Strategic		10004633	10280	MUM_Route_10	NA	MUMU25R010	MUMU25R010MCWB	MUMU25R010MCWB250403D3C3L0029	783339575	50	03-Apr-25	Hotel Elphinstone Annexe	Godee Area opp. Navratna Premises	MCGM	B	Yes	783339575	60	19-Apr-25	Legal	Open Trench			Mastic / Asphalt 40 m	14936	8,96,160		120	60				4,48,080	13,44,420	8,413	5,04,780	8,96,340	14,939	-6,526	4,48,080	13,44,420	MUM-ROW000000083				22-Apr-25	24-Apr-25	24-Apr-25	25-Apr-25	1
18	DC Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	MUM_Route_45	MUM_Route_45	Co-build	New-build	Strategic	AIR52K24R045005, AIR52K24R045006, AIR52K24R045007, AIR52K24R045008, AIR52K24R045009	10004670	6432	MUM_Route_45	NA	MUMU25R045	MUMU25R045NMKK	MUMU25R045NMKK250327D3C3L0004	I110310	4765	45743	Stock Holding Corporation	Shilphata Road	MIDC	KK	Yes	I110310	4765	24-Apr-25	Legal	Open Trench			Embankment Soil	484	23,06,260	0	14,300	-			4,17,908	5,00,000	32,38,468	-	-	23,20,560	487	-487	5,00,000	32,38,468					25-Apr-25	25-Apr-25	28-Apr-25	1-May-25	3
19	DC Route	Route	Co-Built	Airtel	Mumbai Fiber Refresh Project	MUM_Route_90	MUM_Route_90	Co-build	Sify - Common	Strategic	AIR52K24R090010	10004960	14270	MUM_Route_90	NA	MUMU25R090	MUMU25R090MCME	MUMU25R090MCME250424D4C5L0005	783341644	160	24-Apr-25	AGARWADI VILLAGE ROAD	ZARINA PARK GATE NO 02	MCGM	ME	Yes	783341644	160	25-Apr-25	Legal	Open Trench			Carriageway(Trench on already ex)	6711	10,73,760	0	320	160				5,36,880	16,11,120	-	-	10,74,240	6,714	-6,714	5,36,880	16,11,120	MUM-ROW000000087				25-Apr-25	26-Apr-25	26-Apr-25	5-May-25	9
20	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_10	MUM_Route_10	IP-1	Existing	Strategic		10004633	10280	MUM_Route_10	NA	MUMU25R010	MUMU25R010MCWB	MUMU25R010MCWE241221D2C6L0012	783326066	23	26-Jun-24	BOB Mirza Galibh road	Byculla Fire Bricade	MCGM	E	Yes	783326066	33	21-Dec-24	Legal	Open Trench			Carriageway(Mastic Asphalt 25 mm)+footpath/Passages(Finished in Stencil/)	12469/11211	11,52,439		66	33				5,76,220	17,28,758	8,413	2,77,629	11,52,538	34,925	-26,512	5,76,220	17,28,758					4-Apr-25	5-Apr-25	5-Apr-25	10-Apr-25	5
21	DC Route	Route	IP-1	CE	Mumbai Fiber Refresh Project	MUM_Route_10	MUM_Route_10	IP-1	Existing	Strategic		10004633	10280	MUM_Route_10	NA	MUMU25R010	MUMU25R010MCWB	MUMU25R010MCWE241221D3C6L0013	783326083	29	26-Jun-24	BMC E ward office	Mirza Galibh road junction	MCGM	E	Yes	783326083	39	21-Dec-24	Legal	Open Trench			Carriageway(Mastic Asphalt 25 mm)+footpath/Passages(Grey or Any / Color)	12469/8518	3,67,761		78	39				1,83,881	5,51,759	8,413	3,28,107	3,67,878	9,433	-1,020	1,83,881	5,51,759					4-Apr-25	5-Apr-25	5-Apr-25	10-Apr-25	5
22	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA2115	MU-MA2115	Co-Build	New-build	Non-Strategic		10004833	34	NA		MUMU25NL004	MUMU25NL004MCRC	MUMU25NL004MCRC250415D3C3L0005	783340659	3	15-Apr-25	KRISHNA HERITAGE	KRISHNA HERITAGE FOOTPATH	MCGM	RC	Yes	783340659	4	25-Apr-25	Legal	Open Trench			footpath/Passages(Grey or Any / Color)	8518	68,144	2	8	4				34,072	1,02,228	32019	1,28,076	68,156	17,039	14,980	34,072	1,02,228					26-Apr-25	28-Apr-25	28-Apr-25	9-May-25	11
23	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA928	MU-MA928	Co-Build	New-build	Non-Strategic		10004856	368	NA	NA	MUMU25FL012	MUMU25FL012MCRC	MUMU25FL012MCRC250415D3C3L0018	783340711	132	15-Apr-25	PM KULKARNI ROAD	ACHARYA ASHRAM	MCGM	RC	Yes	783340711	100	25-Apr-25	Legal	Open Trench			On Carriageway(Mastic Asphalt 40 m)	14936	14,93,600	1	200	100				7,46,800	22,40,700	14936	14,93,600	14,93,900	14,939	-3	7,46,800	22,40,700					26-Apr-25	28-Apr-25	28-Apr-25	9-May-25	11
24	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA928	MU-MA928	Co-Build	New-build	Non-Strategic		10004856	368	NA	NA	MUMU25FL012	MUMU25FL012MCRC	MUMU25FL012MCRC250415D3C3L0007	783340697	90	15-Apr-25	PM KULKARNI ROAD	ACHARYA ASHRAM	MCGM	RC	Yes	783340697	100	25-Apr-25	Legal	Open Trench			Carriageway(Mastic Asphalt 40 m)	14936	14,93,600	0	200	100				7,46,800	22,40,700	14,936	14,93,600	14,93,900	14,939	-3	7,46,800	22,40,700					26-Apr-25	28-Apr-25	28-Apr-25	9-May-25	11
25	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	3386	MU-3386	Co-Build	New-build	Non-Strategic		10004879	280	NA	NA	MUMU25FL006	MUMU25FL006MCHW	MUMU25FL006MCHW250424D3C30029	783341573	166	24-Apr-25	DR. KESHAW BALRAM CHOWK	GAEITY GALAXY THEATER	MCGM	HW	Yes	783341573	196	26-Apr-25	Legal	Open Trench			Carriageway	6711	13,15,356	0	392	196				6,57,678	19,73,622	8,518	16,69,528	13,15,944	6,714	1,804	6,57,678	19,73,622					27-Apr-25	28-Apr-25	28-Apr-25	29-Apr-25	1
26	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	148	MU-148	Co-Build	New-build	Non-Strategic		10004692	67	NA	NA	MUMU25FL007	MUMU25FL007MCHW	MUMU25FL007MCHW250424D3C30030	783341566	130	24-Apr-25	OPP. JASHMIN HOUSE	PANJETANI VILLA	MCGM	HW	Yes	783341566	140	26-Apr-25	Legal	Open Trench			Carriageway	10187	14,26,180	1	280	140				7,13,090	21,39,690	14,936	20,91,040	14,26,600	10,190	4,746	7,13,090	21,39,690					27-Apr-25	28-Apr-25	19-Apr-25	19-Apr-25	0
27	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	5541	MU-5541	Co-Build	New-build	Non-Strategic		10004701	235	NA	NA	MUMU25FL008	MUMU25FL008MCHW	MUMU25FL008MCHW250424D3C30031	783341581	130	09-Sep-24	WINNIE APARTMENT	EDVIN 189 BUILDING	MCGM	HW	Yes	783341581	135	26-Apr-25	Legal	Open Trench			Carriageway(Bituminous Concrete)+footpath/Passages(Concrete / Finished)	10187/10454	14,27,515	1	280	140				7,13,758	21,41,693	14,936	20,16,360	14,27,935	10,577	4,359	7,13,758	21,41,693					27-Apr-25	28-Apr-25	29-Apr-25	29-Apr-25	0
28	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	5541	MU-5541	Co-Build	New-build	Non-Strategic		10004701	235	NA	NA	MUMU25FL009	MUMU25FL009MCHW	MUMU25FL009MCHW250424D3C30032	783341568	100	09-Sep-24	EDVIN 189 BUILDING	CHIMBAI ROAD CORNER	MCGM	HW	Yes	783341568	120	26-Apr-25	Legal	Open Trench			On Carriageway(Bituminous Concrete)	10187	12,22,440		240	120				6,11,220	18,34,020	14,936	17,92,320	12,22,800	10,190	4,746	6,11,220	18,34,020					27-Apr-25	28-Apr-25	29-Apr-25	29-Apr-25	0
29	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	2958	MU-2958	Co-Build	New-build	Non-Strategic		10004801	224	NA	NA	MUMU25FL010	MUMU25FL010MCMW	MUMU25FL010MCMW250417D3C3L0013	783340898	80	17-Apr-24	OPP. SANKET APARTMENT	NEAR EESH KRIPA BLDG	MCGM	MW	Yes	783340898	90	29-Apr-25	Legal	Open Trench			Carriageway(Bituminous Concrete+Others)	10187	9,16,830	1	180	90				4,58,415	13,75,515	14,936	13,44,240	9,17,100	10,190	4,746	4,58,415	13,75,515	MUM-ROW000000090				29-Apr-25	5-Feb-25	5-Mar-25		-45721
30	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	2958	MU-2958	Co-Build	New-build	Non-Strategic		10004801	224	NA	NA	MUMU25FL010	MUMU25FL010MCMW	MUMU25FL010MCMW250417D3C3L0014	783340954	130	17-Apr-24	NEAR EESH KRIPA BLDG	NEAR MAHESH KUTIR BLDG	MCGM	MW	Yes	783340954	140	29-Apr-25	Legal	Open Trench			Carriageway(Bituminous Concrete+Others)	10187	14,26,180		280	140				7,13,090	21,39,690	14,936	20,91,040	14,26,600	10,190	4,746	7,13,090	21,39,690					29-Apr-25	5-Feb-25	5-Mar-25		-45721
31	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	3054	MU-3054	Co-build	New-build	Non-Strategic		10004641	30	NA	MUMU25R010	MUMU25NL006	MUMU25NL006MCWA	MUMU25NL006MCWA250415D3C3L0015	783340693	20	15-Apr-25	SUN CLINIC	ANIL MILK SUPPLIER	MCGM	A	Yes	783340693	34	02-May-25	Legal	Open Trench			Carriageway(Bituminous Concrete)	10187	3,46,358	1	68	34				1,73,179	5,19,639	14,946	5,08,164	3,46,460	10,190	4,756	1,73,179	5,19,639	MUM-ROW000000093				5-May-25	6-May-25	6-May-25	8-May-25	2
32	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB3135	MU-MB3135	Co-build	New-build	Non-Strategic		10004641	130	NA	MUMU25R010	MUMU25NL007	MUMU25NL007MCWA	MUMU25NL007MCWA250414D3C3L0016	783340649	28	14-Apr-25	HOTEL MANAMA	FRIENDS PREMISES	MCGM	A	Yes	783340649	38	02-May-25	Legal	Open Trench			Carriageway(Mastic Asphalt 40 m)	14936	5,67,568	1	76	38				2,83,784	8,51,466	14,958	5,68,404	5,67,682	14,939	19	2,83,784	8,51,466	MUM-ROW000000094				5-May-25	6-May-25	6-May-25	9-May-25	3
33	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB1585	MU-MB1585	Co-Build	New-build	Non-Strategic		10004873	112	NA	NA	MUMU25FL011	MUMU25FL011KDWA	MUMU25FL011KDWA250424D3C3L0017	Airtel/OSP/2025-26/Open Trench/KDMC/MB-1585/130 Mtrs	130	24-Apr-24	BHIWANDI MURBAD ROAD	SHREE GANESH VANDAN BUILDING	KDMC	A	Yes	KMDC/KA/Const./25	130		Legal					9269.27	12,05,005		26,000	-	1,80,751			1,20,501	15,32,256	11,600	15,08,000	14,11,756	10,860	740	1,20,501	15,32,256					6-May-25	7-May-25	7-May-25		-45784
34	Additional Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA2218	MU-MA2218	Co-build	New-build	Non-Strategic		10004521	20	NA	MUMU25RC07	MUMU25NL008	MUMU25NL008KDWA	MUMU25NL008KDWA250429D3C3L0004	Airtel/OSP/2025-26/Open Trench/KDMC/MA-2218/20 Mtrs	20				KDMC	KDMC		KMDC/KA/Const./27	20		Legal					9269.27	1,85,385		4,000	-	27,808			18,539	2,35,732	11,600	2,32,000	2,17,193	10,860	740	18,539	2,35,733					6-May-25	7-May-25	7-May-25	14-May-25	7
35	Additional Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB1589	MU-MB1589	Co-build	New-build	Non-Strategic		10004521	90	NA	MUMU25RC07	MUMU25NL009	MUMU25NL009KDWA	MUMU25NL009KDWA250429D3C3L0001	Airtel/OSP/2025-26/Open Trench/KDMC/MB-1589/75 Mtrs	75				KDMC	KDMC		KMDC/KA/Const./28	75		Legal					9269.27	6,95,195		15,000	-	1,04,279			69,520	8,83,994	11,600	8,70,000	8,14,475	10,860	740	69,520	8,83,994	MUM-ROW000000092				6-May-25	7-May-25	7-May-25	14-May-25	7
36	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA1048	MU-MA1048	Co-Build	New-build	Non-Strategic		10004830	280	NA	NA	MUMU25FL012	MUMU25FL012KDWB	MUMU25FL012KDWB250418D3C3L0020	Airtel / MBMC /OSP/2025-26/OPEN TRENCH/KDMC/MA-1048/127 Mtrs	127	18-Apr-24	Khadkapada Road	Reliance Digital Building	KDMC	B	Yes	KMDC/KA/Const./26	127	02-May-25	Legal	Open Trench			Paver Block	9269.27	11,77,197		25,400	-	1,76,580			1,17,720	14,96,897	11,600	14,73,200	13,79,177	10,860	740	1,17,720	14,96,897	MUM-ROW000000098				6-May-25	7-May-25	7-May-25		-45784
37	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MA2181	MU-MA2181	Co-build	New-build	Non-Strategic		10004772	400	NA	MUMU25R050	MUMU25NL010	MUMU25NL010NIMI	MUMU25NL010NIMI250418D3C3L0021	MIDC-DIV-2/OSP/2025-26/AIRTEL/PLOT NO-PAP-R-343/375 MTRS	375	18-Apr-24			MIDC	MIDC	Yes	No.EE/Dn.II/MHP/Eoffice/I/I113925	375	19-05-2025	Legal	Open Trench			Hard Side Shoulder		1,81,500		1,200	-	-		32,886	50,000	2,65,586	11,849	44,43,375	1,82,700	487	11,362	50,000	2,65,586	MUM-ROW000000076				20-May-25	20-May-25	20-May-25	27-May-25	7
38	DC Route	LMC	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB3667	MU-MB3667	Co-build	New-build	Non-Strategic		10004772	280	NA	MUMU25R050	MUMU25NL011	MUMU25NL011NIMI	MUMU25NL011NIMI250418D3C3L0022	MIDC-DIV-2/OSP/2025-26/AIRTEL/MB-3667/130 MTRS	130	18-Apr-24			MIDC	MIDC	Yes	No.EE/Dn.II/MHP/Eoffice/I/I113922	130	19-05-2025	Legal	Open Trench			Hard Side Shoulder		63,000		400	-	-		11,412	25,000	99,812	11,107	14,43,910	63,400	488	10,619	25,000	99,812	MUM-ROW000000104				20-May-25	20-May-25	20-May-25	27-May-25	7
40	LMC routes / (stand alone)	Fibmax	Co-Built	Airtel	Mumbai Fiber Refresh Project	MB1608	MU-MB1608	Co-Build	New-build	Non-Strategic		10004869	56	NA	NA	MUMU25FL012	MUMU25FL012MBMB	MUMU25FL012MBMB250411D3C3L0001	Airtel / MBMC /OSP/2025-26/OT/ Arihant “B” CHSL /124 Mtrs	124	11-Apr-24	Radha Krishna Hotel	Arihant “B” CHSL	MBMC	MBMC	Yes	NO.MBMC/PWD/1014/64/2025-26	124	30-Apr-25	Legal	Open Trench			Asphalt Road	9600	11,90,400		24,800	-	-		2,18,736	1,19,040	15,52,976	4,500	5,58,000	12,15,200	9,800	-5,300	1,19,040	15,52,976									0