## Use for board_Sheet3
Delivery month | (Multiple Items)
Row Labels | Sum of POP + route | Row Labels | Sum of PO Length (Mtr)
Praveen Nigam | 56.092 | Praveen Nigam | 4.467 | 1000
Prem Verma | 7.318 | Prem Verma | 2.68
Satish Singh | 30.688 | Satish Singh | 6.286
Yogesh Deshpande | 43.1 | Yogesh Deshpande | 8.189
Grand Total | 137.198 | Grand Total | 21.622

## Route wise
[8 empty] | 170.9412 | 173 | 23.9745 |  | 173.9324 | 183.7585 | 180 | 22.8346 | PO Details_Co Build |  |  |  | PO Details_IP1 |  |  |  |  | 185.272
ac | Manager | Delivery month | Part of | Modality | Parent Route | Sub-Routes | tf | Route Length | No. of POP | Length of POP | Delivery Timelines | Surved Length (Km) | Revised Route Length (Km) | No of POP | Revised POP LM (Km) | PO No cobuild | PO Date | PO End Date | PO Length | PO No Ip1 | PO Date | PO End Date | PO Length | POP + route | Total PO Length | PO Remark |  |  | 2025-04-01 |  | Final Remark | SOBO/Non SOBO | UID | AW
2025-05-31 | Prem Verma | 2026-03-31 | 232 Km Route | IP1 | MUM_Route_10 | MUM_Route_10 | TRUE | 10.6738 | 15 | 2.1505 | May-25 | 10.274 | 10.85 | 15 | 1.09 |  |  |  |  | 10004633 | 2025-03-22 | 2026-03-22 | 10.28 | 11.37 | 10.28 | Ok | 0.006 |  | OK |  | PO Released | SOBO
2025-05-31 | Prem Verma | 2026-03-31 | Additional Route | Co-Built | MUM_Route_10 | MUM_Route_103 | FALSE |  |  |  | May-25 | 0 | 0.18641 | 0 | 0 | 10004641 | 2025-03-22 | 2026-03-22 | 0.19 |  |  |  |  | 0.19 | 0.19 | Ok | 0.19 |  | OK |  | PO Released | SOBO
2025-05-31 | Prem Verma | 2026-03-31 | Additional Route | Co-Built | MUM_Route_10 | MUM_Route_104 | FALSE |  |  |  | May-25 | 0 | 0.18713 | 0 | 0 | 10004641 | 2025-03-22 | 2026-03-22 | 0.19 |  |  |  |  | 0.19 | 0.19 | Ok | 0.19 |  | OK |  | PO Released | SOBO
2025-05-31 | Prem Verma | 2026-03-31 | Additional Route | Co-Built | MUM_Route_10 | MUM_Route_131 | FALSE |  |  |  | May-25 | 0 | 0.2 | 0 | 0 | 10004641 | 2025-03-22 | 2026-03-22 | 0.2 |  |  |  |  | 0.2 | 0.2 | Ok | 0.2 |  | OK |  | PO Released | SOBO |  | Shrikant Chavan
2025-12-31 | Prem Verma | 2025-12-31 | 52 Km Route | IP1 | MUM_Route_101 | MUM_Route_101 | TRUE | 0.7117 | 0 | 0 | Dec-25 | 0.7117 | 0.8 |  | 0 |  |  |  |  | 10004640 | 2025-03-22 | 2026-03-22 | 0.8 | 0.8 | 0.8 | Ok | 0.0883 |  |  |  | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-12-31 | 52 Km Route | IP1 | MUM_Route_102 | MUM_Route_102 | TRUE | 0.4213 | 0 | 0 | Dec-25 | 0.4213 | 0.4213 | 0 | 0 | [8 empty] | 0 | 0 | Under validation | -0.4213 | PO Awaited |  |  | Hold | SOBO
2025-10-31 | Prem Verma | 2026-05-31 | 52 Km Route | IP1 | MUM_Route_105 | MUM_Route_105 | TRUE | 0.99 | 1 | 0.0605 | Oct-25 | 0.99 | 1 | 1 | 0.0605 |  |  |  |  | 10004630 | 2025-03-22 | 2026-03-22 | 1 | 1.0605 | 1 | OK | 0.01 | PO Awaited |  |  | PO Released | SOBO
2025-05-31 | Prem Verma | 2026-04-30 | 52 Km Route | IP1 | MUM_Route_106 | MUM_Route_106 | TRUE | 1.943 | 3 | 0.132 | May-25 | 1.9426 | 2.4 | 4 | 0.23 |  |  |  |  | 10004997 | 2025-05-04 | 2026-05-04 | 3.49 | 3.72 | 3.49 | 10004635 Old PO Deleted, New PO Added on Dated 4th May-2025 | 1.5474 |  | Not Ok |  | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-12-31 | 52 Km Route | IP1+Co-Built | MUM_Route_107 | MUM_Route_107 | TRUE | 2.42 | 1 | 0.0275 | Dec-25 | 2.42 | 2.42 | 1 | 0.002 | 10004623 | 2025-03-22 | 2026-03-22 | 0.65 | 10004626 | 2025-03-22 | 2026-03-22 | 1.768 | 2.42 | 2.418 | Ok | 0 |  |  |  | PO Released | SOBO
2025-11-30 | Prem Verma | 2026-05-31 | 52 Km Route | IP1+Co-Built | MUM_Route_108 | MUM_Route_108 | TRUE | 2.7874 | 2 | 0.484 | Nov-25 | 2.7874 | 3.39 | 2 | 0.47 | 10004634 | 2025-03-22 | 2026-03-22 | 0.6 | 10004643 | 2025-03-22 | 2026-03-22 | 2.787 | 3.857 | 3.387 | Ok | 0.5996 |  | OK | 600 | PO Released | Non SOBO
2025-11-30 | Prem Verma | 2025-11-30 | Additional Route | Co-Built | MUM_Route_108 | MUM_BKC_906_LM | FALSE |  |  |  | Nov-25 | 0 | 0.48 |  |  | 10004634 | 2025-03-22 | 2026-03-22 | 0.48 |  |  |  |  | 0.48 | 0.48 | Ok |  |  | OK |  | PO Released | SOBO
2026-11-30 | Prem Verma | 2026-11-30 | 232 Km Route | Co-Built | MUM_Route_109 | MUM_Route_109 | TRUE | 1.595 | 4 | 0.539 | Nov-26 | 4.015 | 2.9 | 4 | 0.539 | 10004585 | 2025-03-19 | 2026-03-19 | 2.9 |  |  |  |  | 3.439 | 2.9 | Old route no 8 descoped | -1.115 | Shortfall | OK | -1120 | PO Released | Non SOBO
2026-11-30 | Prem Verma | 2026-11-30 | Additional Route | Co-Built | MUM_Route_109 | MUM_KAI_901_LM | FALSE |  |  |  | Nov-26 | 0 | 0.1 |  |  | 10004597 | 2025-03-19 | 2026-03-19 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok |  |  | OK |  | PO Released | Non SOBO
2025-11-30 | Prem Verma | 2025-11-30 | 52 Km Route | IP1 | MUM_Route_11 | MUM_Route_11 | TRUE | 1.401 | 0 | 0 | Nov-25 | 1.8128 | 1.401 |  | 0 | 10004625 | 2025-03-22 | 2026-03-22 | 1 | 10004642 | 2025-03-22 | 2026-03-22 | 0.39 | 1.39 | 1.39 | OK | -0.4228 | Shortfall | Not Ok |  | PO Released | SOBO
2026-05-31 | Yogesh Deshpande | 2026-05-31 | 52 Km Route | Co-Built | MUM_Route_110 | MUM_Route_110 | TRUE | 6.215 | 6 | 1.298 | May-26 | 6.215 | 6.215 | 6 | 1.06 | 10004589 | 2025-03-19 | 2026-03-19 | 6.22 |  |  |  |  | 7.28 | 6.22 | Ok | 0.005 |  |  |  | PO Released | Non SOBO
2025-11-30 | Satish Singh | 2025-11-30 | 52 Km Route | Co-Built | MUM_Route_111 | MUM_Route_111 | TRUE | 0.8415 | 0 | 0 | Nov-25 | 0.8415 | 0.8415 | 0 | 0 | 10004515 | 2025-03-13 | 2026-03-13 | 0.841 |  |  |  |  | 0.841 | 0.841 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-11-30 | Satish Singh | 2025-11-30 | 52 Km Route | Co-Built | MUM_Route_112 | MUM_Route_112 | TRUE | 1.0186 | 2 | 0.231 | Nov-25 | 1.0186 | 1.0186 | 2 | 0.231 | 10004515 | 2025-03-13 | 2026-03-13 | 1.02 |  |  |  |  | 1.251 | 1.02 | Ok | 0.0014 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 52 Km Route | Co-Built | MUM_Route_113 | MUM_Route_113 | TRUE | 2.4695 | 3 | 0.572 | Dec-26 | 1.8865 | 2.4695 | 3 | 0.572 | 10004596 | 2025-03-19 | 2026-03-19 | 1.89 |  |  |  |  | 2.462 | 1.89 | Ok | 0.0035 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2025-10-31 | 89 Km Route | Co-Built | MUM_Route_113 | MUM_Route_135 | FALSE |  |  |  | Dec-26 | 0.44 | 0.44 |  |  | 10004596 | 2025-03-19 | 2026-03-19 | 0.44 |  |  |  |  | 0.44 | 0.44 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_113 | MUM_Route_136 | FALSE |  |  |  | Dec-26 | 0.143 | 0.143 |  |  | 10004596 | 2025-03-19 | 2026-03-19 | 0.14 |  |  |  |  | 0.14 | 0.14 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | Additional Route | Co-Built | MUM_Route_113 | MUM_AND_933_LM | FALSE |  |  |  | Dec-26 | 0 | 0.1 |  |  | 10004598 | 2025-03-19 | 2026-03-19 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok |  |  |  |  | PO Released | Non SOBO
2025-10-31 | Satish Singh | 2026-05-31 | 52 Km Route | Co-Built | MUM_Route_114 | MUM_Route_114 | TRUE | 3.7158 | 3 | 0.1045 | Oct-25 | 3.7158 | 3.7158 | 3 | 0.1045 | 10004526 | 2025-03-13 | 2026-03-13 | 3.72 |  |  |  |  | 3.8245 | 3.72 | Ok | 0.0042 |  |  |  | PO Released | Non SOBO
2025-10-31 | Satish Singh | 2025-10-31 | Additional Route | Co-Built | MUM_Route_114 | MUM/GOE/908_LM | FALSE |  |  |  |  | 0 | 0.05 | 0 | 0 | 10004516 | 2025-03-13 | 2026-03-13 | 0.05 |  |  |  |  | 0.05 | 0.05 | Ok |  |  |  |  | PO Released | Non SOBO
2026-03-31 | Satish Singh | 2026-03-31 | 52 Km Route | Co-Built | MUM_Route_115 | MUM_Route_115 | TRUE | 4.5518 | 6 | 0.836 | Mar-26 | 4.5518 | 4.5518 | 6 | 0.836 | 10004533 | 2025-03-13 | 2026-03-13 | 4.55 |  |  |  |  | 5.386 | 4.55 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-03-31 | Satish Singh | 2026-03-31 | Additional Route | Co-Built | MUM_Route_115 | AGG BSN 903 | FALSE |  |  |  | Mar-26 | 0 | 0.125 |  |  | 10004538 | 2025-03-13 | 2026-03-13 | 0.125 |  |  |  |  | 0.125 | 0.125 | Ok |  |  |  |  | PO Released | Non SOBO
2026-01-31 | Yogesh Deshpande | 2026-01-31 | 52 Km Route | Co-Built | MUM_Route_116 | MUM_Route_116 | TRUE | 0.935 | 0 | 0 | Jan-26 | 0.935 | 0.935 | 0 | 0 | 10004579 | 2025-03-18 | 2026-03-18 | 0.94 |  |  |  |  | 0.94 | 0.94 | Ok | 0.005 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 52 Km Route | Co-Built | MUM_Route_117 | MUM_Route_117 | TRUE | 1.7567 | 1 | 0.121 | Feb-26 | 1.7567 | 1.7567 | 1 | 0.121 | 10004591 | 2025-03-19 | 2026-03-19 | 1.76 |  |  |  |  | 1.881 | 1.76 | Ok | 0.0033 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | Additional Route | Co-Built | MUM_Route_117 | MUM_LBS_906_LM | FALSE |  |  |  | Feb-26 | 0 | 0.12 |  |  | 10004590 | 2025-03-19 | 2026-03-19 | 0.12 |  |  |  |  | 0.12 | 0.12 | Ok |  |  |  |  | PO Released | Non SOBO
2026-05-31 | Praveen Nigam | 2026-05-31 | 52 Km Route | Co-Built | MUM_Route_122 | MUM_Route_122 | TRUE | 2.776 | 7 | 1.056 | Feb-26 | 2.67 | 2.67 | 7 | 1.2262 | 10004530 | 2025-03-13 | 2026-03-13 | 2.67 |  |  |  |  | 3.8962 | 2.67 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-05-31 | Praveen Nigam | 2026-05-31 | 52 Km Route | Co-Built | MUM_Route_122 | MUM_Route_121 | FALSE | 2.083 | 0 | 0 | Feb-26 | 2.083 | 2.083 |  | 0 | 10004530 | 2025-03-13 | 2026-03-13 | 2.08 |  |  |  |  | 2.08 | 2.08 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2026-02-28 | 52 Km Route | Co-Built | MUM_Route_123 | MUM_Route_123 | TRUE | 3.5849 | 0 | 0.315 | Feb-26 | 2.2187 | 1.5 | 3 | 0 | 10004664 | 2025-03-24 | 2026-03-24 | 1.5 |  |  |  |  | 1.5 | 1.5 | Length is decreased 2.22 to 1.50km | -0.7187 | Shortfall | Not Ok |  | PO Modification WIP | Non SOBO
2026-02-28 | Praveen Nigam | 2026-02-28 | 52 Km Route | Co-Built | MUM_Route_123 | MUM_Route_124 | FALSE |  |  |  | Feb-26 | 1.366 | 0.2 | 0 |  | 10004664 | 2025-03-24 | 2026-03-24 | 0.2 |  |  |  |  | 0.2 | 0.2 | Length is decreased 1.37 to 0.20km | -1.166 | Shortfall | Not Ok |  | Hold | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | Additional Route | Co-Built | MUM_Route_125 | MUM_Route_125 | TRUE | 0.18711 | 0 | 0 | Feb-26 | 0 | 0.18711 |  | 0 | 10004684 | 2025-03-24 | 2026-03-24 | 0.19 |  |  |  |  | 0.19 | 0.19 | Ok | 0.19 |  |  |  | PO Released | Non SOBO
2025-09-30 | Satish Singh | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_126 | MUM_Route_126 | TRUE | 0.31893 | 0 | 0 | Sept-25 | 0.31893 | 0.31893 |  | 0 | [8 empty] | 0 | 0 | Under validation | -0.31893 | PO Awaited |  |  | Hold | Non SOBO
2025-05-31 | Prem Verma | 2026-04-30 | Additional Route | Co-Built | MUM_Route_127 | MUM_Route_127 | TRUE | 1.1922 | 0 | 0 | May-25 | 0 | 1.1922 | 0 | 0 | 10004577 | 2025-03-18 | 2026-03-18 | 1.19 |  |  |  |  | 1.19 | 1.19 | Ok | 1.19 |  |  |  | PO Released | Non SOBO
2026-11-30 | Satish Singh | 2026-11-30 | 232 Km Route | Co-Built | MUM_Route_13 | MUM_Route_13 | TRUE | 3.5272 | 1 | 0.1375 | Nov-26 | 3.0272 | 3.027 | 1 | 0.13 | 10004586 | 2025-03-19 | 2026-03-19 | 3.03 |  |  |  |  | 3.16 | 3.03 | Ok | 0.0028 |  |  |  | PO Released | Non SOBO
2025-09-30 | Yogesh Deshpande | 2025-09-30 | Additional Route | Co-Built | MUM_Route_133 | MUM_Route_133 | TRUE | 0.12176 | 0 | 0 | sept-25 | 0 | 0.12176 |  | 0 | 10004686 | 2025-03-24 | 2026-03-24 | 0.12 |  |  |  |  | 0.12 | 0.12 | Ok | 0.12 |  | Ok |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 89 Km Route | Co-Built | MUM_Route_134 | MUM_Route_134 | TRUE | 1.3717 | 0 | 0 | Feb-26 | 1.3717 | 1.3717 | 0 | 0 | 10004679 | 2025-03-24 | 2026-03-24 | 1.37 |  |  |  |  | 1.37 | 1.37 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-07-31 | Yogesh Deshpande | 2026-05-31 | Additional Route | Co-Built | MUM_Route_139 | MUM_Route_139 | TRUE | 0.061435 | 0 | 0 | July-25 | 0 | 0.1 |  | 0 | 10004653 | 2025-03-24 | 2026-03-24 | 0.05 |  |  |  |  | 0.05 | 0.05 | Ok | 0 |  | Ok |  | PO Released | Non SOBO
2025-07-31 | Yogesh Deshpande | 2025-10-31 | Additional Route | Co-Built | MUM_Route_139 | MUM_Route_138 | FALSE |  |  |  | July-25 | 0 | 0.05 |  |  | 10004653 | 2025-03-24 | 2026-03-24 | 0.05 |  |  |  |  | 0.05 | 0.05 | Ok | 0.05 |  | Ok |  | PO Released | Non SOBO
2025-06-30 | Yogesh Deshpande | 2025-09-30 | Additional Route | Co-Built | MUM_Route_140 | MUM_Route_140 | TRUE | 0.074929 | 0 | 0 | June-25 | 0 | 0.074929 |  | 0 | 10004655 | 2025-03-24 | 2026-03-24 | 0.07 |  |  |  |  | 0.07 | 0.07 | Ok | 0.07 |  | Ok |  | PO Released | Non SOBO
2025-12-31 | Satish Singh | 2025-12-31 | 89 Km Route | Co-Built | MUM_Route_141 | MUM_Route_141 | TRUE | 2.282 | 0 | 0 | Dec-25 | 2.282 | 2.282 | 0 | 0 | 10004513 | 2025-03-13 | 2026-03-13 | 2.28 |  |  |  |  | 2.28 | 2.28 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-05-31 | Satish Singh | 2026-05-31 | 89 Km Route | Co-Built | MUM_Route_142 | MUM_Route_142 | TRUE | 2.762 | 2 | 0.0784 | May-26 | 2.762 | 2.762 | 2 | 0.0784 | 10004517 | 2025-03-13 | 2026-03-13 | 2.76 |  |  |  |  | 2.8384 | 2.76 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-05-31 | Satish Singh | 2026-05-31 | Additional Route | Co-Built | MUM_Route_142 | AGG_TVL_903 | FALSE |  |  |  | May-26 | 0 | 0.1 |  |  | 10004528 | 2025-03-13 | 2026-03-13 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok |  |  | OK |  | PO Released | Non SOBO
2026-01-31 | Yogesh Deshpande | 2026-05-31 | Additional Route | Co-Built | MUM_Route_147 | MUM_Route_147 | TRUE | 0.17683 | 0 | 0 | Jan-26 | 0 | 0.17683 |  | 0 | 10004676 | 2025-03-24 | 2026-03-24 | 0.18 |  |  |  |  | 0.18 | 0.18 | Ok | 0.18 |  | Ok |  | PO Released | Non SOBO
#N/A | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_150 & 151 | MUM_Route_150 & 151 | TRUE | 0.4246 | 0 | 0 | sept-25 | 0.2046 | 0.4246 |  | 0 | 10004667 | 2025-03-24 | 2026-03-24 | 0.42 |  |  |  |  | 0.42 | 0.42 | Route No 150 &151 are LMC / Sub Route under parent routes 150 | 0.2154 |  | Ok | 220 | PO Released | Non SOBO
2025-08-31 | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_155 | MUM_Route_155 | TRUE | 0.5973 | 0 | 0 | Aug-25 | 0.5973 | 1.5 |  | 0 | 10004683 | 2025-03-24 | 2026-03-24 | 1.5 |  |  |  |  | 1.5 | 1.5 | Ok.Feasibility needs to be recheck as original routes has been changed. | 0.9027 |  | Ok | 900 | PO Released | Non SOBO
2025-08-31 | Satish Singh | 2026-05-31 | 89 Km Route | Co-Built | MUM_Route_156 | MUM_Route_156 | TRUE | 0.30429 | 0 | 0 | Aug-25 | 0.30429 | 0.5 | 0 | 0 | 10004673 | 2025-03-24 | 2026-03-24 | 0.5 |  |  |  |  | 0.5 | 0.5 | Ok | 0.19571 |  |  |  | PO Released | Non SOBO
2025-11-30 | Yogesh Deshpande | 2025-11-30 | 89 Km Route | Co-Built | MUM_Route_157 | MUM_Route_157 | TRUE | 1.925 | 3 | 0.0825 | Nov-25 | 1.925 | 1.925 | 3 | 0.28 | 10004668 | 2025-03-24 | 2026-03-24 | 1.93 |  |  |  |  | 2.21 | 1.93 | Ok | 0.005 |  |  |  | PO Released | Non SOBO
2025-11-30 | Yogesh Deshpande | 2025-11-30 | Additional Route | Co-Built | MUM_Route_157 | MUM/LBS/904_LM | FALSE |  |  |  |  | 0 | 0.2 | 0 | 0 | [8 empty] | 0 | 0 | PO length not found |  |  |  |  | PO Modification WIP | Non SOBO
2025-11-30 | Yogesh Deshpande | 2025-11-30 | 232 Km Route | Co-Built | MUM_Route_16 | MUM_Route_16 | TRUE | 1.8337 | 1 | 0.22 | Nov-25 | 1.8337 | 1.834 | 1 | 0.22 | 10004592 | 2025-03-19 | 2026-03-19 | 1.83 |  |  |  |  | 2.05 | 1.83 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-04-30 | Praveen Nigam | 2026-04-30 | 89 Km Route | Co-Built | MUM_Route_160 | MUM_Route_160 | TRUE | 1.43 | 1 | 0.11 | Apr-26 | 1.43 | 1.43 | 1 | 0.11 | 10004654 | 2025-03-24 | 2026-03-24 | 1.43 |  |  |  |  | 1.54 | 1.43 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-11-30 | Praveen Nigam | 2025-11-30 | 89 Km Route | Co-Built | MUM_Route_161 | MUM_Route_161 | TRUE | 0.4785 | 0 | 0 | Nov-25 | 0.3025 | 0.3025 |  | 0 | 10004685 | 2025-03-24 | 2026-03-24 | 0.3 |  |  |  |  | 0.3 | 0.3 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-11-30 | Praveen Nigam | 2025-11-30 | 89 Km Route | Co-Built | MUM_Route_161 | MUM_Route_162 | FALSE |  |  |  | Nov-25 | 0.18 | 0.18 |  |  | 10004685 | 2025-03-24 | 2026-03-24 | 0.18 |  |  |  |  | 0.18 | 0.18 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-07-31 | Praveen Nigam | 2025-10-31 | 89 Km Route | Co-Built | MUM_Route_169 | MUM_Route_169 | TRUE | 0.561 | 0 | 0 | July-25 | 0.561 | 1.1 |  | 0 | 10004666 | 2025-03-24 | 2026-03-24 | 1.11 |  |  |  |  | 1.11 | 1.11 | Ok | 0.549 |  | Ok | 550 | PO Released | Non SOBO
2025-08-31 | Praveen Nigam | 2026-05-31 | 89 Km Route | Co-Built | MUM_Route_170 | MUM_Route_170 | TRUE | 1.1 | 0 | 0 | Aug-25 | 1.1 | 1.1 |  | 0 | 10004652 | 2025-03-24 | 2026-03-24 | 1.11 |  |  |  |  | 1.11 | 1.11 | Ok | 0.01 |  |  |  | PO Released | Non SOBO
#N/A | Praveen Nigam | 2025-07-31 | 89 Km Route | Co-Built | MUM_Route_171 & 172 | MUM_Route_171 & 172 | TRUE | 0.22 | 0 | 0 | July-25 | 0.22 | 0.22 |  | 0 | 10004660 | 2025-03-24 | 2026-03-24 | 0.22 |  |  |  |  | 0.22 | 0.22 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-10-31 | Yogesh Deshpande | 2026-10-31 | 232 Km Route | Co-Built | MUM_Route_19 | MUM_Route_19 | TRUE | 5.9246 | 12 | 1.8927 | Oct-26 | 5.9246 | 5.9246 | 12 | 1.65 | 10004663 | 2025-03-24 | 2026-03-24 | 5.92 |  |  |  |  | 7.57 | 5.92 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-10-31 | Yogesh Deshpande | 2026-10-31 | Additional Route | Co-Built | MUM_Route_19 | Satyam Agg_LM | FALSE |  |  |  | Oct-26 | 0 | 0.2 |  |  | 10004663 | 2025-03-24 | 2026-03-24 | 0.2 |  |  |  |  | 0.2 | 0.2 | Ok |  |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 232 Km Route | IP1+Co-Built | MUM_Route_23 | MUM_Route_23 | TRUE | 24.0643 | 11 | 1.2463 | Nov-26 | 22.0902 | 22.0902 | 11 | 0.92 | 10004959 | 2025-04-05 | 2026-04-05 | 12.5 | 10004631 | 2025-03-22 | 2026-03-22 | 6.42 | 19.84 | 18.92 | Ok | -3.1702 | Shortfall | Not Ok |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2025-10-31 | Additional Route | Co-Built | MUM_Route_23 | MUM_Route_173 | FALSE |  |  |  | Nov-26 | 0 | 0.55 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.55 |  |  |  |  | 0.55 | 0.55 | Ok | 0.55 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 89 Km Route | Co-Built | MUM_Route_23 | MUM_Route_148 | FALSE |  |  |  | Nov-26 | 0.28 | 0.28 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.28 |  |  |  |  | 0.28 | 0.28 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 89 Km Route | Co-Built | MUM_Route_23 | MUM_Route_149 | FALSE |  |  |  | Nov-26 | 0.4 | 0.4 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.4 |  |  |  |  | 0.4 | 0.4 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 89 Km Route | Co-Built | MUM_Route_23 | MUM_Route_153 | FALSE |  |  |  | Nov-26 | 0.517 | 0.517 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.52 |  |  |  |  | 0.52 | 0.52 | Ok | 0.003 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 89 Km Route | Co-Built | MUM_Route_23 | MUM_Route_152 | FALSE | 0.165 | 0 | 0.165 | Nov-25 | 0.495 | 0.52 |  | 0 | 10004959 | 2025-04-05 | 2026-04-05 | 0.5 |  |  |  |  | 0.5 | 0.5 | Ok | 0.005 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | Additional Route | Co-Built | MUM_Route_23 | Netmagic DC7_LM | FALSE |  |  |  | Nov-25 | 0 | 0.1 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok |  |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | Additional Route | Co-Built | MUM_Route_23 | Supreme Chamber_LM | FALSE |  |  |  | Nov-25 | 0 | 0.8 |  |  | 10004959 | 2025-04-05 | 2026-04-05 | 0.8 |  |  |  |  | 0.8 | 0.8 | Ok |  |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 232 Km Route | Co-Built | MUM_Route_25 | MUM_Route_25 | TRUE | 10.105 | 4 | 0.852 | Feb-26 | 9.537 | 8.5 | 4 | 0.58 | 10004650 | 2025-03-24 | 2026-03-24 | 8.5 |  |  |  |  | 9.08 | 8.5 | Ok..overlapping section in eastern express highway has been descoped.(1km). | -1.037 | Shortfall | Ok | -1004 | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 89 Km Route | Co-Built | MUM_Route_25 | MUM_Route_158 | FALSE |  |  |  | Feb-26 | 0.22 | 0.22 |  |  | 10004650 | 2025-03-24 | 2026-03-24 | 0.22 |  |  |  |  | 0.22 | 0.22 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 89 Km Route | Co-Built | MUM_Route_25 | MUM_Route_159 | FALSE |  |  |  | Feb-26 | 0.39 | 0.39 |  |  | 10004650 | 2025-03-24 | 2026-03-24 | 0.39 |  |  |  |  | 0.39 | 0.39 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | Additional Route | Co-Built | MUM_Route_25 | MUM/FTB/915_LM | FALSE |  |  |  |  | 0 | 0.15 |  |  | 10004651 | 2025-03-24 | 2026-03-24 | 0.15 |  |  |  |  | 0.15 | 0.15 | Ok |  |  |  |  | PO Modification WIP | Non SOBO
2026-01-31 | Satish Singh | 2026-01-31 | 232 Km Route | Co-Built | MUM_Route_27 | MUM_Route_27 | TRUE | 9.2268 | 8 | 1.1075 | Jan-26 | 9.2268 | 9.2268 | 8 | 1.69 | 10004587 | 2025-03-19 | 2026-03-19 | 9.23 |  |  |  |  | 10.92 | 9.23 | PO Modification WIP | 0.0032 | PO Awaited |  |  | PO Released | Non SOBO
2026-01-31 | Satish Singh | 2026-01-31 | Additional Route | Co-Built | MUM_Route_27 | MUM_VRL_901_LM | FALSE |  |  |  | Jan-26 | 0 | 0.2 |  |  | 10004594 | 2025-03-19 | 2026-03-19 | 0.2 |  |  |  |  | 0.2 | 0.2 | Ok |  |  |  |  | PO Released | Non SOBO
2025-12-31 | Satish Singh | 2025-12-31 | 232 Km Route | Co-Built | MUM_Route_30 | MUM_Route_30 | TRUE | 1.1451 | 2 | 0.319 | Dec-25 | 1.1451 | 1.1451 | 2 | 0.319 | 10004669 | 2025-03-24 | 2026-03-24 | 1.15 |  |  |  |  | 1.469 | 1.15 | Ok | 0.0049 |  |  |  | PO Released | Non SOBO
2026-04-30 | Satish Singh | 2026-04-30 | 232 Km Route | Co-Built | MUM_Route_31 | MUM_Route_31 | TRUE | 0.9658 | 0 | 0 | Apr-26 | 0.9658 | 0.9658 |  | 0 | 10004662 | 2025-03-24 | 2026-03-24 | 0.97 |  |  |  |  | 0.97 | 0.97 | Ok | 0.0042 |  |  |  | PO Released | Non SOBO
2026-04-30 | Satish Singh | 2026-04-30 | 232 Km Route | Co-Built | MUM_Route_33 | MUM_Route_33 | TRUE | 4.2295 | 5 | 0.561 | Apr-26 | 4.2295 | 4.2295 | 5 | 0.57 | 10004524 | 2025-03-13 | 2026-03-13 | 4.23 |  |  |  |  | 4.8 | 4.23 | Ok | 0.0005 |  |  |  | PO Released | Non SOBO
2026-11-30 | Satish Singh | 2026-11-30 | 232 Km Route | Co-Built | MUM_Route_35 | MUM_Route_35 | TRUE | 0.3564 | 1 | 0.066 | Nov-26 | 0.3564 | 0.3564 | 1 | 0.066 | 10004671 | 2025-03-24 | 2026-03-24 | 0.36 |  |  |  |  | 0.426 | 0.36 | Ok | 0.0036 |  |  |  | PO Released | Non SOBO
2026-04-30 | Satish Singh | 2026-04-30 | 232 Km Route | Co-Built | MUM_Route_36 | MUM_Route_36 | TRUE | 6.0324 | 2 | 0.902 | Apr-26 | 6.0324 | 3.6 | 2 | 0.24 | 10004962 | 2025-04-08 | 2026-04-08 | 3.6 |  |  |  |  | 3.84 | 3.6 | Route length decreased from 6032 to 3600 according to the new KML | -2.4324 | Shortfall | Not Ok |  | PO Released | Non SOBO
2026-01-31 | Satish Singh | 2026-01-31 | 232 Km Route | Co-Built | MUM_Route_37 | MUM_Route_37 | TRUE | 2.4915 | 1 | 0.11 | Jan-26 | 2.4915 | 2.62 | 1 | 0.11 | 10004535 | 2025-03-13 | 2026-03-13 | 2.62 |  |  |  |  | 2.73 | 2.62 | Ok | 0.1285 |  | Ok | 130 | PO Released | Non SOBO
2026-10-31 | Satish Singh | 2026-10-31 | 232 Km Route | Co-Built | MUM_Route_38 | MUM_Route_38 | TRUE | 3.1662 | 5 | 0.902 | Oct-26 | 3.0822 | 3.0822 | 5 | 0.85 | 10004674 | 2025-03-24 | 2026-03-24 | 3.08 |  |  |  |  | 3.93 | 3.08 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-10-31 | Satish Singh | 2026-10-31 | Additional Route | Co-Built | MUM_Route_38 | MUM_Route_137 | FALSE |  |  |  | Oct-26 | 0 | 0.3 |  |  | 10004674 | 2025-03-24 | 2026-03-24 | 0.3 |  |  |  |  | 0.3 | 0.3 | Ok | 0.3 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 232 Km Route | Co-Built | MUM_Route_4 | MUM_Route_4 | TRUE | 6.82 | 6 | 0.902 | Dec-26 | 6.82 | 6.82 | 6 | 0.79 | 10004522 | 2025-03-13 | 2026-03-13 | 6.82 |  |  |  |  | 7.61 | 6.82 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 89 Km Route | Co-Built | MUM_Route_4 | MUM_Route_144 | FALSE | 0.1 | 0 |  | Dec-26 | 0.1 | 0.1 |  | 0 | 10004541 | 2025-03-13 | 2026-03-13 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 89 Km Route | Co-Built | MUM_Route_4 | MUM_Route_143 | FALSE | 0.11 | 0 |  | Dec-26 | 0.11 | 0.11 |  | 0 | 10004541 | 2025-03-13 | 2026-03-13 | 0.11 |  |  |  |  | 0.11 | 0.11 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 89 Km Route | Co-Built | MUM_Route_4 | MUM_Route_146 | FALSE | 0.5 | 0 |  | Dec-26 | 0.5 | 0.5 |  | 0 | 10004541 | 2025-03-13 | 2026-03-13 | 0.5 |  |  |  |  | 0.5 | 0.5 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-12-31 | Satish Singh | 2026-12-31 | 89 Km Route | Co-Built | MUM_Route_4 | MUM_Route_145 | FALSE | 0.2 | 0 |  | Dec-26 | 0.2 | 0.2 |  | 0 | 10004541 | 2025-03-13 | 2026-03-13 | 0.2 |  |  |  |  | 0.2 | 0.2 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 232 Km Route | Co-Built | MUM_Route_42 | MUM_Route_42 | TRUE | 7.766 | 12 | 2.53 | Feb-26 | 7.766 | 7.766 | 12 | 2.04 | 10004961 | 2025-04-08 | 2026-04-08 | 7.77 |  |  |  |  | 9.81 | 7.77 | Ok | 0.004 | PO Awaited |  |  | PO Released | Non SOBO
2027-02-28 | Praveen Nigam | 2027-02-28 | 232 Km Route | IP1+Co-Built | MUM_Route_45 | MUM_Route_45 | TRUE | 19.3201 | 9 | 1.892 | Feb-27 | 18.3623 | 18.3623 | 9 | 1.47 | 10004670 | 2025-03-24 | 2026-03-24 | 6.432 | 10004678 | 2025-03-24 | 2026-03-24 | 11.93 | 19.832 | 18.362 | Ok | 0 |  |  |  | PO Released | Non SOBO
2027-02-28 | Praveen Nigam | 2025-09-30 | 52 Km Route | Co-Built | MUM_Route_45 | MUM_Route_24 | FALSE |  |  |  | Feb-27 | 0.9581 | 0.9581 |  |  | 10004670 | 2025-03-24 | 2026-03-24 | 0.96 |  |  |  |  | 0.96 | 0.96 | Ok | 0.0019 |  |  |  | PO Released | Non SOBO
2027-02-28 | Praveen Nigam | 2027-02-28 | Additional Route | Co-Built | MUM_Route_45 | MUM_STS_901 AGG | FALSE |  |  |  | Feb-27 | 0 | 0.15 |  |  | 10004670 | 2025-03-24 | 2026-03-24 | 0.15 |  |  |  |  | 0.15 | 0.15 | Ok |  |  |  |  | PO Released | Non SOBO
2025-05-31 | Praveen Nigam | 2025-07-31 | 232 Km Route | IP1 | MUM_Route_48 | MUM_Route_48 | TRUE | 4.7449 | 0 | 0.95 | May-25 | 3.2384 | 3.3 |  | 0 |  |  |  |  | 10004681 | 2025-03-24 | 2026-03-24 | 3.3 | 3.3 | 3.3 | Ok | 0.0616 |  |  |  | PO Released | Non SOBO
2025-05-31 | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_48 | MUM_Route_163 | FALSE |  |  |  | May-25 | 0.5555 | 0.56 |  |  | 10004682 | 2025-03-24 | 2026-03-24 | 0.231 |  |  |  |  | 0.231 | 0.231 | PO Cancelled | 0 |  |  |  | PO Cancelled | Non SOBO
2025-05-31 | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_48 | MUM_Route_164 & 165 | FALSE |  |  |  | May-25 | 0.231 | 0.231 |  |  | 10004682 | 2025-03-24 | 2026-03-24 | 0.56 |  |  |  |  | 0.56 | 0.56 | PO Cancelled | 0.329 |  |  |  | PO Cancelled | Non SOBO
2025-05-31 | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_48 | MUM_Route_167 | FALSE |  |  |  | May-25 | 0.11 | 0.11 |  |  | 10004681 | 2025-03-24 | 2026-03-24 | 0.11 |  |  |  |  | 0.11 | 0.11 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-05-31 | Praveen Nigam | 2025-09-30 | 89 Km Route | Co-Built | MUM_Route_48 | MUM_Route_168 | FALSE |  |  |  | May-25 | 0.11 | 0.11 |  |  | 10004681 | 2025-03-24 | 2026-03-24 | 0.11 |  |  |  |  | 0.11 | 0.11 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-03-31 | Praveen Nigam | 2026-03-31 | 232 Km Route | Co-Built | MUM_Route_49 | MUM_Route_49 | TRUE | 4.8675 | 1 | 0.055 | Mar-26 | 4.8675 | 2.8 | 1 | 0.055 | 10004665 | 2025-03-24 | 2026-03-24 | 2.8 |  |  |  |  | 2.855 | 2.8 | Ok..Route length decreased from 4867 to 2800 . | -2.0675 | Shortfall | Ok | -2007 | PO Released | Non SOBO
2025-05-31 | Praveen Nigam | 2025-07-31 | 232 Km Route | IP1 | MUM_Route_50 | MUM_Route_50 | TRUE | 6.0335 | 2 | 0.81825 | May-25 | 6.0335 | 6.0335 | 2 | 0.81825 |  |  |  |  | 10004765 | 2025-03-25 | 2026-03-25 | 6.03 | 6.8483 | 6.03 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-05-31 | Prem Verma | 2026-04-30 | 232 Km Route | IP1 | MUM_Route_54 | MUM_Route_54 | TRUE | 5.06 | 4 | 0.572 | May-25 | 5.06 | 5.06 | 4 | 0.572 |  |  |  |  | 10004637 | 2025-03-22 | 2026-03-22 | 5.06 | 5.632 | 5.06 | Ok | 0 |  |  |  | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-08-31 | 232 Km Route | IP1+Co-Built | MUM_Route_55 | MUM_Route_55 | TRUE | 14.005 | 11 | 1.6544 | Dec-25 | 14.0063 | 14.005 | 11 | 1.07 | 10005002 | 2025-05-06 | 2026-05-06 | 2.04 | 10004629 | 2025-03-25 | 2026-03-25 | 11.962 | 15.072 | 14.002 | Co-build PO received on 7 May-25 | -0.0043 | Shortfall | Ok | -1004 | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-08-31 | Additional Route | Co-Built | MUM_Route_55 | MUM_XNQ_901_LM | FALSE |  |  |  | Dec-25 | 0 | 0.1 |  |  | 10004628 | 2025-03-22 | 2026-03-22 | 0.1 |  |  |  |  | 0.1 | 0.1 | Ok |  |  |  |  | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-08-31 | Additional Route | Co-Built | MUM_Route_55 | NSE Mumbai_LM | FALSE |  |  |  | Dec-25 | 0 | 0.5 |  |  | 10004628 | 2025-03-22 | 2026-03-22 | 0.5 |  |  |  |  | 0.5 | 0.5 | Ok |  |  |  |  | PO Released | SOBO
2026-03-31 | Praveen Nigam | 2026-03-31 | 232 Km Route | Co-Built | MUM_Route_57 | MUM_Route_57 | TRUE | 4.8587 | 3 | 0.55 | Mar-26 | 4.8587 | 4.8587 | 3 | 0.39 | 10004659 | 2025-03-24 | 2026-03-24 | 4.86 |  |  |  |  | 5.25 | 4.86 | Ok | 0.0013 |  |  |  | PO Released | Non SOBO
2026-01-31 | Praveen Nigam | 2026-01-31 | 232 Km Route | Co-Built | MUM_Route_58 | MUM_Route_58 | TRUE | 4.785 | 1 | 0.385 | Jan-26 | 4.785 | 4.785 | 1 | 0.33 | 10004658 | 2025-03-24 | 2026-03-24 | 4.79 |  |  |  |  | 5.12 | 4.79 | Ok | 0.005 |  |  |  | PO Released | Non SOBO
2025-12-31 | Satish Singh | 2025-12-31 | 232 Km Route | Co-Built | MUM_Route_62 | MUM_Route_62 | TRUE | 0.3113 | 1 | 0.11 | Dec-25 | 0.3113 | 0.3113 | 1 | 0.1 | 10004599 | 2025-03-19 | 2026-03-19 | 0.9 |  |  |  |  | 1 | 0.9 | Ok | 0.5887 |  | Ok | 590 | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2026-02-28 | 52 Km Route | Co-Built | MUM_Route_68 | MUM_Route_68 | TRUE | 3.949 | 7 | 3.615 | Feb-26 | 3.949 | 3.95 | 7 | 0.41 | 10004657 | 2025-03-24 | 2026-03-24 | 3.95 |  |  |  |  | 4.36 | 3.95 | Ok | 0.001 |  |  |  | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2025-09-30 | 52 Km Route | Co-Built | MUM_Route_68 | MUM_Route_75 | FALSE | 0.563 | 0 |  | Feb-26 | 0.5632 | 0.563 |  | 0 | 10004657 | 2025-03-24 | 2026-03-24 | 0.563 |  |  |  |  | 0.563 | 0.563 | OK | 0 |  | Ok |  | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2025-09-30 | 52 Km Route | Co-Built | MUM_Route_68 | MUM_Route_118 | FALSE | 0.72 | 0 |  | Feb-26 | 0.6468 | 0.72 |  | 0 | 10004657 | 2025-03-24 | 2026-03-24 | 0.72 |  |  |  |  | 0.72 | 0.72 | OK | 0.0732 |  | Ok | 70 | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2025-09-30 | 52 Km Route | Co-Built | MUM_Route_68 | MUM_Route_74 | FALSE | 0.39 | 0 |  | Feb-26 | 0.2651 | 0.39 |  | 0 | 10004657 | 2025-03-24 | 2026-03-24 | 0.39 |  |  |  |  | 0.39 | 0.39 | OK | 0.1249 |  | Ok | 120 | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2025-09-30 | Additional Route | Co-Built | MUM_Route_68 | CapitaLand Data Centre (CDC)_LM | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 10004657 | 2025-03-24 | 2026-03-24 | 0.18 |  |  |  |  | 0.18 | 0.18 | OK |  |  |  |  | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2026-02-28 | Additional Route | Co-Built | MUM_Route_68 | Mercury Tower AGG_LM | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 10004657 | 2025-03-24 | 2026-03-24 | 1.2 |  |  |  |  | 1.2 | 1.2 | OK |  |  |  |  | PO Released | Non SOBO
2025-11-30 | Prem Verma | 2026-01-31 | 232 Km Route | IP1+Co-Built | MUM_Route_8 | MUM_Route_8 | TRUE | 14.283 | 14 | 2.664 | Nov-25 | 14.1955 | 14.195 | 14 | 2.23 | 10004619 | 2025-03-22 | 2026-03-22 | 2.424 | 10004632 | 2025-03-22 | 2026-03-22 | 11.771 | 16.425 | 14.195 | Ok | 0 |  |  |  | PO Released | SOBO
2025-11-30 | Praveen Nigam | 2026-01-31 | 232 Km Route | IP1 | MUM_Route_80 | MUM_Route_80 | TRUE | 5.068 | 5 | 0.759 | Nov-25 | 5.0677 | 5.068 | 5 | 0.759 |  |  |  |  | 10004639 | 2025-03-22 | 2026-03-22 | 5.07 | 5.829 | 5.07 | Ok | 0.0023 |  |  |  | PO Released | Non SOBO
2026-12-31 | Praveen Nigam | 2026-12-31 | 232 Km Route | Co-Built | MUM_Route_81 | MUM_Route_81 | TRUE | 12.4889 | 14 | 3.335 | Dec-26 | 11.9383 | 12.01 | 14 | 2.71 | 10004680 | 2025-03-24 | 2026-03-24 | 12.01 |  |  |  |  | 14.72 | 12.01 | Ok | 0.0717 |  | Ok | 70 | PO Released | Non SOBO
2026-12-31 | Praveen Nigam | 2025-09-30 | 52 Km Route | Co-Built | MUM_Route_81 | MUM_Route_46 | FALSE |  |  |  | Dec-26 | 0.4829 | 0.48 |  |  | 10004680 | 2025-03-24 | 2026-03-24 | 0.48 |  |  |  |  | 0.48 | 0.48 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-04-30 | Yogesh Deshpande | 2026-04-30 | 232 Km Route | Co-Built | MUM_Route_89 | MUM_Route_89 | TRUE | 4.8928 | 0 | 0 | Apr-26 | 4.8928 | 4.8928 | 0 | 0 | 10004675 | 2025-03-24 | 2026-03-24 | 4.89 |  |  |  |  | 4.89 | 4.89 | Ok | 0 |  |  |  | PO Released | Non SOBO
2027-01-31 | Praveen Nigam | 2027-01-31 | 232 Km Route | IP1+Co-Built | MUM_Route_90 | MUM_Route_90 | TRUE | 20.1707 | 7 | 1.8295 | Jan-27 | 20.1707 | 20.85 | 7 | 1.02 | 10004960 | 2025-04-08 | 2026-04-08 | 14.27 | 10004771 | 2025-03-25 | 2026-03-25 | 4.9 | 20.19 | 19.17 | Ok | -1.0007 | Shortfall | Not Ok |  | PO Released | Non SOBO
2027-01-31 | Praveen Nigam | 2025-11-30 | 89 Km Route | IP1+Co-Built | MUM_Route_90 | MUM_Route_166 | FALSE | 1.6841 | 0 | 0 | Nov-25 | 1.6841 | 1.6841 |  | 0 | 10004960 | 2025-04-08 | 2026-04-08 | 1.684 |  |  |  |  | 1.684 | 1.684 | Ok | 0 |  |  |  | PO Released | Non SOBO
2027-01-31 | Praveen Nigam | 2027-01-31 | Additional Route | Co-Built | MUM_Route_90 | Sapata Sangam_LM | FALSE |  |  |  | Nov-25 | 0 | 1.2 |  |  | 10004960 | 2025-04-08 | 2026-04-08 | 1.2 |  |  |  |  | 1.2 | 1.2 | Ok |  |  |  |  | PO Released | Non SOBO
2025-12-31 | Yogesh Deshpande | 2025-12-31 | 232 Km Route | Co-Built | MUM_Route_97 | MUM_Route_97 | TRUE | 14.9622 | 7 | 0.737 | Dec-25 | 15.0502 | 12 | 7 | 0.6 | 10004672 | 2025-03-24 | 2026-03-24 | 12 |  |  |  |  | 12.6 | 12 | Ok..old route no 11 overlaped length removed. | -3.0502 | Shortfall | Ok | -3005 | PO Released | Non SOBO
2025-12-31 | Prem Verma | 2025-12-31 | 52 Km Route | IP1 | MUM_Route_99 | MUM_Route_99 | TRUE | 1.9701 | 8 | 0.6082 | Dec-25 | 1.9701 | 1.9701 | 8 | 0.52 |  |  |  |  | 10004622 | 2025-03-22 | 2026-03-22 | 1.97 | 2.49 | 1.97 | Ok | 0 |  |  |  | PO Released | SOBO
2025-12-31 | Prem Verma | 2025-12-31 | Additional Route | Co-Built | MUM_Route_99 | BSE India_LM | FALSE |  |  |  |  | 0 | 1 | 0 | 0 | 10004624 | 2025-03-22 | 2026-03-22 | 1 |  |  |  |  | 1 | 1 | Ok |  |  |  |  | PO Released | SOBO
2026-03-31 | Satish Singh | 2026-03-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route1 | Mumbai_Coverage_Route1 | TRUE | 1.2089 | 1 | 0.011 | Mar-26 | 1.2089 | 1.2089 | 1 | 0.011 | 10004966 | 2025-04-15 | 2026-04-15 | 1.21 |  |  |  |  | 1.221 | 1.21 | Mira Road | 0.0011 | PO Awaited |  |  | PO Released | Non SOBO
2026-03-31 | Yogesh Deshpande | 2026-03-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route10 | Mumbai_Coverage_Route10 | TRUE | 1.4278 | 3 | 0.209 | Mar-26 | 1.4278 | 1.4278 | 3 | 0.29 | 10004527 | 2025-03-13 | 2026-03-13 | 1.43 |  |  |  |  | 1.72 | 1.43 | Ok | 0.0022 |  |  |  | PO Released | Non SOBO
2026-10-31 | Yogesh Deshpande | 2026-02-28 | 89 Km Route | Co-Built | Mumbai_Coverage_Route12 | Mumbai_Coverage_Route12 | TRUE | 4.4 | 4 | 0.1166 | Oct-26 | 4.4 | 4.4 | 4 | 1.17 | 10004542 | 2025-03-17 | 2026-03-17 | 4.4 |  |  |  |  | 5.57 | 4.4 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-11-30 | Yogesh Deshpande | 2026-11-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route13 | Mumbai_Coverage_Route13 | TRUE | 3.0294 | 6 | 1.0956 | Nov-26 | 3.0294 | 3.0294 | 6 | 1.88 | 10004545 | 2025-03-17 | 2026-03-17 | 3.03 |  |  |  |  | 4.91 | 3.03 | Ok | 0.0006 |  |  |  | PO Released | Non SOBO
2026-04-30 | Praveen Nigam | 2026-04-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route15 | Mumbai_Coverage_Route15 | TRUE | 1.5752 | 2 | 0.20403 | Apr-26 | 1.5752 | 1.5752 | 2 | 0.19 | 10004551 | 2025-03-17 | 2026-03-17 | 1.58 |  |  |  |  | 1.77 | 1.58 | Ok | 0.0048 |  |  |  | PO Released | Non SOBO
2026-01-31 | Satish Singh | 2026-05-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route17 | Mumbai_Coverage_Route17 | TRUE | 1.32 | 4 | 0.264 | Jan-26 | 1.32 | 1.32 | 4 | 0.36 | 10004552 | 2025-03-17 | 2026-03-17 | 1.32 |  |  |  |  | 1.68 | 1.32 | Ok | 0 |  |  |  | PO Released | Non SOBO
2025-10-31 | Satish Singh | 2025-10-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route2 | Mumbai_Coverage_Route2 | TRUE | 0.9075 | 1 | 0.011 | Oct-25 | 0.9075 | 0.9075 | 1 | 0.011 | 10004553 | 2025-03-17 | 2026-03-17 | 0.91 |  |  |  |  | 0.921 | 0.91 | Ok | 0.0025 |  |  |  | PO Released | Non SOBO
2026-10-31 | Yogesh Deshpande | 2026-10-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route21 | Mumbai_Coverage_Route21 | TRUE | 2.937 | 5 | 0.561 | Oct-26 | 2.937 | 2 | 5 | 0.86 | 10004564 | 2025-03-17 | 2026-03-17 | 2 |  |  |  |  | 2.86 | 2 | Ok End taping point changed length decreased to 2km from original route length of 2.9km. | -0.937 | Shortfall | Ok | -940 | PO Released | Non SOBO
2026-12-31 | Yogesh Deshpande | 2026-12-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route23 | Mumbai_Coverage_Route23 | TRUE | 1.7556 | 4 | 0.055 | Dec-26 | 1.7556 | 1.7556 | 4 | 0.18 | 10004554 | 2025-03-17 | 2026-03-17 | 1.76 |  |  |  |  | 1.94 | 1.76 | Ok | 0.0044 |  |  |  | PO Released | Non SOBO
2026-11-30 | Satish Singh | 2026-11-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route25 | Mumbai_Coverage_Route25 | TRUE | 1.65 | 4 | 0.275 | Nov-26 | 1.65 | 1.65 | 4 | 1.23 | 10004569 | 2025-03-18 | 2026-03-18 | 1.65 |  |  |  |  | 2.88 | 1.65 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-10-31 | Satish Singh | 2026-10-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route28 | Mumbai_Coverage_Route28 | TRUE | 1.8623 | 2 | 0.0825 | Oct-26 | 1.8623 | 1.8623 | 2 | 0.07 | 10004511 | 2025-03-11 | 2026-03-11 | 1.86 |  |  |  |  | 1.93 | 1.86 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-04-30 | Satish Singh | 2026-04-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route29 | Mumbai_Coverage_Route29 | TRUE | 2.0603 | 5 | 0.7351 | Apr-26 | 2.0603 | 2.4 | 5 | 0.63 | 10004540 | 2025-03-13 | 2026-03-13 | 2.4 |  |  |  |  | 3.03 | 2.4 | Ok..Route length is increased from 2.06 to 2.40km | 0.3397 |  | Ok | 340 | PO Released | Non SOBO
2026-04-30 | Satish Singh | 2026-04-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route3 | Mumbai_Coverage_Route3 | TRUE | 2.2 | 8 | 0.385 | Apr-26 | 2.2 | 2.2 | 8 | 0.37 | 10004544 | 2025-03-17 | 2026-03-17 | 2.2 |  |  |  |  | 2.57 | 2.2 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-11-30 | Satish Singh | 2026-11-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route30 | Mumbai_Coverage_Route30 | TRUE | 2.0537 | 3 | 0.176 | Nov-26 | 2.0537 | 2.0537 | 3 | 0.22 | 10004566 | 2025-03-18 | 2026-03-18 | 2.05 |  |  |  |  | 2.27 | 2.05 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-02-28 | Yogesh Deshpande | 2026-02-28 | 89 Km Route | Co-Built | Mumbai_Coverage_Route31 | Mumbai_Coverage_Route31 | TRUE | 1.7765 | 6 | 0.6215 | Feb-26 | 1.7765 | 2.2 | 6 | 0.47 | 10004578 | 2025-03-18 | 2026-03-18 | 2.2 |  |  |  |  | 2.67 | 2.2 | Ok..Route length is increased from 1.78 to 2.20km | 0.4235 |  | Ok | 420 | PO Released | Non SOBO
2026-03-31 | Yogesh Deshpande | 2026-03-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route32 | Mumbai_Coverage_Route32 | TRUE | 6.7452 | 3 | 0.132 | Mar-26 | 6.7452 | 6.7452 | 3 | 0.33 | 10004543 | 2025-03-17 | 2026-03-17 | 6.75 |  |  |  |  | 7.08 | 6.75 | Ok | 0.0048 |  |  |  | PO Released | Non SOBO
2026-03-31 | Yogesh Deshpande | 2026-03-31 | Additional Route | Co-Built | Mumbai_Coverage_Route32 | Gopi Cinema_AGG_LM | FALSE | 0 | 0 | - |  | 0 | 0.38 | 0 | 0 | 10004555 | 2025-03-17 | 2026-03-17 | 0.38 |  |  |  |  | 0.38 | 0.38 | OK |  |  |  |  | PO Released | Non SOBO
2026-02-28 | Praveen Nigam | 2026-02-28 | 89 Km Route | Co-Built | Mumbai_Coverage_Route33 | Mumbai_Coverage_Route33 | TRUE | 4.8565 | 3 | 0.287 | Feb-26 | 4.8565 | 4.8565 | 3 | 0.26 | 10004565 | 2025-03-18 | 2026-03-18 | 4.86 |  |  |  |  | 5.12 | 4.86 | Ok | 0.0035 |  |  |  | PO Released | Non SOBO
2025-12-31 | Satish Singh | 2025-12-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route34 | Mumbai_Coverage_Route34 | TRUE | 1.595 | 2 | 0.612 | Dec-25 | 1.595 | 1.595 | 2 | 0.612 | 10004968 | 2025-04-15 | 2026-04-15 | 1.6 |  |  |  |  | 2.212 | 1.6 | Mira Road | 0.005 | PO Awaited |  |  | PO Released | Non SOBO
2026-10-31 | Satish Singh | 2026-10-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route35 | Mumbai_Coverage_Route35 | TRUE | 4.07 | 5 | 0.55 | Oct-26 | 4.07 | 4.07 | 5 | 0.64 | 10004963 | 2025-04-08 | 2026-04-08 | 4.07 |  |  |  |  | 4.71 | 4.07 | Ok | 0 | Shortfall | Not Ok |  | PO Released | Non SOBO
2026-02-28 | Satish Singh | 2026-02-28 | 89 Km Route | Co-Built | Mumbai_Coverage_Route36 | Mumbai_Coverage_Route36 | TRUE | 0.869 | 1 | 0.033 | Feb-26 | 0.869 | 0.869 | 1 | 0.033 | 10004584 | 2025-03-18 | 2026-03-18 | 0.87 |  |  |  |  | 0.903 | 0.87 | Ok | 0.001 |  |  |  | PO Released | Non SOBO
2026-04-30 | Prem Verma | 2026-04-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route37 | Mumbai_Coverage_Route37 | TRUE | 2.0295 | 3 | 0.3608 | Apr-26 | 2.0295 | 1.9 | 3 | 0.2 | 10004575 | 2025-03-18 | 2026-03-18 | 1.9 |  |  |  |  | 2.1 | 1.9 | Ok..End taping point changed length is decreased from 2.03 to 1.90km. | -0.1295 | Shortfall | Ok | -130 | PO Released | SOBO
2026-03-31 | Prem Verma | 2026-03-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route38 | Mumbai_Coverage_Route38 | TRUE | 2.057 | 3 | 0.32173 | Mar-26 | 2.057 | 2.3 | 3 | 1.35 | 10004967 | 2025-04-15 | 2026-04-15 | 2.3 |  |  |  |  | 3.65 | 2.3 | PO cancelled | 0.243 |  | Ok | 240 | PO Released | SOBO
2026-12-31 | Yogesh Deshpande | 2026-12-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route39 | Mumbai_Coverage_Route39 | TRUE | 2.311 | 4 | 1.149 | Dec-26 | 2.3111 | 2.311 | 4 | 0.87 | 10004570 | 2025-03-18 | 2026-03-18 | 2.31 |  |  |  |  | 3.18 | 2.31 | Ok | 0 |  |  |  | PO Released | Non SOBO
#N/A | Prem Verma | 2026-12-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route4 | Mumbai_Coverage_Route 4 | FALSE | 2.178 | 1 | 0.099 | Dec-26 | 2.178 | 1.5 | 1 | 0.099 | 10004560 | 2025-03-17 | 2026-03-17 | 1.5 |  |  |  |  | 1.599 | 1.5 | Ok length is decreased 2.18 to 1.5 | -0.678 | Shortfall | Ok | -680 | PO Released | SOBO
2026-05-31 | Prem Verma | 2026-05-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route5 | Mumbai_Coverage_Route5 | TRUE | 2.321 | 3 | 0.099 | May-26 | 2.321 | 1.9 | 3 | 0.2 | 10004529 | 2025-03-13 | 2026-03-13 | 1.9 |  |  |  |  | 2.1 | 1.9 | PO Modification WIP | -0.421 | PO Awaited |  |  | PO Modification WIP | Non SOBO
2026-12-31 | Prem Verma | 2026-12-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route6 | Mumbai_Coverage_Route6 | TRUE | 1.98 | 3 | 0.337 | Dec-26 | 1.98 | 1.98 | 3 | 0.2 | 10004563 | 2025-03-17 | 2026-03-17 | 1.98 |  |  |  |  | 2.18 | 1.98 | Ok | 0 |  |  |  | PO Released | Non SOBO
2026-05-31 | Yogesh Deshpande | 2025-06-30 | 89 Km Route | Co-Built | Mumbai_Coverage_Route7 | Mumbai_Coverage_Route7 | TRUE | 2.5872 | 5 | 0.308 | May-26 | 2.5872 | 2.5872 | 5 | 0.308 | 10004531 | 2025-03-13 | 2026-03-13 | 2.59 |  |  |  |  | 2.898 | 2.59 | Ok | 0.0028 |  |  |  | PO Released | Non SOBO | FF_NW2122_785420
2026-03-31 | Yogesh Deshpande | 2026-03-31 | 89 Km Route | Co-Built | Mumbai_Coverage_Route9 | Mumbai_Coverage_Route9 | TRUE | 3.7719 | 4 | 0.6105 | Mar-26 | 3.7719 | 3.77 | 4 | 0.54 | 10004532 | 2025-03-13 | 2026-03-13 | 3.77 |  |  |  |  | 4.31 | 3.77 | Ok | 0 |  |  |  | PO Released | Non SOBO
#N/A | Prem Verma | 2026-04-30 | Additional Route | IP1 | Route55 to Route 107 | Route55 to Route 107 | TRUE |  |  |  |  | 0 | 0.6 | 0 | 0 |  |  |  |  | 10004623 | 45738 | 46103 | 0.6 | 0.6 | 0.6 | OK | 0.6 |  | Ok | 600 | PO Released | Non SOBO
#N/A | Prem Verma | 2026-05-31 | Mono Rail | IP1 | Tamil Sangham to Guru Teg Bahadur Nagar Station | Tamil Sangham to Guru Teg Bahadur Nagar Station | TRUE |  |  |  |  | 0 | 2.273 | 3 | 0.41 |  |  |  |  | 10004971 | 45764 | 46129 | 2.273 | 2.683 | 2.273 | Ok |  |  |  |  | PO Released | Non SOBO
#N/A | Prem Verma | 2026-04-30 | Mono Rail | IP1 | Sant Gadge Maharaj Chowk to NM Joshi Marg | Sant Gadge Maharaj Chowk to NM Joshi Marg | TRUE |  |  |  |  | 0 | 0.88 | 0 | 0 |  |  |  |  | 10004974 | 45764 | 46129 | 0.88 | 0.88 | 0.88 | Ok |  |  |  |  | PO Released | SOBO
#N/A | Prem Verma | 2026-04-30 | Mono Rail | IP1+Co-Built | Center Point to Mint Colony Station | Center Point to Mint Colony Station | TRUE |  |  |  |  | 0 | 0.75 | 0 | 0 | 10004973 | 2025-04-17 | 2026-04-17 | 0.2 | 10004973 | 45764 | 46129 | 0.55 | 0.75 | 0.75 | Ok |  |  |  |  | PO Released | SOBO
#N/A | Prem Verma | 2026-04-30 | Mono Rail | Co-Built | Jairamdas to VNP & RC Marg Junction Station | Jairamdas to VNP & RC Marg Junction Station | TRUE |  |  |  |  | 0 | 1 | 0 | 0 | 10004972 | 2025-04-17 | 2026-04-17 | 1 |  |  |  |  | 1 | 1 | Ok |  |  |  |  | PO Released | Non SOBO
Formulas:
ac = XLOOKUP([Parent Route],'[1]Edited_Route+LM'!$D:$D,'[1]Edited_Route+LM'!$K:$K)
PO End Date = [PO Date]+365
Delivery month = XLOOKUP([Sub-Routes],'[1]Edited_Route+LM'!$D:$D,'[1]Edited_Route+LM'!$K:$K)
Delivery month = [ac]

## Sheet2 (hidden)
Sr No | Parent Route | Sub-Routes | PO No | PO Length
1 | MUM_Route_48 | MUM_Route_163 | 10004682 | 0.231 | 2025-09-30
2 | MUM_Route_48 | MUM_Route_164 & 165 | 10004682 | 0.56 | 2025-09-30
3 | MUM_Route_48 | MUM_Route_167 | 10004682 | 0.11 | 2025-09-30
4 | MUM_Route_48 | MUM_Route_168 | 10004682 | 0.11 | 2025-09-30
5 | MUM_Route_45 | MUM_Route_24 | 10004670 | 0.96 | 2025-09-30
6 | MUM_Route_68 | MUM_Route_75 | 10004657 | 0.56 | 2025-09-30
7 | MUM_Route_68 | MUM_Route_118 | 10004657 | 0.72 | 2025-09-30
8 | MUM_Route_68 | MUM_Route_74 | 10004657 | 0.39 | 2025-09-30
9 | MUM_Route_68 | CapitaLand Data Centre (CDC)_LM | 10004657 | 0.18 | 2025-09-30
10 | MUM_Route_150 & 151 | MUM_Route_150 & 151 | 10004667 | 0.42 | 2025-09-30
11 | MUM_Route_155 | MUM_Route_155 | 10004683 | 1.5 | 2025-09-30
12 | MUM_Route_140 | MUM_Route_140 | 10004655 | 0.07 | 2025-09-30
13 | MUM_Route_81 | MUM_Route_46 | 10004680 | 0.48 | 2025-09-30
14 | MUM_Route_113 | MUM_Route_136 | 10004596 | 0.14 | 2025-09-30
15 | MUM_Route_113 | MUM_Route_135 | 10004596 | 0.44 | 2025-10-31
16 | MUM_Route_23 | MUM_Route_173 | 10004959 | 0.55 | 2025-10-31
17 | MUM_Route_139 | MUM_Route_138 | 10004653 | 0.05 | 2025-10-31
18 | MUM_Route_139 | MUM_Route_139 | 10004653 | 0.05 | 2025-10-31
19 | MUM_Route_155 | MUM_Route_155 | 10004683 | 1.5 | 2025-10-31
20 | MUM_Route_150 & 151 | MUM_Route_150 & 151 | 10004667 | 0.42 | 2025-10-31
21 | MUM_Route_169 | MUM_Route_169 | 10004666 | 1.11 | 2025-10-31
22 | MUM_Route_170 | MUM_Route_170 | 10004652 | 1.11 | 2025-10-31
23 | MUM_Route_156 | MUM_Route_156 | 10004673 | 0.5 | 2025-10-31

## Sheet5 (hidden)
Row Labels | Sum of PO Length (Mtr)
<30-04-2025 | 0
2025 | 16039
Qtr2 | 11312
Apr | 4003
May | 7309
Qtr4 | 4727
Oct | 255
Nov | 350
Dec | 4122
2026 | 26301
Qtr1 | 8231
Jan | 3182
Feb | 1296
Mar | 3753
Qtr2 | 9194
Apr | 2858
May | 6336
Qtr4 | 8876
Oct | 3929
Nov | 3451
Dec | 1496
2027 | 3155
Grand Total | 45495

## Sheet6
Categaory | (All)
Revised delivery | (Multiple Items)
Row Labels | Sum of PO Length (Mtr)
Praveen Nigam | 4467
Prem Verma | 2680
Satish Singh | 6286
Yogesh Deshpande | 8189
Grand Total | 21622

## Sheet3
Row Labels | Count of Authority | Sum of PO Length (Mtr)
0 | 1 | 10
JNPT | 1 | 246
KDMC | 81 | 13063
MBMC | 29 | 3374
MCGM | 403 | 44758
MMRDA | 2 | 250
MSRDC | 3 | 0
NMMC | 75 | 12953
PMC | 39 | 7334
TMC | 64 | 7327
Grand Total | 698 | 89315

## 684 POP
[8 empty] | 128103.0844 | 114554.6192 | [19 empty] | 89315 |  | 4515.0368 | [10 empty] | -80112
for formula | Revised delivery | Sr No. | Circle | Area | asd | SiteID | UID | Airtel Length-Mtr | CE-Length-Mtr | Lat | Long | Parent Route Name / HH | Sub Route | Authority | Ward | Site Name | Address | TOCO | Category | Modality | Remarks | Tentative Month of Delivery | Engineer Name | Manager Name | Revised Feasible Status | PO No | PO Date | PO End Date | PO Length (Mtr) | PO-Remark | GAP | Allocateion Status | Part of 99 | Demand Note Status | UID | CWIP ID | RFI Status | 2025-04-18 | Job ID | PE NAME | Aplication Length | PO Length Amendment | PO LA Approval | Alternate | Planning KML | ff
|  | 1 | MU | Airoli |  | MB817 | MU-MB817 | 165 | 165 | 19.174 | 72.9931 | 19.1749 | 72.9933 | NMMC | - | Gigaplex IT Park-Buidling No.09 | MIDC, Plot No 1 I.T.5,Airoli Knowledge Park Rd, TTC Industrial Area, Airoli , Navi Mumbai, Maharashtra 400708.. | FIREFLY | Fibmax | Co-build | Feasible | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-01-31 | 2 | MU | Dahisar |  | MA3428 | MU-MA3428 | 55 | 55 | 19.2547 | 72.8695 | 19.2545 | 72.8697 | MCGM | R/N | Dahiser fly over | Near check naka dhaiser east,Dahisar, Mumbai, Maharashtra- 400068 | Suyog | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004817 | 2025-03-26 | 2026-03-26 | 55 | PO Pending |  | PO Released-Hold by Airtel | - |  | Not created | CWIP-76775 | Received | PO Released | - |  | 0 | -55 | -
Fibmax | 2026-05-31 | 3 | MU | Kandivali |  | 6195 | MU-6195 | 242 | 242 | 19.2128 | 72.8744 | 19.2135 | 72.8745 | MCGM | R/S | THAKURHSOF | Thakur Shyamnarayan school,opp evershine green park,thakur villege,kandivali(e) | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004835 | 2025-03-26 | 2026-03-26 | 242 | PO length is less than Feasibility length | 0 | PO Released | Part of 99 |  | FF_NW1920_14557 | CWIP-76776 | RFAI Awaited | PO Released | 719431 | Santosh Yadav | 65 | -177 | - |  | Yes
|  | 4 | MU | Santacruz |  | MB1474 | MU-MB1474 | 11 | 11 | 19.0803 | 72.8472 | 19.0801 | 72.8472 | MCGM | H/E | Santacruz FOB | Santacruz FOB , Nehru Rd, Anand Nagar, Vakola, Santacruz East, Mumbai, Maharashtra 400055 | Suyog | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | CWIP-21505 | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-05-31 | 5 | MU | Vile Parle |  | MA2736 | MU-MA2736 | 22 | 22 | 19.0847 | 72.8339 | 19.0847 | 72.834 | MCGM | H/W | Muslim Mazlish | opp juhu police station juhu tara road Santa kruz west | INDUS | Fibmax | Co-build | Feasible | May'25 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 22 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15320 | CWIP-76777 | RFAI Awaited | PO Released | 457140 | Santosh Yadav | 5 | -17 | - |  | No
Fibmax | 2026-05-31 | 6 | MU | Andheri |  | MA5407 | MU-MA5407 | 11 | 11 | 19.1303 | 72.8187 | 19.1301 | 72.8184 | MCGM | K/W | P-05_Varsova | WM-P-05_VARSOVA, VERSOVA, ANDHERI WEST,MUMBAI, MAHARASHTRA 400061 | INDUS | Fibmax | Co-build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 11 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15395 | CWIP-76778 | RFAI Awaited | PO Released | - |  | 0 | -11 | - |  | No
Fibmax | 2026-01-31 | 7 | MU | Shahad |  | MB2460 | MU-MB2460 | 168 | 168 | 19.2481 | 73.1535 | 19.2479 | 73.1536 | KDMC | - | Yogidham Canbera CHSL | Building No:-D13,Yogidham Clifton Co-Operative Housing Society,Opposite Yogidham Clubhouse, Kalyan-Murbad Road, Kalyan, Maharashtra 421301 | Purple Soil | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004739 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76779 | RFAI Awaited | PO Released | - |  | 0 | -168 | -
|  | 8 | MU | Kalyan |  | MA3795 | MU-MA3795 | 224 | 224 | 19.2414 | 73.1478 | 19.2414 | 73.1478 | KDMC | - | Hotel Heritage | KALYAN-MURBAD RD, CHOWK, MURBAD ROAD, OPP. HERITAGE HOTEL, PURNIMA, KALYAN, MUMBAI, MAHARASHTRA. 421301 | Microqual | Fibmax | Co-build | Feasible | April'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-05-31 | 9 | MU | Khadakpada |  | MA4535 | MU-MA4535 | 280 | 280 | 19.2529 | 73.1448 | 19.2527 | 73.1441 | KDMC | - | Kene Plot | BHOIRWADI, KALYAN, MAHARASHTRA PINCODE- 421301 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004768 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785455 | CWIP-76780 | Received | PO Released | - |  | 0 | -280 | Pending |  | Yes
Fibmax | 2026-02-28 | 10 | MU | Kalyan |  | 5592 | MU-5592 | 280 | 280 | 19.2483 | 73.1433 | 19.2485 | 73.1436 | KDMC | - | Uma Darshan | Uma Darshan,Opp Birla Collage,Kalyan West | ATC | Fibmax | Co-build | Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004748 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76781 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-05-31 | 11 | MU | Khadakpada |  | 274 | MU-274 | 224 | 224 | 19.2555 | 73.1397 | 19.2549 | 73.1395 | KDMC | - | MANGALA PARK | MANGALA PARK,GODREJ HILL ROAD,KHADAKPADA,KALYAN (W), 421301 | INDUS | Fibmax | Co-build | Feasible | April'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004742 | 2025-03-25 | 2026-03-25 | 224 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785456 | CWIP-76782 | RFAI Awaited | PO Released | - |  | 0 | -224 | Pending |  | Yes
Fibmax | 2026-05-31 | 12 | MU | Khadakpada |  | 855 | MU-855 | 168 | 168 | 19.261 | 73.1339 | 19.2605 | 73.1337 | KDMC | - | kharbhari Gala | kharbhari Gala,Gandhari,nr.Golden wok hotel,Adharwadi jail Rd,Kalyan (w) 421301 | Suyog | Fibmax | Co-build | Feasible | April'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released-Hold by Airtel | Part of 99 |  | FF_NW1920_15047 | CWIP-76783 | Received | PO Released | - |  | 0 | -168 | Pending
|  | 13 | MU | Kalyan |  | MA6103 | MU-MA6103 | 224 | 224 | 19.2128 | 73.1321 | 19.2124 | 73.1321 | KDMC | - | SADGURU VILLA | SADGURU VILLA NANDIWALI KALYAN, | High G | Fibmax | Co-build | Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-02-28 | 14 | MU | Kalyan |  | MB3478 | MU-MB3478 | 112 | 112 | 19.2242 | 73.1303 | 19.2249 | 73.1302 | KDMC | - | Vijushree Elite | VIJUSHREE ELITE,BUILDING NO. 1,SANTOSH NAGAR, KALYAN, MAHARASHTRA . POST OFFICE:-KALYAN,POLICE STATION:- KALYAN | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004718 | 2025-03-24 | 2026-03-24 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76784 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-02-28 | 15 | MU | Kalyan |  | 5709 | MU-5709 | 112 | 112 | 19.2398 | 73.1223 | 19.2398 | 73.1224 | KDMC | - | Aksa Tower | Aksa Tower,Opp Memon Masjid,Valipeer Road,Kalyan(W) Mumbai-421301 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004767 | 2025-03-25 | 2026-03-25 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76785 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-01-31 | 16 | MU | Dombivali |  | 6520 | MU-6520 | 224 | 224 | 19.2125 | 73.0825 | 19.2125 | 73.0825 | KDMC | - | New Ayre Rd_Pandurang Niwas | Pandurang Niwas,New ayera Road,sainath Nagar,Near Sai baba Mandir,Dombivali(E),Mumbai | ATC | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004774 | 2025-03-25 | 2026-03-25 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76786 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-01-31 | 17 | MU | Shilphata |  | 1251 | MU-1251 | 168 | 168 | 19.1445 | 73.0515 | 19.1441 | 73.0518 | TMC | - | SHILPATAO | Survey No 87, Hissa No 2, Village Digar, Shilphata, Taluka Thane 421204 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004763 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76787 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
| 2026-01-31 | 18 | MU | Diva |  | 1256 | MU-1256 | 896 | 896 | 19.1907 | 73.0444 | 19.1865 | 73.0398 | TMC | - | DIVATOWEO | Survey No 41/2, Navin (Shart), Talathi-Diva, Taluka Thane-400612 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | Received | Under validation | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-02-28 | 19 | MU | Koparkhairane |  | MB4699 | MU-MB4699 | 134.4 | 134.4 | 19.1053 | 73.0283 | 19.1048 | 73.0282 | NMMC | - | Aramex India Pvt Ltd_Mahape | ABHINAV BUILDING,PLOT-P-107,TTC INDUSTRIAL AREA,MIDC,MAHAPE | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004715 | 2025-03-24 | 2026-03-24 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76788 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
|  | 20 | MU | Sanpada |  | MB1935 | MU-MB1935 | 224 | 224 | 19.0639 | 73.025 | 19.0629 | 73.0248 | NMMC | - | SB Communication | SB Communication, Plot No:-D-30/6, MIDC Industrial Area, Turbhe, Navi Mumbai, Maharashtra 400613. Post Office:-Turbhe, Police Station:-Turbhe, Thane | INDUS | Fibmax | Co-build | Feasible | April'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-02-28 | 21 | MU | Ghansoli |  | 4719 | MU-4719 | 112 | 112 | 19.114 | 73.0055 | 19.1141 | 73.0054 | NMMC | - | BLSMCHS | Blossoms Chs,Plot No:11 , Sector 3 , Npore Durges , Ghanjoli , Navi Mumbai-400701 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004773 | 2025-03-25 | 2026-03-25 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76789 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-02-28 | 22 | MU | Ghansoli |  | 4971 | MU-4971 | 100 | 0 | 19.1197 | 73.0003 | 19.1197 | 73.0002 | NMMC | - | OMGANESHO | Om Ganesh, Sector 6, Kopar Khairne, Thane - Belapur Highway, Mumbai-400701 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 100 | Ok | 100 | PO Released | - |  | Not created | CWIP-76790 | RFAI Awaited | PO Released | - |  | 0 | -100 | - |  | Yes
Fibmax | 2026-05-31 | 23 | MU | Thane |  | 5979 | MU-5979 | 280 | 280 | 19.1951 | 72.971 | 19.195 | 72.9706 | TMC | - | Vandana Cinema | VANDANA S.T.DEPO,LBS ROAD, PANCH-PAKHDI, THANE WEST, 400602 | Crest Digitel | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004744 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76791 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
Fibmax | 2026-05-31 | 24 | MU | Vartak Nagar |  | 2610 | MU-2610 | 168 | 168 | 19.2107 | 72.9611 | 19.2103 | 72.9611 | TMC | - | NarmadaBldg | NARMADABLDG, LOKMANYA NAGAR, THANE WEST, DISTRICT-THANE, STATE-MAHARASHTRA, PINCODE- 400606 | ATC | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004769 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76792 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-05-31 | 25 | MU | Vartak Nagar |  | MA1044 | MU-MA1044 | 168 | 168 | 19.2084 | 72.9601 | 19.2087 | 72.96 | TMC | - | Smelting Koras Road-1 | Smelting Koras Road, Vartak Nagar, Thane West | ATC | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004866 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76793 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-05-31 | 26 | MU | Mulund |  | 4234 | MU-4234 | 56 | 56 | 19.1737 | 72.951 | 19.1734 | 72.9508 | MCGM | T | KALPAVRUOF | Kalpvruksha CHS,RHB Rd. mulund(W) | INDUS | Fibmax | Co-build | Feasible | May'25 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004714 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released | Part of 99 |  | FF_CF1819_375 | CWIP-76794 | RFAI Awaited | PO Released | - |  | 0 | -56 | - |  | Yes
Fibmax | 2026-05-31 | 27 | MU | Thane |  | 3123 | MU-3123 | 280 | 280 | 19.1912 | 72.9457 | 19.1912 | 72.947 | TMC | - | shinde estate office | SHINDE ESTATE OFFICE , OPPO MAVIS GYM ,SHREENAGER WAGHALE ESTATE THANE(W), MUMBAI, MAHARASHTRA. | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004825 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76795 | Received | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-12-31 | 28 | MU | Vartak Nagar |  | MA4012 | MU-MA4012 | 112 | 112 | 19.1976 | 72.9454 | 19.1972 | 72.9455 | TMC | - | Khan Shop | PLOT NO. 162-164, RD NUMBER 27, WAGLE INDUSTRIAL ESTATE,THANE WEST, STATE-MAHARASHTRA, PINCODE-400604 | Suyog | Fibmax | Co-build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004846 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76796 | Received | PO Released | - |  | 0 | -112 | -
Fibmax | 2026-05-31 | 29 | MU | Mulund |  | 4381 | MU-4381 | 56 | 56 | 19.1685 | 72.945 | 19.1683 | 72.945 | MCGM | T | AIROTAQQOMM1 | Airota Ind Estate,NEAR SATSANG HALL, POOJA BLOOD BANK,P K ROAD,MULUND W | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004777 | 2025-03-26 | 2026-03-26 | 56 | Ok | 0 | PO Released | - |  | Not created | CWIP-76797 | Received | PO Released | - |  | 0 | -56 | - |  | Yes
Fibmax | 2026-12-31 | 30 | MU | Kanjurmarg East |  | 1342 | MU-1342 | 56 | 56 | 19.141 | 72.9374 | 19.1412 | 72.9377 | MCGM | S | CGHS Colony_CCTV | C.G.S. Colony, BhandupEast, Mumbai,Maharashtra400042 | Suyog | Fibmax | Co-build | Feasible | Jan'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004703 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76798 | Received | PO Released | - |  | 0 | -56 | -
Fibmax | 2026-05-31 | 31 | MU | Chembur |  | MA1811 | MU-MA1811 | 78.4 | 78.4 | 19.0531 | 72.9139 | 19.0527 | 72.9141 | MCGM | M/E | Hashu Adwani School | BS Devashi Marg, Patwardhan Colony, Govandi East, Mumbai, Maharashtra 400088 | ATC | Fibmax | Co-build | Feasible | Feb'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004697 | 2025-03-24 | 2026-03-24 | 78 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76799 | RFAI Awaited | PO Released | - |  | 0 | -78 | - |  | Yes
| 2026-05-31 | 32 | MU | Ghatkoper |  | 3463 | MU-3463 | 67.2 | 67.2 | 19.1038 | 72.9116 | 19.1038 | 72.9116 | MCGM | N | Ashish CHS | Amrut Nagar, Ghatkopar West, Mumbai-400086 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | - |  |  | 0 | PO length is greater than Feasibility Length | -67.2 | PO Cancelled | - |  | Not created | CWIP-76800 | - | PO Modification WIP | - |  | 0 | 0 | - |  | Yes
|  | 33 | MU | Andheri |  | 1420 | MU-1420 | 33.6 | 33.6 | 19.1216 | 72.8855 | 19.1216 | 72.8857 | MCGM | K/E | SHIVAM APT | Near Ganesh Pada Bus Stop, Military Road, Marol, Andheri East-400059 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-05-31 | 34 | MU | Miraroad |  | MB2148 | MU-MB2148 | 44.8 | 44.8 | 19.2764 | 72.8789 | 19.2765 | 72.8787 | MBMC | - | Poonam Green CHS | A-102,New Poonam Green co op society, near Fashion Factory, Pleasant Park, Mira Road East, Maharashtra 401107,post office:-Mira Road,police station:-Mira Road | INDUS | Fibmax | Co-build | Feasible | April'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004849 | 2025-03-26 | 2026-03-26 | 45 | Ok | 0.2 | PO Released | Part of 99 |  | FF_NW2122_785457 | CWIP-76801 | RFAI Awaited | PO Released | - |  | 90 | 45 | Pending |  | Yes
Fibmax | 2025-12-31 | 35 | MU | Miraroad |  | MA2816 | MU-MA2816 | 112 | 112 | 19.2805 | 72.877 | 19.2805 | 72.877 | MBMC | - | Ankur bld_Samruddhi Bldg_Crack | SAMRUDHI BLDG , HATKESH UDYOG MIRA BHYANDER ROAD MIRA ROAD EAST, MUMBAI, MAHARASHTRA.t | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004706 | 2025-03-24 | 2026-03-24 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76802 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-11-30 | 36 | MU | Sion |  | MA2877 | MU-MA2877 | 78.4 | 78.4 | 19.0526 | 72.875 | 19.0529 | 72.8751 | MCGM | L | Akansha CHSL | Near ashirwad hotel, VN Purav Road, Samarth Nagar,Chuna Bhatti, Sion Mumbai | ATC | Fibmax | Co-build | Feasible | March'26 | Swapnil Salvi | Prem Verma | Feasible | 10004821 | 2025-03-26 | 2026-03-26 | 78 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76803 | RFAI Awaited | PO Released | - |  | 0 | -78 | - |  | Yes
Fibmax | 2026-11-30 | 37 | MU | Goregaon |  | MA18 | MU-MA18 | 123.2 | 123.2 | 19.1762 | 72.8745 | 19.1759 | 72.8743 | MCGM | P/N | Muneer House_Crack GBT | Muneer,Gala no.3 Khadakpada near film citi road malad east, Azad Nagar, Sankalp Colony,Gokuldham Colony, Goregaon, Mumbai, Maharashtra 400097 | Suyog | Fibmax | Co-build | Feasible | March'26 | Virendra | Satish Singh | Feasible | 10004730 | 2025-03-24 | 2026-03-24 | 123 | PO Pending |  | PO Released-Hold by Airtel | - |  | Not created | CWIP-76804 | Received | PO Released | - |  | 0 | -123 | -
Fibmax | 2026-05-31 | 38 | MU | Sion |  | 1000 | MU-1000 | 89.6 | 89.6 | 19.0522 | 72.8725 | 19.0528 | 72.8726 | MCGM | L | Vasant Vaibhav | Vasant Vaibhav,Gulmohar Road,Chunabhatti(E) 400022 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Swapnil Salvi | Prem Verma | Feasible | 10004699 | 2025-03-24 | 2026-03-24 | 90 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-76805 | RFAI Awaited | PO Released | - |  | 0 | -90 | - |  | Yes
Fibmax | 2026-05-31 | 39 | MU | Borivali |  | MA3372 | MU-MA3372 | 44.8 | 44.8 | 19.2367 | 72.8687 | 19.2366 | 72.8689 | MCGM | R/C | SAI ENCLAVE CHS | Sant Eknath Marg, Kajupada, Borivali East, Mumbai, Maharashtra 400066 | INDUS | Fibmax | Co-build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004865 | 2025-03-26 | 2026-03-26 | 45 | Ok | 0.2 | PO Released | Part of 99 |  | FF_NW1920_15377 | CWIP-76806 | RFAI Awaited | PO Released | - |  | 0 | -45 | - |  | Yes
Fibmax | 2026-04-30 | 40 | MU | Sion |  | MB1155 | MU-MB1155 | 78.4 | 78.4 | 19.0398 | 72.8664 | 19.0398 | 72.8671 | MCGM | F/N | Pramjal | PRANJAL CHS,SARDAR NAGAR NO 01,SION KOLIWADA, MUMBAI, MAHARASHTRA-400022 | INDUS | Fibmax | Co-build | Feasible | April'25 | Swapnil Salvi | Prem Verma | Feasible | 10004843 | 2025-03-26 | 2026-03-26 | 78 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW2122_785458 | CWIP-76807 | RFAI Awaited | PO Released | - |  | 0 | -78 | Pending |  | Yes
|  | 41 | MU | Wadala East |  | 6138 | MU-6138 | 87.808 | 87.808 | 19.0226 | 72.8658 | 19.0225 | 72.8659 | MCGM | F/N | Shopee link_Indus | SHOPEE LINK, ANTOP HILL RD, DOSTI ACRES, -WORLI NAKA ,DISTRICT-MUMBAI, STATE- MAHARASHTRA, PINCODE- 400037 | INDUS | Fibmax | Co-build | Feasible | April'25 | Sandeep randive | Prem Verma | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2025-12-31 | 42 | MU | Andheri |  | 6021 | MU-6021 | 112 | 112 | 19.0966 | 72.8653 | 19.0967 | 72.8651 | MCGM | K/E | RANGOLI | 120-122, Sahar Road, Andheri (East) | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | 10004827 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76808 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-04-30 | 43 | MU | Borivali |  | 5831 | MU-5831 | 67.2 | 67.2 | 19.2404 | 72.8582 | 19.2407 | 72.8586 | MCGM | R/N | Amrut apt. | Sai Amrut, Jaywant Sawant Road, Ambawadi, Dahisar West, Mumbai | ATC | Fibmax | Co-build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004791 | 2025-03-26 | 2026-03-26 | 67 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW2122_785459 | CWIP-76809 | Received | PO Released | 461089 | Santosh Yadav | 126 | 59 | Pending |  | Yes
Fibmax | 2026-04-30 | 44 | MU | Sion |  | 3330 | MU-3330 | 44.8 | 44.8 | 19.0357 | 72.8571 | 19.0355 | 72.8574 | MCGM | F/N | Sion Shivaji Nagar | Plot No6 (pt), 9 (pt), of Sion Division, Bhaudaji Road Extn, Sion (W), Mumbai- 400 022 | ATC | Fibmax | Co-build | Feasible | April'25 | Swapnil Salvi | Prem Verma | Feasible | 10004874 | 2025-03-26 | 2026-03-26 | 45 | Ok | 0.2 | PO Released | Part of 99 |  | FF_NW1920_14699 | CWIP-76810 | Received | PO Released | - |  | 0 | -45 | - |  | Yes
| 2026-04-30 | 45 | MU | Sewri |  | MA751 | MU-MA751 | 78.4 | 78.4 | 18.9952 | 72.8558 | 18.9952 | 72.8558 | MCGM | F/S | L&T's MMRDA MTHL Project (Package-1), Sewri | SEWRI MMRDA, MPT, SEWRI, MUMBAI, MAHARASHTRA 400015 | Airtel Own | Fibmax | Co-build | Feasible | April'25 | Swapnil Salvi | Prem Verma | Feasible | - |  |  | 0 | PO length is greater than Feasibility Length | -78.4 | PO Cancelled | Part of 99 |  | FF_NW2122_785460 | CWIP-76811 | - | PO Released | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-04-30 | 46 | MU | Miraroad |  | 3166 | MU-3166 | 67.2 | 67.2 | 19.3096 | 72.854 | 19.3096 | 72.8534 | MBMC | - | Sarkar Bhavan | Sarkar Bhavan,Chandan nagar, Bhayandar East Mira Bhayandar, Maharashtra 401105 | INDUS | Fibmax | Co-build | Feasible | April'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004781 | 2025-03-26 | 2026-03-26 | 67 | PO Pending |  | PO Released | Part of 99 |  | Not created | CWIP-76812 | RFAI Awaited | PO Released | In-Process |  | 67 | 0 | - |  | Yes
Fibmax | 2025-12-31 | 47 | MU | Jogeshwari |  | 4883 | MU-4883 | 50.4 | 50.4 | 19.1444 | 72.8456 | 19.1447 | 72.8456 | MCGM | K/W | HAPYHOMEOF | Vaishali Nagar, Off S V Road, Jogeshwari West, Mumbai-400102 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Dudhnath Tiwari | Satish Singh | Feasible | 10004778 | 2025-03-26 | 2026-03-26 | 50 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76813 | RFAI Awaited | PO Released | - |  | 0 | -50 | - |  | Yes
Fibmax | 2026-04-30 | 48 | MU | Mahim |  | 2317 | MU-2317 | 156.8 | 156.8 | 19.0354 | 72.8446 | 19.0352 | 72.8443 | MCGM | G/N | Victory mansion | Mr. Rajman (9769293371),VICTORY MANSION,Sitla devi Temple Road, New Dinkar Co Operative Housing Society, Mahim, Mumbai, Maharashtra 400016, India MUMBAI | INDUS | Fibmax | Co-build | Feasible | May'25 | Prem Verma | Prem Verma | Feasible | 10004847 | 2025-03-26 | 2026-03-26 | 157 | Ok | 0.2 | PO Released | Part of 99 |  | FF_NW1920_15108 | CWIP-76814 | RFAI Awaited | PO Released | - | Shrikant Chavan | 125 | -32 | - |  | Yes
Fibmax | 2026-04-30 | 49 | MU | Dadar |  | 1308 | MU-1308 | 78.4 | 78.4 | 19.0179 | 72.844 | 19.0178 | 72.8443 | MCGM | F/N | HOTELSHUO | Hotel Shubham,Café Premier, L. N. Road, Opposite Swami Narayan Mandir, Dadar (East), Mumbai - 400014 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Swapnil Salvi | Prem Verma | Feasible | 10004808 | 2025-03-26 | 2026-03-26 | 78 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW1920_14134 | CWIP-76815 | RFAI Awaited | PO Released | - |  | 0 | -78 | - |  | Yes
Fibmax | 2026-04-30 | 50 | MU | Vile Parle |  | 3151 | MU-3151 | 78.4 | 78.4 | 19.1062 | 72.8435 | 19.1062 | 72.8442 | MCGM | K/W | MEGHDENU | Irla Road, Near East West Flyover, Vile Parle West, Mumbai-400058 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | 10004729 | 2025-03-24 | 2026-03-24 | 78 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW1920_15724 | CWIP-76816 | RFAI Awaited | PO Released | - | Santosh Yadav | 370 | 292 | Pending |  | Yes
Fibmax | 2026-04-30 | 51 | MU | Andheri |  | 2322 | MU-2322 | 100.8 | 100.8 | 19.1263 | 72.8433 | 19.1258 | 72.8433 | MCGM | K/W | Bhagya Apt, | 23, Bhardawadi Ln,Dhakoji Sethpada, Navneeth Colony, Amboli,Mumbai, Maharashtra 400058 | ATC | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | 10004710 | 2025-03-24 | 2026-03-24 | 101 | Ok | 0.2 | PO Released | Part of 99 |  | FF_NW1920_15029 | CWIP-76817 | RFAI Awaited | PO Released | 499006 | Santosh Yadav | 87 | -14 | - |  | Yes | Site under Relocation
Fibmax | 2026-04-30 | 52 | MU | Goregaon |  | MA4247 | MU-MA4247 | 179.2 | 179.2 | 19.1626 | 72.8402 | 19.1624 | 72.8399 | MCGM | P/S | MAMTA CHSL | Sv Road, Tilak Nagar, Goregaon West, Mumbai | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Virendra | Satish Singh | Feasible | 10004719 | 2025-03-24 | 2026-03-24 | 179 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW1920_15498 | CWIP-76818 | RFAI Awaited | PO Released | 654317 | Santosh Yadav | 278 | 99 | Pending |  | Yes
|  | 53 | MU | Masjid Bundar |  | MB1723 | MU-MB1723 | 313.6 | 313.6 | 18.9604 | 72.8344 | 18.961 | 72.8345 | MCGM | B | Imamiya masjid | Plot No:13,Mirzali St,Balu Changu Patil Marg, Umerkhadi, Mumbai, Maharashtra 400009. Post Office:-Umerkhadi,Police Station:-Dongari | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Narayan Parab | Prem Verma | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-10-31 | 54 | MU | Vile Parle |  | MA4127 | MU-MA4127 | 145.6 | 145.6 | 19.1076 | 72.8321 | 19.1072 | 72.8323 | MCGM | K/W | Nirmal Prabhu | NIRMAL PRABHU CHS,GURU NANAK ROAD,LAKSHMIKANT MARG,NS RD,VILE PARLE (W)-4000049. | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004868 | 2025-03-26 | 2026-03-26 | 146 | Ok | 0.4 | PO Released | Part of 99 |  | FF_NW2122_785461 | CWIP-76819 | RFAI Awaited | PO Released | 841789 | Santosh Yadav | 63 | -83 | - |  | Yes | Site under Relocation
|  | 55 | MU | Bandra |  | 333 | MU-333 | 50.4 | 50.4 | 19.062 | 72.8318 | 19.0623 | 72.832 | MCGM | H/W | Fortune Heritage | DR KB HEDGEKAR ROAD, PALLI VILLAGE BANDRA (W). | ATC | Fibmax | Co-build | Feasible | Nov'25 | Prem Verma | Prem Verma | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-05-31 | 56 | MU | Santacruz |  | MA183 | MU-MA183 | 106.4 | 106.4 | 19.079 | 72.83 | 19.079 | 72.8292 | MCGM | H/W | Guru Ashish | North Avenue Road, Dhan Pothohar Nagar, Santacruz West, Mumbai | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004693 | 2025-03-24 | 2026-03-24 | 106 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76820 | RFAI Awaited | PO Released | - |  | 0 | -106 | - |  | Yes
Fibmax | 2026-05-31 | 57 | MU | Vile Parle |  | MA129 | MU-MA129 | 28 | 28 | 19.114 | 72.8296 | 19.1139 | 72.8298 | MCGM | K/W | Raval CHS | Eden Square, NS Road No.10, Samarth Ramdas Marg, JVPD Scheme, Vile Parle West | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004803 | 2025-03-26 | 2026-03-26 | 28 | Ok | 0 | PO Released | - |  | Not created | CWIP-76821 | RFAI Awaited | PO Released | - |  | 0 | -28 | - |  | Yes
Fibmax | 2026-05-31 | 58 | MU | Kandivali |  | 3589 | MU-3589 | 280 | 280 | 19.2096 | 72.8295 | 19.2096 | 72.8301 | MCGM | R/S | Technosys Limited | ZOHA ICE CREAM, NEAR SHAYDRI NAGAR, FRONT OFF BHARTIYA STATE BANK, CHARKOP, KANDIVALI WEST | ATC | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004782 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76822 | Received | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2025-12-31 | 59 | MU | Khar |  | MA5238 | MU-MA5238 | 89.6 | 89.6 | 19.0744 | 72.8256 | 19.0741 | 72.8261 | MCGM | H/W | Hermitage Villa | Hermitage Villa,Chuim Village, Danda Pada, Khar Danda, Khar West, Mumbai | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | 10004716 | 2025-03-24 | 2026-03-24 | 90 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-76823 | RFAI Awaited | PO Released | - |  | 0 | -90 | - |  | Yes
Fibmax | 2026-05-31 | 60 | MU | Kandivali |  | MB3183 | MU-MB3183 | 4.48 | 4.48 | 19.2134 | 72.8239 | 19.2136 | 72.824 | MCGM | R/S | Ramjaruka | Ram Jharokha Cooperative Housing Society Limited, Cluster_mumbai Suburban_271, RSC Rd Number 11, Kandivali, Charkop, Sector 2 Charkop, Kandivali West, Mumbai, Maharashtra 400067,Post office:-Charkop,police station:-Charkop | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004788 | 2025-03-26 | 2026-03-26 | 40 | PO length is greater than Feasibility Length | 35.52 | PO Released | - |  | Not created | CWIP-76824 | RFAI Awaited | PO Released | - |  | 0 | -40 | - |  | Yes
Fibmax | 2025-12-31 | 61 | MU | Worli |  | 1027 | MU-1027 | 145.6 | 145.6 | 18.995 | 72.8229 | 18.9959 | 72.8228 | MCGM | G/S | SAHYADRIOF | Kasturba Gandhi Nagar, Dainik Shivner Marg, Worli | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Prem Verma | Prem Verma | Feasible | 10004864 | 2025-03-26 | 2026-03-26 | 146 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-76825 | RFAI Awaited | PO Released | - |  | 0 | -146 | - |  | Yes
Fibmax | 2026-10-31 | 62 | MU | Malabar Hill |  | 1264 | MU-1264 | 12.544 | 12.544 | 18.9649 | 72.8037 | 18.9651 | 72.8038 | MCGM | D | MEHERABAOF | 1/ 594, Warden Road Junction,_Mumbai- 26 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Vaijesh Patil | Prem Verma | Feasible | 10004784 | 2025-03-26 | 2026-03-26 | 30 | PO length is greater than Feasibility Length | 17.456 | PO Released | Part of 99 |  | FF_NW1920_14131 | CWIP-76826 | RFAI Awaited | PO Released | 199842 | Shrikant Chavan | 10 | -20 | - |  | Yes
Fibmax | 2026-10-31 | 63 | MU | Malabar Hill |  | 5436 | MU-5436 | 106.4 | 106.4 | 18.9543 | 72.7986 | 18.9547 | 72.7985 | MCGM | D | Rajat Apartment | Rajat Apts.,Mount Pleasant Road, Malabar Hill, Mumbai 400 006 | ATC | Fibmax | Co-build | Feasible | Nov'25 | Vaijesh Patil | Prem Verma | Feasible | 10004780 | 2025-03-26 | 2026-03-26 | 106 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW1920_14814 | CWIP-76827 | RFAI Awaited | PO Released | - | Shrikant Chavan | 56 | -50 | - |  | Yes
Fibmax | 2026-10-31 | 64 | MU | Malabar Hill |  | 5525 | MU-5525 | 388.416 | 388.416 | 18.9497 | 72.7963 | 18.9481 | 72.7976 | MCGM | D | Anupam CHSL | Anupam CHS, Manav Mandir Road, Malabar hill, Mumbai-400006 | ATC | Fibmax | Co-build | Feasible | Nov'25 | Vaijesh Patil | Prem Verma | Feasible | 10004776 | 2025-03-26 | 2026-03-26 | 338 | PO length is less than Feasibility length | -50.416 | PO Released | Part of 99 |  | FF_NW2122_785462 | CWIP-76828 | RFAI Awaited | PO Released | - |  | 363 | 25 | LA Considered |  | Yes
Fibmax | 2026-12-31 | 65 | MU | Govandi |  | MB4330 | MU-MB4330 | 228.032 | 228.032 | 19.0612 | 72.9188 | 19.0615 | 72.9182 | MCGM | M/E | Khaliliya Massjid | Mankurd Link Road,Bhimvadi,New Gautam Nagar,Govandi,Mumbai 400043 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004796 | 2025-03-26 | 2026-03-26 | 228 | Ok | -0.032 | PO Released | - |  | Not created | CWIP-76829 | RFAI Awaited | PO Released | - |  | 0 | -228 | - |  | Yes
Fibmax | 2026-11-30 | 66 | MU | Miraroad |  | MB1608 | MU-MB1608 | 56 | 56 | 19.2784 | 72.8632 | 19.2785 | 72.8629 | MBMC | - | Arihant CHS | ARIHANT CHS,3A-4, BHAGWAN MAHAVIR MARG, SECTOR 7, SHANTI NAGAR, MIRA ROAD EAST, MIRA BHAYANDAR, MAHAR,POST OFFICE:-MIRA ROAD,POLICE STATION:-MIRA ROAD | INDUS | Fibmax | Co-build | Feasible | April'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004869 | 2025-03-26 | 2026-03-26 | 56 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785463 | CWIP-76830 | Received | PO Released | 198508 |  | 124 | 68 | Pending |  | Yes
Fibmax | 2026-11-30 | 67 | MU | Khadakpada |  | MB1585 | MU-MB1585 | 112 | 112 | 19.2526 | 73.1271 | 19.2524 | 73.1273 | KDMC | - | Shree Ganesh Vandan CHSL | Ganesh Vandan Building, Shop No: 7, Near Lotus Hospital, Aadharwadi Chowk, Birla College Rd, Kalyan West, Thane, Maharashtra 421301 | ATC | Fibmax | Co-build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004873 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785464 | CWIP-76831 | RFAI Awaited | PO Released | 198210 | Tulsi Yadav | 130 | 18 | LA Considered |  | Yes
Fibmax | 2026-12-31 | 68 | MU | Naupada |  | MB1728 | MU-MB1728 | 112 | 112 | 19.1882 | 72.9759 | 19.1882 | 72.9759 | TMC | - | Fenkin Emperior | Dr. Bhanushali Hospital Kaushalya', Shivaji path, near Thane Rly station, Thane, Maharashtra 400601,Post office :-Thane,police station:-Thane | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004805 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76832 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-12-31 | 69 | MU | Mulund |  | MB2983 | MU-MB2983 | 112 | 112 | 19.1736 | 72.9574 | 19.1732 | 72.9571 | MCGM | T | Shanti | New Arihant Shopping Centre Office No.23, 2nd floor J.D road Near Station Mulund Mumbai West, Maharashtra 400080,Post office:-Mulund,Police Station:-Mulund | ATC | Fibmax | Co-build | Feasible | Jan'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76833 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2025-12-31 | 70 | MU | Bhandup |  | 4609 | MU-4609 | 224 | 224 | 19.1399 | 72.928 | 19.1402 | 72.9282 | MCGM | S | Fuggawala compound | Fugewala Compound, Maharashtra Nagr Bus stop, Bhandup w | Suyog | Fibmax | Co-build | Feasible | Nov'25 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004810 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76834 | Received | PO Released | - |  | 0 | -224 | - |  |  | Site under Relocation
Fibmax | 2026-12-31 | 71 | MU | Santacruz |  | 174 | MU-174 | 190.4 | 190.4 | 19.0757 | 72.8321 | 19.0759 | 72.8326 | MCGM | H/W | Little Star CHSL | 15th Road, Ramkrishna Mission Road, Santacruz (w) Mumbai â€“ 400054 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Hari Yadav | Satish Singh | Feasible | 10004711 | 2025-03-24 | 2026-03-24 | 190 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76835 | RFAI Awaited | PO Released | - |  | 0 | -190 | - |  | Yes
Fibmax | 2026-12-31 | 72 | MU | Kandivali |  | MB2484 | MU-MB2484 | 22.4 | 22.4 | 19.2072 | 72.8775 | 19.2076 | 72.8773 | MCGM | R/S | Windsor Chsl | Windsor Chsl,Phase No:-2,The Windsor,Opp. Esis Hospital,Damu Nagar,Thakur Village,Kandivali East, Mumbai,Maharashtra:400101 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004794 | 2025-03-26 | 2026-03-26 | 30 | Ok | 7.6 | PO Released | - |  | Not created | CWIP-76836 | Received | PO Released | - |  | 0 | -30 | - |  | Yes
Fibmax | 2026-11-30 | 73 | MU | Mahape |  | MB640 | MU-MB640 | 112 | 112 | 19.11 | 73.0172 | 19.1102 | 73.0173 | NMMC | - | SPIRE BPO SERVICE LLP_BLDG NO.1_MBP | 3rd ,2nd & Ground floor, A Wing, Bldg No. 1(61), Sector 2, Millennium Business Park, Mahape, Navi Mumbai | Airtel Own | Fibmax | Co-build | Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004829 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785465 | CWIP-76837 | RFAI Awaited | PO Released | - |  | 0 | -112 | Pending |  | Yes
Fibmax | 2026-12-31 | 74 | MU | Thane |  | 6087 | MU-MM6087 | 112 | 112 | 19.2033 | 72.9582 | 19.2032 | 72.9582 | TMC | - | 0 | Devkar Niwas,Road No 33, Dnyaneshwar nagar, Thane [W]. | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76838 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-12-31 | 75 | MU | Kurla |  | MA3670 | MU-MA3670 | 67.2 | 67.2 | 19.0642 | 72.8749 | 19.0642 | 72.8748 | MCGM | L | Devi-Darshan Apartment_Netsol/Dilip Gone (Rel of Devi Darshan) Indus-NB Team | SAINATH CHOWK,LBS ROAD,NEAR KURLA TELUGU BAPTISH CHURCH, Opp. KURLA COURT KURLA(W),MUMBAI, MAHARASHTRA 400070 | Netsol | Fibmax | Co-build | Feasible | Jan'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004876 | 2025-03-26 | 2026-03-26 | 67 | Ok | -0.2 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76839 | RFAI Awaited | PO Released | - |  | 0 | -67 | -
Fibmax | 2026-12-31 | 76 | MU | Dahisar |  | 247 | MU-MM247 | 112 | 112 | 19.2499 | 72.8706 | 19.2494 | 72.8702 | MCGM | R/N | 0 | Ghartan Pada, Dahisar East, Mumbai, Maharashtra 400068 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76840 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-11-30 | 77 | MU | Miraroad |  | MB2489 | MU-MB2489 | 33.6 | 33.6 | 19.277 | 72.8701 | 19.2767 | 72.8706 | MBMC | - | Krishna Tower CHSL | Building No:-1 & 2,Krishna Tower, RNA Complex,Om Shanti Chowk, Mira Road, Mira Bhayandar, Maharashtra 401107 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004789 | 2025-03-26 | 2026-03-26 | 34 | Ok | 0.4 | PO Released | Part of 99 |  | FF_NW2122_785466 | CWIP-76841 | Received | PO Released | 199854 | Santosh Yadav | 32 | -2 | - |  | Yes
Fibmax | 2026-05-31 | 78 | MU | Vile Parle |  | 334 | MU-334 | 112 | 112 | 19.1035 | 72.8512 | 19.1036 | 72.8513 | MCGM | K/E | Anish Appt | Hanuman nagar Opp.ICICI bank, Parle €, Mumbai | ATC | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004804 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76842 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-10-31 | 79 | MU | Vile Parle |  | MA2 | MU-MA2 | 78.4 | 78.4 | 19.0967 | 72.8501 | 19.0971 | 72.8505 | MCGM | K/E | HOTEL JOY PALACE | Hotel Joy Palace,N Patkar Marg, Vile Parle, Vile Parle East | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Sushil Patil | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 78 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW2122_785467 | CWIP-76843 | RFAI Awaited | PO Released | 583552 | Santosh Yadav | 65 | -13 | - |  | No
|  | 80 | MU | Andheri |  | 4295 | MU-4295 | 112 | 112 | 19.115 | 72.8501 | 19.1152 | 72.8505 | MCGM | K/E | HUB TOWN SOLARIS | HUB TOWN SOLARIS, Ghokhle pool, ProfNS Phadke Marg, Teli Galli, Andheri(E), Mumbai | IBUS | Fibmax | Co-build | Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-05-31 | 81 | MU | Vile Parle |  | 1387 | MU-1387 | 78.4 | 78.4 | 19.1087 | 72.8485 | 19.1089 | 72.8488 | MCGM | K/E | Jeevan Dhara | Jeevan Dhara Co Hsg Soc Ltd, Shahaji Raje Marg, Near Prabodhan Thackeray Krida Sankul, Shivaji Nagar, Vile Parle East, Mumbai, Maharashtra- 400057 MUMBAI | ATC | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004863 | 2025-03-26 | 2026-03-26 | 78 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76844 | RFAI Awaited | PO Released | - |  | 0 | -78 | - |  | Yes
|  | 82 | MU | Vile Parle |  | 5387 | MU-5387 | 33.6 | 33.6 | 19.1025 | 72.8358 | 19.1027 | 72.8357 | MCGM | K/W | GNGNIWASONM1 | Ganga Niwas, VM Road, Opposite SVKM"s College of Management, Vile Parle(W), Mumbai-400066 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-11-30 | 83 | MU | Bandra |  | 148 | MU-148 | 67.2 | 67.2 | 19.0637 | 72.8296 | 19.0643 | 72.8297 | MCGM | H/W | Panjitani Villa | Dr.Ambedkar Road Pali Hill Bandra /west,Maharashtra | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Prem Verma | Prem Verma | Feasible | 10004692 | 2025-03-24 | 2026-03-24 | 67 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW1920_15817 | CWIP-76845 | RFAI Awaited | PO Released | 198254 | Santosh Yadav | 130 | 63 | Pending |  | Yes
Fibmax | 2026-12-31 | 84 | MU | Gorai |  | MA4659 | MU-MA4659 | 67.2 | 67.2 | 19.2249 | 72.828 | 19.2244 | 72.8277 | MCGM | R/C | Rakesh reddy house | 38-A/23, RDP RD NUMBER 5, BHIM NAGAR, BORIVALI WEST, MUMBAI, MAHARASHTRA 400091 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004822 | 2025-03-26 | 2026-03-26 | 67 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-76846 | Received | PO Released | - |  | 0 | -67 | - |  | Yes
Fibmax | 2026-10-31 | 85 | MU | Nariman Point |  | 1008 | MU-1008 | 67.2 | 67.2 | 18.9236 | 72.8236 | 18.9232 | 72.8238 | MCGM | A | RAHEJACTOF | Plot No 214, Free Press Journal Marg | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Prem Verma | Prem Verma | Feasible | 10004709 | 2025-03-24 | 2026-03-24 | 67 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW2122_785468 | CWIP-76847 | RFAI Awaited | PO Released | 198255 | Shrikant Chavan | 90 | 23 | LA Considered |  | Yes
Fibmax | 2026-10-31 | 86 | MU | Charni Road |  | 356 | MU-356 | 123.2 | 123.2 | 18.9559 | 72.8086 | 18.9555 | 72.808 | MCGM | D | Mahayoonas Cashabh, ISLAM CLUB | ISLAM CLUB, BEGMOHAMMAD MANSION ABOVE ISLAM CLUB SEAFACE CHOWPATTY | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Prem Verma | Prem Verma | Feasible | 10004728 | 2025-03-24 | 2026-03-24 | 123 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW1920_15796 | CWIP-76848 | RFAI Awaited | PO Released | - |  | 85 | -38 | - |  | Yes
Fibmax | 2026-12-31 | 87 | MU | Vitthalwadi |  | 6323 | MU-6323 | 224 | 224 | 19.2256 | 73.1518 | 19.2254 | 73.1525 | KDMC | - | SALMAN | Mr. Kaab Ansari (9987143713),Shree Ganesh Colony, Pune Link Rd, Khadegolwali, Vitthalwadi, Kalyan, Maharashtra 421004 KALYAN | ATC | Fibmax | Co-build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004785 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76849 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-11-30 | 88 | MU | Miraroad |  | 4409 | MU-4409 | 110 | 110 | 19.2923 | 72.9061 | 19.2922 | 72.9055 | MBMC | - | HAVELIINO | Hotel Haveli Inn GBT,Ahmedabad Natiomal Highway,Near Versova Bridge Ghodbunder Road,Thane | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004841 | 2025-03-26 | 2026-03-26 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76850 | RFAI Awaited | PO Released | - |  | 0 | -110 | - |  | Yes
Fibmax | 2026-05-31 | 89 | MU | Airoli |  | 273 | MU-273 | 448 | 448 | 19.1582 | 72.9965 | 19.1601 | 72.9956 | NMMC | - | Namaskar CHS | Namaskar Chsl,Plot No191,Sec-3,Super Market,Airoli,Navi Mumbai | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 448 | Ok | 0 | PO Released | - |  | Not created | CWIP-76851 | RFAI Awaited | PO Released | - |  | 0 | -448 | - |  | Yes | Site under Relocation
|  | 90 | MU | Thane |  | 3292 | MU-3292 | 560 | 560 | 19.2057 | 73.0022 | 19.2069 | 73.0033 | TMC | - | RATI PUSHPAGANDHA | NEAR BHAVIKA VIDYALAYA, PAKADI,KHAREGOAN,KALWA(W) THANE 400605 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Ranjit Wadkar | Yogesh Deshpande | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-11-30 | 91 | MU | Bandra |  | 1371 | MU-1371 | 66 | 66 | 19.0688 | 72.8238 | 19.069 | 72.8241 | MCGM | H/W | Moon Craft | Mooncraft,Carter Road , Next to 175 Carter Road, Bandra West, Mumbai | ATC | Fibmax | Co-build | Feasible | Nov'25 | Vaijesh Patil | Prem Verma | Feasible | 10004832 | 2025-03-26 | 2026-03-26 | 66 | Site dismantal | 0 | PO Released | Part of 99 |  | FF_NW1920_14923 | CWIP-76852 | RFAI Awaited | PO Released | - | Santosh Yadav | 30 | -36 | - |  | Yes
Fibmax | 2026-10-31 | 92 | MU | Borivali |  | 4534 | MU-4534 | 220 | 220 | 19.2278 | 72.8584 | 19.2277 | 72.858 | MCGM | R/C | MANGESHSO | Carter Road, Borivili (E) | INDUS | Fibmax | Co-build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004807 | 2025-03-26 | 2026-03-26 | 220 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_14388 | CWIP-76853 | RFAI Awaited | PO Released | - |  | 0 | -220 | - |  | Yes
Fibmax | 2026-05-31 | 93 | MU | Vikroli |  | MB1311 | MU-MB1311 | 373 | 373 | 19.1191 | 72.9395 | 19.1175 | 72.9393 | MCGM | S | Rajashree Shahu Maharaj_Indus | Rajshree shahu Maharaj, Near Vikas Vidyalaya, Road No. 1, Kannamwar Nagar II, Vikhroli East, Mumbai, Maharashtra- 400083 MUMBAI | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004877 | 2025-03-26 | 2026-03-26 | 373 | Ok | 0 | PO Released | - |  | Not created | CWIP-76854 | RFAI Awaited | PO Released | - |  | 0 | -373 | - |  | Yes
Fibmax | 2026-11-30 | 94 | MU | Panvel |  | 4998 | MU-4998 | 330 | 330 | 18.974 | 73.1211 | 18.9751 | 73.1208 | PMC | - | ASHOKPARO | Ashok Pardeshi,Ashok Pardeshi, Bhingari ONGC Tal Panvel 410206 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Manoj Ligade | Praveen Nigam | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 300 | PO length is less than Feasibility length | -30 | PO Released | - |  | Not created | CWIP-76855 | RFAI Awaited | PO Released | - |  | 0 | -300 | - |  | No
Fibmax | 2026-11-30 | 95 | MU | Panvel |  | MA3675 | MU-MA3675 | 187 | 187 | 18.9682 | 73.134 | 18.9682 | 73.1349 | PMC | - | HARESH THADWANI FARM | ANUPAM NURSUREY,81 / 2,83 / 1,KOLKHE VILLAGE,MUMBAI - PUNE ROAD,PALAS PHATA, PANVEL, NAVI MUMBAI 410221 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Manoj Ligade | Praveen Nigam | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 187 | Ok | 0 | PO Released | - |  | Not created | CWIP-76856 | RFAI Awaited | PO Released | - |  | 0 | -187 | - |  | No
|  | 96 | MU | Panvel |  | 6177 | MU-6177 | 220 | 220 | 18.9983 | 73.1079 | 18.9993 | 73.1085 | PMC | - | MUNOTAPTOF | Old Panvel, HOC Colony, Panvel, Navi Mumbai, Maharashtra 410206 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Manoj Ligade | Praveen Nigam | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-11-30 | 97 | MU | Juinagar |  | MB4281 | MU-MB4281 | 220 | 220 | 19.0458 | 73.0173 | 19.0455 | 73.0178 | NMMC | - | Khare Open Plot | Sukhshanti nursery beside budhh vihar close to Afjal auto works, opposite Chincholi talaw, Sector 25, Juinagar West, Navi Mumbai, Maharashtra 400705 | INDUS | Fibmax | Co-build | Feasible | April'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004852 | 2025-03-26 | 2026-03-26 | 220 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785469 | CWIP-76857 | RFAI Awaited | PO Released | - |  | 0 | -220 | Pending |  | Yes
Fibmax | 2026-05-31 | 98 | MU | Thane |  | 4546 | MU-4546 | 200 | 200 | 19.2102 | 72.9808 | 19.2112 | 72.9806 | TMC | - | RUTUQQQ | National Highway ,Thane West,Majiwada, Thane (W)-400601 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 200 | Ok | 0 | PO Released | - |  | Not created | CWIP-76858 | RFAI Awaited | PO Released | - |  | 0 | -200 | - |  | No
Fibmax | 2026-05-31 | 99 | MU | Thane |  | 1670 | MU-1670 | 104.5 | 104.5 | 19.2588 | 72.971 | 19.2585 | 72.97 | TMC | - | KANCHANPO | Kavesar, Thane WestThane, Maharashtra Thane Gobunder Road | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 104 | Ok | -0.5 | PO Released | - |  | Not created | CWIP-76859 | RFAI Awaited | PO Released | - |  | 0 | -104 | - |  | No
Fibmax | 2026-11-30 | 100 | MU | Saki Naka |  | MA5034 | MU-MA5034 | 110 | 110 | 19.0933 | 72.8835 | 19.0936 | 72.8831 | MCGM | L | kurla exhibitors mall | 90 FIT ROAD,JARIMARI,NEAR HINDUSTAN WAY BRIDGE,ANDHERI KURLA ROAD MUMBAI, MAHARASHTRA.400093 | ATC | Fibmax | Co-build | Feasible | Nov'25 | Manoj Ligade | Prem Verma | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76860 | RFAI Awaited | PO Released | - |  | 0 | -110 | - |  | No
Fibmax | 2026-12-31 | 101 | MU | Kurla |  | MA2088 | MU-MA2088 | 57.2 | 57.2 | 19.0867 | 72.8813 | 19.0865 | 72.881 | MCGM | L | Khan House | Khan House, Near Municipal School, Bail Bazaar, Kurla West, Mumbai 400070 | Suyog | Fibmax | Co-build | Feasible | Jan'26 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 58 | Ok | 0.8 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76861 | Received | PO Released | - |  | 0 | -58 | -
Fibmax | 2026-11-30 | 102 | MU | Andheri |  | 4088 | MU-4088 | 253 | 253 | 19.1312 | 72.8766 | 19.1298 | 72.8764 | MCGM | K/E | BLDGNOQ | Bldg No-1,Sharitup, Rup Nagar,Jogeshwari - Vi33oli Link Road, Jogeshwari,Mumbai | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Dudhnath Tiwari | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 253 | Ok | 0 | PO Released | - |  | Not created | CWIP-76862 | RFAI Awaited | PO Released | - |  | 0 | -253 | - |  | No
Fibmax | 2026-12-31 | 103 | MU | Jogeshwari |  | 2643 | MU-2643 | 16.5 | 16.5 | 19.1377 | 72.8644 | 19.1377 | 72.8641 | MCGM | K/E | Arena Space | Arena Spacce, Station Rd, Shyam Nagar, Jogeshwari East, Mumbai, Maharashtra | Airtel Own | Fibmax | Co-build | Feasible | Jan'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 16 | Ok | -0.5 | PO Released | - |  | Not created | CWIP-76863 | RFAI Awaited | PO Released | - |  | 0 | -16 | - |  | No
Fibmax | 2026-05-31 | 104 | MU | Santacruz |  | 194 | MU-194 | 99 | 99 | 19.0777 | 72.8592 | 19.0786 | 72.8596 | MCGM | H/E | Nikita Building | Vakola Village Road, Kalina, Santacruz East, Mumbai-400044 | ATC | Fibmax | Co-build | Feasible | Feb'26 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 99 | Ok | 0 | PO Released | - |  | Not created | CWIP-76864 | RFAI Awaited | PO Released | - |  | 0 | -99 | - |  | No
Fibmax | 2026-10-31 | 105 | MU | Andheri |  | MA5982 | MU-MA5982 | 11 | 11 | 19.1401 | 72.8291 | 19.1399 | 72.8293 | MCGM | K/W | RAHEJA CREAST | Shashtri Nagar Road, Near Bhakti Vedanta School, Andheri W , Mumbai - 400058. | ATC | Fibmax | Co-build | Feasible | May'25 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 11 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15280 | CWIP-76865 | RFAI Awaited | PO Released | 198141 | Santosh Yadav | 158 | 147 | LA Considered |  | No
|  | 106 | MU | Juhu |  | 6213 | MU-6213 | 297 | 297 | 19.0902 | 72.8285 | 19.0883 | 72.827 | MCGM | K/W | JALTARNGOF | Jal Tarang,kishor Kumar Road,Juhu Tara ,Juhu. | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Hari Yadav | Satish Singh | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 107 | MU | Thane |  | MA1056 | MU-MA1056 | 297 | 297 | 19.2349 | 72.977 | 19.2343 | 72.9763 | TMC | - | Odedra Apartment | Odedra,Nr. Petrol pump Manpada, Ghodbunder road, Thane | ATC | Fibmax | Co-build | Feasible | Jan'26 | Manoj Ligade | Yogesh Deshpande | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-10-31 | 108 | MU | Andheri |  | MB2466 | MU-MB2466 | 110 | 110 | 19.1308 | 72.8231 | 19.1312 | 72.8221 | MCGM | K/W | Anurag Chsl | Anurag Chs, A-Wing, Jp Rd, Mudran Press Colony, Andheri West, Mumbai, Maharashtra ,Police Station:-Andheri,Post Office-Andheri, Mumbai | INDUS | Fibmax | Co-build | Feasible | May'25 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 110 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785470 | CWIP-76866 | Received | PO Released | In-Process | Santosh Yadav | 218 | 108 | Pending |  | No
Fibmax | 2027-01-31 | 109 | MU | Santacruz |  | 636 | MU-636 | 253 | 253 | 19.079 | 72.8656 | 19.0784 | 72.8666 | MCGM | H/E | Ajanta Madhulata | Ajanta Madhulata, Arvind Nagar, Kalina, Santacruz East, Mumbai, Maharashtra 400029 MUMBAI | ATC | Fibmax | Co-build | Feasible | Jan'26 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 253 | Ok | 0 | PO Released | - |  | Not created | CWIP-76867 | Received | PO Released | - |  | 0 | -253 | - |  | No
Fibmax | 2026-04-30 | 110 | MU | Santacruz |  | MA981 | MU-MA981 | 110 | 110 | 19.0798 | 72.8591 | 19.0803 | 72.8591 | MCGM | H/E | LOTUS CHS. | MILETRY ROAD, BEHIND DOLPHINE HERITAGE, KALINA CAMP SANTAKRUZ E. | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76868 | RFAI Awaited | PO Released | - |  | 0 | -110 | - |  | No
Fibmax | 2026-10-31 | 111 | MU | Jogeshwari |  | 5158 | MU-5158 | 253 | 253 | 19.1455 | 72.836 | 19.1463 | 72.836 | MCGM | K/W | LINPALACOF | Link Palace ,Link Rd, Kadam Nagar, Jogeshwari West 400102 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 253 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785471 | CWIP-76869 | RFAI Awaited | PO Released | 342225 | Santosh Yadav | 140 | -113 | - |  | No
Fibmax | 2026-04-30 | 112 | MU | Digha |  | MA1840 | MU-MA1840 | 253 | 253 | 19.1775 | 73.0036 | 19.177 | 73.0029 | NMMC | - | Jai Bajarang Automobile | Digha Naka, Dighe, Navi Mumbai, Maharashtra 400708 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 253 | Ok | 0 | PO Released | - |  | Not created | CWIP-76870 | RFAI Awaited | PO Released | 659033 |  | 0 | -253 | - |  | No
Fibmax | 2026-04-30 | 113 | MU | Airoli |  | 4093 | MU-4093 | 165 | 165 | 19.1535 | 72.9941 | 19.1535 | 72.9949 | NMMC | - | TERAPANQOF | Samarth Ramdas Swami Road, Airoli, Navi Mumbai-400708 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 165 | Ok | 0 | PO Released | - |  | Not created | CWIP-76871 | RFAI Awaited | PO Released | - |  | 0 | -165 | - |  | No
Fibmax | 2027-01-31 | 114 | MU | Thane |  | 1474 | MU-1474 | 33 | 33 | 19.2086 | 72.9851 | 19.2085 | 72.9851 | TMC | - | BRINDAVAAN Socity Buliding No. 71 Thane (W). | Bldg. No.71 B,Brindavan Society Complex, Thane West. | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004770 | 2025-03-25 | 2026-03-25 | 33 | Ok | 0 | PO Released | - |  | Not created | CWIP-76872 | RFAI Awaited | PO Released | - |  | 0 | -33 | - |  | No
Fibmax | 2026-05-31 | 115 | MU | Thane |  | 4936 | MU-4936 | 24.2 | 24.2 | 19.2552 | 72.972 | 19.2552 | 72.972 | TMC | - | Siddheshwar Arcade | Sidheshwar Arcade,Suraj Water Park,Thane W | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 25 | Ok | 0.8 | PO Released | - |  | Not created | CWIP-76873 | RFAI Awaited | PO Released | - |  | 0 | -25 | - |  | No
|  | 116 | MU | Thane |  | MA1436 | MU-MA1436 | 11 | 11 | 19.2716 | 72.9655 | 19.2712 | 72.9644 | TMC | - | VASTU-B | Kasarvadavali, Thane West, Thane, Maharashtra 400615 | High G | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-05-31 | 117 | MU | Thane |  | 5395 | MU-5395 | 38.5 | 38.5 | 19.2742 | 72.9612 | 19.2742 | 72.9612 | TMC | - | Global Gallaria Ovla | Global Gallerie, Gloroa Hall,Godhbunder road, Ovala Goan, thane west | Airtel Own | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 38 | Ok | -0.5 | PO Released | - |  | Not created | CWIP-76874 | RFAI Awaited | PO Released | - |  | 0 | -38 | - |  | No
Fibmax | 2026-05-31 | 118 | MU | Thane |  | MA3827 | MU-MA3827 | 22 | 22 | 19.2838 | 72.9484 | 19.2838 | 72.9484 | TMC | - | Dayanand House | DUBEY OPEN PLOT, PLOT NO. 41/A, GALA 2-3, GAIMUKH GAON,THANE, 400615 | ATC | Fibmax | Co-build | Feasible | Feb'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 22 | Ok | 0 | PO Released | - |  | Not created | CWIP-76875 | RFAI Awaited | PO Released | - |  | 0 | -22 | - |  | No
Fibmax | 2026-10-31 | 119 | MU | kalwa |  | MB1084 | MU-MB1084 | 220 | 220 | 19.2039 | 73.0026 | 19.2025 | 73.0029 | TMC | - | Sai Chaya CHS | NEAR JARIMARI TEMPLE, KALWA ,THANE 400605 | ATC | Fibmax | Co-build | Feasible | Jan'26 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004853 | 2025-03-26 | 2026-03-26 | 220 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785472 | CWIP-76876 | RFAI Awaited | PO Released | - |  | 0 | -220 | - |  | Yes
Fibmax | 2026-04-30 | 120 | MU | Thane |  | MA1156 | MU-MA1156 | 50 | 50 | 19.2265 | 72.971 | 19.2265 | 72.971 | TMC | - | Hiranandini Medows-Mayflower bldg | MAYFLOWER, HIRANDANI MEDOWS PAWAR NAGER THANE (W), MUMBAI, MAHARASHTRA. | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 50 | Ok | 0 | PO Released | - |  | Not created | CWIP-76877 | RFAI Awaited | PO Released | - |  | 0 | -50 | - |  | No
Fibmax | 2026-04-30 | 121 | MU | Mulund |  | 4485 | MU-4485 | 20 | 20 | 19.1695 | 72.9639 | 19.1695 | 72.9639 | MCGM | T | SRGANESHOF | Shree Ganesh Kripa ,Atlanta Tower, Bhoir Nagar, Vidyalaya Marg, Mulund (East), Mumbai - 400081 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004854 | 2025-03-26 | 2026-03-26 | 20 | PO Pending |  | PO Released | - |  | Not created | CWIP-76878 | Received | PO Released | - |  | 0 | -20 | - |  | Yes
Fibmax | 2027-01-31 | 122 | MU | Dahisar |  | MA2545 | MU-MA2545 | 11 | 11 | 19.2531 | 72.8584 | 19.2531 | 72.8584 | MCGM | R/N | Durga Niwas 19.253 72.8584 | Damodar Mhatre Rd, Mhatre Wadi, Dahisar West, Mumbai, Maharashtra 400068 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004858 | 2025-03-26 | 2026-03-26 | 113 | PO length is greater than Feasibility Length | 102 | PO Released | - |  | Not created | CWIP-76879 | RFAI Awaited | PO Released | - |  | 0 | -113 | - |  | Yes
Fibmax | 2026-10-31 | 123 | MU | Dahisar |  | MB6370 | MU-MB6370 | 33 | 33 | 19.2494 | 72.8536 | 19.2495 | 72.8534 | MCGM | R/N | Raj Heritage CHS | Navagaon, Mandapeshwar, Dahisar West, Mumbai, Maharashtra 400068 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004838 | 2025-03-26 | 2026-03-26 | 33 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785473 | CWIP-76880 | RFAI Awaited | PO Released | 640418 | Santosh Yadav | 81 | 48 | Pending |  | Yes
Fibmax | 2026-11-30 | 124 | MU | Nilje gaon |  | 6281 | MU-6281 | 165 | 165 | 19.1468 | 73.0809 | 19.1461 | 72.8349 | MCGM | K/W | Pole near Volga | Pole near Volga, Lodha Casario, Nilje, Dombivali East,Mumbai-421204 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Virendra | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 165 | Ok | 0 | PO Released | - |  | Not created | CWIP-76881 | RFAI Awaited | PO Released | - |  | 0 | -165 | - |  | No
Fibmax | 2026-04-30 | 125 | MU | Andheri |  | 5886 | MU-5886 | 110 | 110 | 19.1259 | 72.8387 | 19.1251 | 72.8381 | MCGM | K/W | JEEVAN SANGAM | Above SBI Bank, Near Bhavans College, J P Road, Andheri West, Mumbai-400058 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004815 | 2025-03-26 | 2026-03-26 | 140 | PO length is greater than Feasibility Length | 30 | PO Released | - |  | Not created | CWIP-76882 | RFAI Awaited | PO Released | - |  | 0 | -140 | - |  | Yes
Fibmax | 2026-04-30 | 126 | MU | Andheri |  | MA4575 | MU-MA4575 | 286 | 286 | 19.1199 | 72.8532 | 19.1182 | 72.8528 | MCGM | K/E | Suhana CHSL | GUNDAWALI AZAD RD, GUNDAVALI GAOTHAN,ANDHERI EAST, MUMBAI, 400053 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 286 | Ok | 0 | PO Released | - |  | Not created | - | RFAI Awaited | PO Released | - |  | 0 | -286 | - |  | No
Fibmax | 2026-10-31 | 127 | MU | Borivali |  | MA928 | MU-MA928 | 368.5 | 368.5 | 19.2277 | 72.8424 | 19.2277 | 72.8424 | MCGM | R/C | Shri Pancham CHSL | Shri Pancham Chsl, PM Kulkarni Road, Koliwada, Vazira, Borivali West, Mumbai, Maharashtra- 400092 MUMBAI | INDUS | Fibmax | Co-build | Feasible | May'25 | Virendra | Satish Singh | Feasible | 10004856 | 2025-03-26 | 2026-03-26 | 368 | Ok | -0.5 | PO Released | Part of 99 |  | FF_NW2122_785474 | CWIP-76883 | RFAI Awaited | PO Released | 779249 | Santosh Yadav | 222 | -146 | - |  | Yes
Fibmax | 2026-10-31 | 128 | MU | Borivali |  | MA2115 | MU-MA2115 | 11 | 11 | 19.2284 | 72.8405 | 19.2284 | 72.8406 | MCGM | R/C | Krishna Heritage-Gorai Asmita CHSL | Link Road, Opp. Don Bosco, Borivali (W), Mumbai 400092 | INDUS | Fibmax | Co-build | Feasible | May'25 | Virendra | Satish Singh | Feasible | 10004833 | 2025-03-26 | 2026-03-26 | 34 | PO length is greater than Feasibility Length | 23 | PO Released | Part of 99 |  | FF_NW2122_74399 | CWIP-76884 | RFAI Awaited | PO Released | 585504 | Santosh Yadav | 3 | -31 | - |  | Yes
|  | 129 | MU | Goregaon |  | MA699 | MU-MA699 | 22 | 22 | 19.1642 | 72.8578 | 19.1642 | 72.858 | MCGM | P/S | RADIUM APT. | RADIUM TOWER, PAHADI RD, MADHUSHEE CO-OPERATIVE HOUSING SOCIETY, JAY PRAKASH NAGAR, GOREGAON, MUMBAI, MAHARASHTRA 400063 | ATC | Fibmax | Co-build | Feasible | Dec'25 | Virendra | Satish Singh | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2025-10-31 | 130 | MU | Nilje gaon |  | 3128 | MU-3128 | 165 | 165 | 19.1557 | 73.0744 | 19.1589 | 73.0763 | KDMC | - | Chandresh Jyoti | Chandresh Jyoti Chs, Nilje Gaon, Kalyan-Shilphata Road, Maharashtra- 421204 DOMBIVALI | ATC | Fibmax | Co-build | Feasible | Oct'25 | Abdul Quadir | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 165 | Ok | 0 | PO Released | - |  | Not created | CWIP-76885 | RFAI Awaited | PO Released | - |  | 0 | -165 | - |  | No
Fibmax | 2026-11-30 | 131 | MU | Andheri |  | 2931 | MU-2931 | 385 | 385 | 19.1139 | 72.8513 | 19.1148 | 72.8514 | MCGM | K/E | Sai Charan | Sai_Charan_C_Wing,NS_Phadke_Road,Saiwadi,Near_Regency_Hotel,Andheri-East,Mumbai-400053 | INDUS | Fibmax | Co-build | Feasible | April'25 | Hari Yadav | Satish Singh | Feasible | 10004855 | 2025-03-26 | 2026-03-26 | 372 | PO length is less than Feasibility length | -13 | PO Released | Part of 99 |  | FF_NW2122_785475 | CWIP-76886 | RFAI Awaited | PO Released | - |  | 0 | -372 | - |  | Yes
Fibmax | 2026-11-30 | 132 | MU | Bhayander East |  | 4081 | MU-4081 | 165 | 165 | 19.3046 | 72.8537 | 19.3046 | 72.8537 | MBMC | - | JESALCMPOF | Jesal Apt.,Jesal Complex, A, Cabin Cross road, Near foot over bridge, Bhayander ( E ), Mumbai | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 165 | Ok | 0 | PO Released | - |  | Not created | CWIP-76887 | RFAI Awaited | PO Released | - |  | 0 | -165 | - |  | No
|  | 133 | MU | Dongri |  | 4858 | MU-4858 | 30.8 | 30.8 | 18.9585 | 72.8355 | 18.9584 | 72.8355 | MCGM | B | LKHDWALAO | Lokhandwala Building, S V P Road, Near Delhi Darbar, Dongri, Masjid Bunder, Mumbai-400009 | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Narayan Parab | Prem Verma | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 134 | MU | Mazgaon |  | 4880 | MU-4880 | 55 | 55 | 18.9674 | 72.8392 | 18.9674 | 72.8392 | MCGM | E | SHIREEN MANZIL (Vikrikar Bhavan ) | Shirin Manzil,18/24,behind Vikrikar Bhavan,St Mary rd,Mazgaon,Mum10 | ATC | Fibmax | Co-build | Feasible | Jan'26 | Narayan Parab | Prem Verma | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-11-30 | 135 | MU | Taloja |  | MA649 | MU-MA649 | 542 | 542 | 19.0735 | 73.099 | 19.0707 | 73.0996 | PMC | - | SHUBH ENCLAVE | Shubh Enclave, Sector 16, Taloja Panchanand, Taloja, Navi Mumbai - 410208 | INDUS | Fibmax | Co-build | Feasible | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004802 | 2025-03-26 | 2026-03-26 | 542 | Ok | 0 | PO Released | - |  | Not created | CWIP-76888 | RFAI Awaited | PO Released | - |  | 0 | -542 | - |  | Yes
Fibmax | 2026-11-30 | 136 | MU | Bhayander East |  | MA1621 | MU-MA1621 | 165 | 165 | 19.3094 | 72.8621 | 19.3094 | 72.8621 | MBMC | - | Shree Dham CHSL | Ganesh Lane, Navghar Road, Bhayander (E.) - 401105 | ATC | Fibmax | Co-build | Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004882 | 2025-03-26 | 2026-03-26 | 165 | Ok | 0 | PO Released | - |  | Not created | CWIP-76889 | Received | PO Released | - |  | 0 | -165 | - |  | Yes | Site under Relocation
Fibmax | 2026-02-28 | 137 | MU | Titwala |  | MA2398 | MU-MA2398 | 346.5 | 346.5 | 19.2974 | 73.211 | 19.2955 | 73.2121 | KDMC | - | Bhoye plot | Bhoye Open Plot, Near Regency Park, Ganpati Mandir Road, Manda, Titwala(E)-421605 | Suyog | Fibmax | Co-build | Feasible | Feb'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004787 | 2025-03-26 | 2026-03-26 | 346 | Ok | -0.5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76890 | Received | PO Released | - |  | 0 | -346 | -
Fibmax | 2026-11-30 | 138 | MU | Diva |  | MA6227 | MU-MA6227 | 154 | 154 | 19.1851 | 73.042 | 19.1843 | 73.044 | TMC | - | Chandras Shopping Center | Shop Number 4 Sai Krupa Chawl Station Road Near Shiv Sena Office Diva East, Sabe Gaon, Thane, Maharashtra 400612 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004850 | 2025-03-26 | 2026-03-26 | 154 | Ok | 0 | PO Released | - |  | Not created | CWIP-76891 | RFAI Awaited | PO Released | - |  | 0 | -154 | - |  | Yes
Fibmax | 2027-01-31 | 139 | MU | Kalyan |  | MA241 | MU-MA241 | 297 | 297 | 19.1727 | 73.1112 | 19.1711 | 73.1133 | KDMC | - | Lodha Location 1 | Mr. Ganesh (9867504678), Lodha Location 1, Khoni Village, Khoni Phata, Gate No.3, Dombivali (E), Maharashtra 421204, India | INDUS | Fibmax | Co-build | Feasible | Jan'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004857 | 2025-03-25 | 2026-03-25 | 297 | PO Pending |  | PO Released | - |  | Not created | CWIP-76892 | Received | PO Released | - |  | 0 | -297 | - |  | Yes
Fibmax | 2027-01-31 | 140 | MU | Marol |  | 2372 | MU-2372 | 10 | 10 | 19.1227 | 72.8829 | 19.1227 | 72.8829 | MCGM | K/E | Highland Park | Building No.1, Plot No.9, Bhawani Nagar, Off Marol Maroshi Road, Andheri (E.), Mumbai - 400 059 | ATC | Fibmax | Co-build | Feasible | Jan'26 | Hari Yadav | Satish Singh | Feasible | 10004816 | 2025-03-26 | 2026-03-26 | 360 | PO length is greater than Feasibility Length | 350 | PO Released | - |  | Not created | - | RFAI Awaited | PO Released | - |  | 0 | -360 | - |  | Yes
Fibmax | 2026-11-30 | 141 | MU | Bhayander East |  | MB2509 | MU-MB2509 | 11 | 11 | 19.3053 | 72.8615 | 19.305 | 72.8613 | MBMC | - | Govind Rao CHS | Navghar Naka, Bhayandar East, Mira Bhayandar, Maharashtra 401105 | INDUS | Fibmax | Co-build | Feasible | April'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004839 | 2025-03-26 | 2026-03-26 | 102 | PO length is greater than Feasibility Length | 91 | PO Released | Part of 99 |  | FF_NW2122_785476 | CWIP-76893 | Received | PO Released | - |  | 0 | -102 | - |  | Yes
Fibmax | 2026-11-30 | 142 | MU | Bandra |  | MA2576 | MU-MA2576 | 38.5 | 38.5 | 19.0677 | 72.8329 | 19.0679 | 72.8328 | MCGM | H/W | Link Apartment | Links Building Khar-Pali Road 14th Road Pali Village Khar West Mumbai Maharashtra- 400052 MUMBAI | INDUS | Fibmax | Co-build | Feasible | April'25 | Hari Yadav | Prem Verma | Feasible | 10004884 | 2025-03-26 | 2026-03-26 | 39 | Ok | 0.5 | PO Released | Part of 99 |  | FF_NW2122_785477 | CWIP-76894 | RFAI Awaited | PO Released | - |  | 0 | -39 | - |  | Yes
|  | 143 | MU | Malad |  | 1471 | MU-1471 | 308 | 308 | 19.1814 | 72.8638 | 19.18 | 72.8654 | MCGM | P/N | AKANSHA | Mr. Nilesh Bhikaji Wangnekar- 9594312315, Akanksha HM2, Kurar Village, Triveni Nagar, Pathanwadi Road, Malad East, Maharashtra- 400097 MUMBAI | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Dudhnath Tiwari | Satish Singh | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 144 | MU | Airoli |  | 319 | MU-319 | 286 | 286 | 19.167 | 73.003 | 19.1669 | 73.0042 | NMMC | - | WAKURDE NIWAS | Near Reliable Tech Park, Central Road,Airoli, Navi Mumbai | UNITY | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-04-30 | 145 | MU | Airoli |  | MB2367 | MU-MB2367 | 143 | 143 | 19.1597 | 72.991 | 19.1595 | 72.9902 | NMMC | - | Brahmaraj Developers | Sector-19, Airoli, Navi Mumbai, Maharashtra 400708 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 143 | Ok | 0 | PO Released | - |  | Not created | CWIP-76895 | RFAI Awaited | PO Released | - |  | 0 | -143 | - |  | No
Fibmax | 2026-11-30 | 146 | MU | Andheri |  | 370 | MU-370 | 66 | 66 | 19.1287 | 72.8257 | 19.1294 | 72.8257 | MCGM | K/W | Guru Nagar | Guru Nagar,Gharkul Society, Manish Nagar, Four Bungalows, Andheri West, Mumbai, Maharashtra 400053 MUMBAI | INDUS | Fibmax | Co-build | Feasible | April'25 | Hari Yadav | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 66 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15816 | CWIP-76896 | RFAI Awaited | PO Released | - |  | 0 | -66 | - |  | No
Fibmax | 2026-11-30 | 147 | MU | Versova |  | MA1855 | MU-MA1855 | 110 | 110 | 19.1283 | 72.8198 | 19.1283 | 72.8197 | MCGM | K/W | Everest | SEVEN BUNGLOW GARDEN, ANDHERI(W) MUMBAI,MAHARASHTRA, PINCODE- 400061 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Hari Yadav | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 110 | PO Pending |  | PO Released | Part of 99 |  | FF_NW2122_785478 | CWIP-76897 | RFAI Awaited | PO Released | 479033 | Santosh Yadav | 70 | -40 | - |  | No
Fibmax | 2026-01-31 | 148 | MU | Vichumbe |  | MA4114 | MU-MA4114 | 726 | 726 | 18.9852 | 73.1303 | 18.9873 | 73.1268 | PMC | - | Namarta | Namrata Complex, Sector 16, 32, Vichumbe Rd, Vichumbe Village, New Panvel East, Panvel, Navi Mumbai, Maharashtra 410206 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004819 | 2025-03-26 | 2026-03-26 | 726 | Ok | 0 | PO Released | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -726 | - |  | Yes
| 2026-11-30 | 149 | MU | Dombivali |  | MA3841 | MU-MA3841 | 1210 | 1210 | 19.1853 | 73.079 | 19.187 | 73.0891 | KDMC | - | Patil Plot | DIVA MANPADA RD,BHADRA NAGAR, DESALE PADA,DOMBIVLI, MUMBAI, MAHARASHTRA. 400612 | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Sandeep randive | Yogesh Deshpande | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | Received | Under validation | - |  | 0 | 0 | - |  | No
Fibmax | 2026-11-30 | 150 | MU | Chinchpokali |  | 4337 | MU-4337 | 742.5 | 742.5 | 18.9831 | 72.8386 | 18.983 | 72.8387 | MCGM | E | CENTINQ | Central Tin Bldg, Retiwala Ind Estate, Chinchpokli X Lane, Es Patanwala Road, Mumbai-400027 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Vaijesh Patil | Prem Verma | Feasible | 10004883 | 2025-03-26 | 2026-03-26 | 133 | PO length is less than Feasibility length | -609.5 | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -133 | - |  | Yes
| 2026-11-30 | 151 | MU | Tembhode |  | MA3052 | MU-MA3052 | 2552 | 2552 | 19.0222 | 73.1246 | 19.0337 | 73.121 | PMC | - | Sachin Kathra | Sachin Khatra,32,Vasan nagar,panvel | INDUS | Fibmax | Co-build | Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | - |  | No
Fibmax | 2026-10-31 | 152 | MU | Cheda Nagar |  | 4449 | MU-4449 | 1155 | 1155 | 19.0663 | 72.906 | 19.0631 | 72.9048 | MCGM | M/W | Naraynee chsl | Narayanee, CHEDDA NAGAR,ROAD NO.4,CHEMBUR. | ATC | Fibmax | Co-build | Feasible | Feb'26 | Narayan Parab | Yogesh Deshpande | Feasible | 10004818 | 2025-03-26 | 2026-03-26 | 1202 | PO length is greater than Feasibility Length | 47 | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -1202 | - |  | Yes
|  | 153 | MU | Charkop |  | 423 | MU-423 | 1078 | 1078 | 19.2192 | 72.8181 | 19.2157 | 72.8188 | MCGM | R/C | OMKAR BUNGLOW | Sector 8, Kandivali West,Mumbai, Maharashtra 400067 | INDUS | Fibmax | Co-build | Feasible | Feb'26 | Dudhnath Tiwari | Satish Singh | Not Feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2025-12-31 | 154 | MU | Panvel |  | MA2194 | MU-MA2194 | 517 | 517 | 18.9723 | 73.1293 | 18.9736 | 73.1277 | PMC | - | Samar Park | Palaspe Phata, New Panvel, Kalokhe, Mumbai | INDUS | Fibmax | Co-build | Not Feasible | Dec'25 | Manoj Ligade | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 517 | PO Pending |  | PO Released | - |  | Not created | CWIP-76898 | RFAI Awaited | PO Released | - |  | 0 | -517 | - |  | No
|  | 155 | MH | Panvel |  | ROM1533 | MH-ROM1533 | 138.644 | 0 | 18.9551 | 73.1623 | 18.9489 | 73.1549 | PMC | - | #N/A | #N/A | INDUS | Fibmax | Co-build | Not Feasible | Dec'25 | Manoj Ligade | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 156 | MU | Andheri |  | 306 | MU-306 | 396 | 396 | 19.1182 | 72.8509 | 19.1182 | 72.8528 | MCGM | K/E | CRESPLAIIMI1 | CRESCENT PLAZA, OPP HOTEL IMPERIAL BLUE, NEAR STATION ANDHERI (E), Mumbai 400069 | Airtel Own | Fibmax | Co-build | Not Feasible | Dec'25 | Hari Yadav | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2025-12-31 | 157 | MU | Andheri |  | 3645 | MU-3645 | 476 | 476 | 19.1182 | 72.8528 | 19.1182 | 72.8528 | MCGM | K/E | NEW MOON LIGHT | Gamdevi Bhendi Galli, Azad Nagar, Andheri Kurla Road, Andheri East, Mumbai-400053 | INDUS | Fibmax | Co-build | Not Feasible | Dec'25 | Dudhnath Tiwari | Satish Singh | Feasible | 10004790 | 2025-03-26 | 2026-03-26 | 476 | Ok | 0 | PO Released | - |  | Not created | CWIP-76899 | Received | PO Released | - |  | 0 | -476 | - |  | Yes
|  | 158 | MU | Vikroli |  | 5331 | MU-5331 | 103.052 | 0 | 19.1614 | 72.8365 | 19.1613 | 72.836 | MCGM | P/S | Dr. Ambedkar SRA CHSL R1 | Mitha Nagar, Goregaon West Mumbai, Maharashtra 400104 | INDUS | Fibmax | Co-build | Not Feasible | March'26 | Dudhnath Tiwari | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 159 | MU | Rabale |  | 679 | MU-679 | 448 | 448 | 19.1458 | 72.9923 | 19.1466 | 72.9913 | NMMC | - | Tanmay Villa | Tanmay Villa,Sector -9,Airoli ,Navi Mumbai 400708 | INDUS | Fibmax | Co-build | Not Feasible | Feb'26 | Abdul Quadir | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 160 | MU | Bandra |  | 1467 | MU-1467 | 1428.672 | 1428.672 | 19.0487 | 72.8252 | 19.0496 | 72.8231 | MCGM | H/W | BLUEHEAVO | Baptista Road, Bandra Reclamation Road, Bandra West, Mumbai-400050 | INDUS | Fibmax | Co-build | Not Feasible | Nov'25 | Vaijesh Patil | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 161 | MU | Goregaon |  | 4019 | MU-4019 | 418 | 418 | 19.1692 | 72.8811 | 19.1686 | 72.8805 | MCGM | P/N | Mantri Park | Mantri Park,Mhada Colony,Near Goregaon Film City 400 104 | Airtel Own | Fibmax | Co-build | Not Feasible | March'26 | Virendra | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-05-31 | 162 | MU | Kashimira |  | MA882 | MU-MA882 | 11 | 11 | 19.288 | 72.8804 | 19.288 | 72.8804 | MBMC | - | Gaurav Ratan 5 & 6 | Gaurav Enclave Road, Mira Road (E.)Maharashtra 401107 | ATC | Fibmax | Co-build | Not Feasible | May'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 11 | PO Pending |  | PO Released | - |  | Not created | - | RFAI Awaited | PO Released | - |  | 0 | -11 | - |  | No
Fibmax | 2026-01-31 | 163 | MU | Kandivali |  | MB3510 | MU-MB3510 | 422.532 | 0 | 19.2036 | 72.853 | 19.2047 | 72.8513 | MCGM | R/S | Tirupati CHS | TIRUPATI CHS,AKURLI CROSS RD NUMBER 1, KANDIVALI, AARYA CHANAKYA NAGAR, KANDIVALI EAST,POST OFFICE:-KANDIVALI,POLICE STATION:-KANDIVALI | INDUS | Fibmax | Co-build | Not Feasible | March'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 110 | Ok | 110 | PO Released | - |  | Not created | CWIP-76900 | Received | PO Released | - |  | 0 | -110 | - |  | No
Fibmax | 2026-10-31 | 164 | MU | Kandivali |  | 5504 | MU-5504 | 100 | 0 | 19.196 | 72.839 | 19.196 | 72.839 | MCGM | P/N | CASBLNCAONM1 | Casablanca,2nd Dominic Colony, near UTI Bank, Orlem, Malad West | INDUS | Fibmax | Co-build | Not Feasible | March'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004851 | 2025-03-26 | 2026-03-26 | 25 | Ok | 25 | PO Released | - |  | Not created | CWIP-76901 | Received | PO Released | - |  | 0 | -25 | - |  | Yes
|  | 165 | MU | Versova |  | 403 | MU-403 | 429 | 429 | 19.1391 | 72.8113 | 19.14 | 72.8126 | MCGM | K/W | ZA TOWER | Amit Nagar, Versova, Andheri West,Mumbai, Maharashtra 400047 | INDUS | Fibmax | Co-build | Not Feasible | March'26 | Virendra | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-10-31 | 166 | MU | Airoli |  | 3099 | MU-3099 | 682 | 682 | 19.1522 | 72.9958 | 19.1524 | 72.9951 | NMMC | - | Mauli Vyapar Shankul | MAULI VYPAR SANKUL PLOT NO 40 SEC 5 AIROLI NAVI MUMBAI | ATC | Fibmax | Co-build | more than 500 mtr | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 517 | PO length is less than Feasibility length | -165 | PO Released | - |  | Not created | CWIP-76902 | Received | PO Released | - |  | 0 | -517 | - |  | No
|  | 167 | MU | Bandra |  | 5767 | MU-5767 | 1430 | 1430 | 19.0484 | 72.827 | 19.0515 | 72.8271 | MCGM | H/W | Ambro Bldg | Emro CHS,Reclamation,Nr. Bus Depot, Bandra W. | ATC | Fibmax | Co-build | more than 500 mtr | May'25 | Hari Yadav | Prem Verma | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 168 | MU | Borivali |  | 1550 | MU-1550 | 737 | 737 | 19.2412 | 72.8642 | 19.2415 | 72.865 | MCGM | R/N | NANCYFLYOVR | MR. VINOD- 9594760634, MMRDA-FOBR-NancyColony, Borivali-1, Near Western Express Highway, Ratan Nagar, Borivali East, Mumbai, Maharashtra- 400066 MUMBAI | Suyog | Fibmax | Co-build | more than 500 mtr | May'25 | Virendra | Satish Singh | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
| 2027-01-31 | 169 | MU | Palava City |  | 6279 | MU-6279 | 2420 | 2420 | 19.1464 | 73.0772 | 19.1579 | 73.1177 | KDMC | - | Casa Rio near Building River dale | Mr. Rajesh Mhatare (9930372079), Casa Rio, near Building River dale , Cooperative Housing Society, Nilje Gaon, Maharashtra 421204 DOMBIVALI | INDUS | Fibmax | Co-build | more than 500 mtr | Jan'26 | Abdul Quadir | Yogesh Deshpande | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | Received | Under validation | - |  | 0 | 0 | - |  | No
|  | 170 | MU | Taloja |  | MB2619 | MU-MB2619 | 550 | 550 | 19.0651 | 73.1125 | 19.0673 | 73.1178 | PMC | - | J J Electrofab | J.J.electrofab,PLOT NO. D1, TALOJA | ATC | Fibmax | Co-build | more than 500 mtr | Dec'25 | Abdul Quadir | Praveen Nigam | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-04-30 | 171 | MU | Titwala |  | MA1336 | MU-MA1336 | 712.8 | 712.8 | 19.2943 | 73.2009 | 19.2964 | 73.2048 | KDMC | - | Mahendra Service Center | Sangoda Rd, Titwala, Maharashtra 421605 | ATC | Fibmax | Co-build | more than 500 mtr | Feb'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 11 | PO length is less than Feasibility length | -701.8 | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -11 | - |  | Yes
Fibmax | 2026-10-31 | 172 | MU | Dombivali |  | MA4735 | MU-MA4735 | 858 | 858 | 19.1846 | 73.0958 | 19.1878 | 73.0925 | KDMC | - | Vishnu Valley | KHONI-UMBHARLI GAON - KALAYN SHI RD, VILLAGE-MANGAON, SONAR PADA, DOMBIVLI EAST,THANE,MAHARASHTRA, PINCODE- 421203 | ATC | Fibmax | Co-build | more than 500 mtr | Nov'25 | Sandeep randive | Yogesh Deshpande | Feasible | 10004871 | 2025-03-26 | 2026-03-26 | 858 | Ok | 0 | PO Released | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -858 | - |  | Yes
Fibmax | 2026-04-30 | 173 | MU | Ambivli |  | 1297 | MU-1297 | 981.2 | 981.2 | 19.2699 | 73.1705 | 19.2648 | 73.1738 | KDMC | - | NUTANSHIVKR | Nuten Shiv Karpa Near Ambivali Station Road (W)-421102 | ATC | Fibmax | Co-build | more than 500 mtr | Feb'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 422 | PO length is less than Feasibility length | -559.2 | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -422 | - |  | No
Fibmax | 2026-10-31 | 174 | MU | Titwala |  | MA3828 | MU-MA3828 | 903.1 | 903.1 | 19.2963 | 73.2003 | 19.2964 | 73.2048 | KDMC | - | Ramchandra Heights | Ramchandra Height, Behind Police Station Manda, Sangoda Road, Manda, Titwala(W), Dist-Thane-421605 | Suyog | Fibmax | Co-build | more than 500 mtr | March'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 682 | PO length is less than Feasibility length | -221.1 | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | -682 | - |  | No
|  | 175 | MU | Panvel |  | MB2693 | MU-MB2693 | 550 | 550 | 18.98 | 73.0956 | 18.9785 | 73.0934 | PMC | - | Shankar Parvati niwas | Navi Mumbai, Maharashtra 410206 | INDUS | Fibmax | Co-build | more than 500 mtr | Dec'25 | Abdul Quadir | Praveen Nigam | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 176 | MU | Kalwa |  | 5095 | MU-5095 | 891 | 891 | 19.1939 | 72.9924 | 19.1968 | 72.9916 | TMC | - | AMRUT ARCADE | Amrut Arcade,Amrut Tower,Thane Chinchpada,Stn Road,Kalwa West | ATC | Fibmax | Co-build | more than 500 mtr | Dec'25 | Manoj Ligade | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
|  | 177 | MU | Kalwa |  | 660 | MU-660 | 2750 | 2750 | 19.209 | 73.0077 | 19.2114 | 73.0082 | TMC | - | Appa salvi open plo | A-4, Parsik Nagar, Kalwa, Thane mumbai | INDUS | Fibmax | Co-build | more than 500 mtr | May'25 | Manoj Ligade | Yogesh Deshpande | Not feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 178 | MU | Fort |  | MB328 | MU-MB328 | 194.53 | 0 | 18.9412 | 72.8333 | 18.9406 | 72.8326 | MCGM | A | BMC Head Office | Municipal Corporation Of Greater Mumbai 4 Building-1, MCGM Sabhagruh Rd, Dhobi Talao, Chhatrapati Shivaji Terminus Area, Fort, Mumbai, Maharashtra 400001 | Netsol | Fibmax | Co-build | Data mismatch | March'26 | Narayan Parab | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2025-11-30 | 179 | MU | Bandra |  | 434 | MU-434 | 56 | 56 | 19.0626 | 72.8275 | 19.0628 | 72.8277 | MCGM | H/W | PALI REC-STN(Adani Sub Station) | ADANI SUB STATION, PALI BANDRA, 223, ST ANDREWS RD, BANDRA WEST, MUMBAI, MAHARASHTRA 400050 | INDUS | Fibmax | Co-build | Data mismatch | Nov'25 | Prem Verma | Prem Verma | Feasible | 10004725 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released | - |  | Not created | CWIP-76903 | RFAI Awaited | PO Released | - |  | 0 | -56 | - |  | Yes
Fibmax | 2026-02-28 | 180 | MU | Seawoods |  | MA1813 | MU-MA1813 | 100 | 0 | 19.0242 | 73.0185 | 19.0242 | 73.0186 | NMMC | - | CENTRE COURT | Nr-SEAWOOD RLY STATION,SEC-23,NERUL,NAVI MUMBAI MAHARASHTRA-400706 | INDUS | Fibmax | Co-build | Data mismatch | Feb'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 100 | Ok | 100 | PO Released | - |  | Not created | CWIP-76904 | RFAI Awaited | PO Released | - |  | 0 | -100 | - |  | Yes
Fibmax | 2025-11-30 | 181 | MU | Koparkhairane |  | MB2632 | MU-MB2632 | 123.124 | 0 | 19.0985 | 73.0173 | 19.0985 | 73.0173 | NMMC | - | Saif Chemical Pvt. Ltd. | TTC industrial area, MIDC Industrial area,Kopar Khairne, Navi mumbai | ATC | Fibmax | Co-build | Data mismatch | Nov'25 | Narayan Parab | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 123 | Ok | 123 | PO Released | - |  | Not created | CWIP-76905 | Received | PO Released | - |  | 0 | -123 | - |  | No
Fibmax | 2026-05-31 | 182 | MU | Thane |  | 4690 | MU-4690 | 11 | 11 | 19.2371 | 72.9741 | 19.2371 | 72.9741 | TMC | - | Babu Bhai Plot | NEAR GREEN STROKES ART GALLERY, MANPADA THANE WEST | INDUS | Fibmax | Co-build | Data mismatch | May'25 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 11 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785479 | CWIP-76906 | Received | PO Released | - |  | 0 | -11 | - |  | No
|  | 183 | MU | Jogeshwari |  | MA5091 | MU-MA5091 | 163.89 | 0 | 19.1448 | 72.8435 | 19.1448 | 72.8435 | MCGM | K/W | Lovely Home | SUFI SAYED KAMAL AHMED MARG, KHOJA SOCIETY, VAISHALI NAGAR, JOGESHWARI, MUMBAI, MAHARASHTRA 400102 | INDUS | Fibmax | Co-build | Data mismatch | March'26 | Dudhnath Tiwari | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-05-31 | 184 | MU | Kharghar |  | 880 | MU-880 | 420.8972 | 0 | 19.0354 | 73.077 | 19.0354 | 73.077 | PMC | - | Shivtirth | Shivtirth CHSL, Kopra Rd.,Anushakti nagar,sector 10, Kharghar, Navi Mumbai, Maharashtra 410210 KAMOTE | INDUS | Fibmax | Co-build | Data mismatch | May'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 420 | Ok | 420 | PO Released | Part of 99 |  | FF_NW2122_785480 | CWIP-76907 | RFAI Awaited | PO Released | - |  | 0 | -420 | Pending |  | Yes
| 2026-05-31 | 185 | MU | Kharghar |  | 4997 | MU-4997 | 606.046 | 0 | 19.0348 | 73.0742 | 19.0347 | 73.0742 | PMC | - | Atmaram | Atmaram,Atmaram ghaikar residency,kopra Vill, Belapur panwel highway, kharghar | ATC | Fibmax | Co-build | Data mismatch | May'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | - |  | No
| 2026-05-31 | 186 | MU | Kharghar |  | 3989 | MU-3989 | 597.004 | 0 | 19.0328 | 73.0616 | 19.0328 | 73.0616 | PMC | - | ANUVIGYAN | Plot No10, Sector 4, Kharghar, Mumbai-410210 | INDUS | Fibmax | Co-build | Data mismatch | May'25 | Abdul Quadir | Praveen Nigam | Feasible | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | - |  | No
Fibmax | 2025-12-31 | 187 | MU | Airoli |  | 5508 | MU-5508 | 435.042 | 0 | 19.1512 | 72.9932 | 19.1512 | 72.9931 | NMMC | - | Airoli Plaza - B Chsl | Airoli Plaza-B CHSL,Sec 16,Airoli | INDUS | Fibmax | Co-build | Data mismatch | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 435 | Ok | 435 | PO Released | - |  | Not created | CWIP-76908 | RFAI Awaited | PO Released | - |  | 0 | -435 | - |  | No
Fibmax | 2026-10-31 | 188 | MU | Vile Parle |  | MB2355 | MU-MB2355 | 157.27 | 0 | 19.0933 | 72.8485 | 19.0933 | 72.8485 | MCGM | K/E | Vasant Smurti | Vasant Smruti,Plot No:- 352, Nanda Patkar Rd Ext, Navpada, Vile Parle East, Vile Parle, Mumbai, Maharashtra 400057 | INDUS | Fibmax | Co-build | Data mismatch | March'26 | Hari Yadav | Satish Singh | Feasible | 10004836 | 2025-03-26 | 2026-03-26 | 102 | Ok | 102 | PO Released | - |  | Not created | CWIP-76909 | RFAI Awaited | PO Released | - |  | 0 | -102 | - |  | Yes
Fibmax | 2025-11-30 | 189 | MU | Koparkhairane |  | 8 | MU-8 | 170.574 | 0 | 19.1114 | 73.0151 | 19.1112 | 73.0155 | NMMC | - | Rupa Solitaire | Rupa Solitaire , MBP, Mahape, Navi Mumbai | Airtel Own | Fibmax | Co-build | Data mismatch | Nov'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004809 | 2025-03-26 | 2026-03-26 | 171 | Ok | 171 | PO Released | - |  | Not created | CWIP-76910 | RFAI Awaited | PO Released | - |  | 0 | -171 | - |  | Yes
|  | 190 | MU | MANKHURD |  | MA769 | MU-MA769 | 100 | 0 | 19.0563 | 72.9289 | 19.0565 | 72.9291 | MCGM | M/E | Ayub Traders | MANHUROAD WEST, DR.BABSAHEB AMBEDKER NAGAR, GOVANDI EAST, MUMBAI, MAHARASHTRA 400001 | Rakshit | Fibmax | Co-build | Data mismatch | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 191 | MU | Cheda Nagar |  | MB2229 | MU-MB2229 | 100 | 0 | 19.0711 | 72.9078 | 19.0714 | 72.9077 | MCGM | N | Chedhanagar Flyover | Flyover No:-01,AMSP-17,Chheda Ngr Junction Highway Ghatkopar,Mumbai - Agra National Hwy, Sector 3, Chedda Nagar, Mumbai, Maharashtra 400089 | OSR | Fibmax | Co-build | Data mismatch | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 192 | MU | Chembur |  | 1852 | MU-1852 | 167.238 | 0 | 19.0411 | 72.8986 | 19.041 | 72.8986 | MCGM | M/E | GIRNARH | Dongre Park, Behind Rcf Colony, Chembur 400071 | INDUS | Fibmax | Co-build | Data mismatch | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-04-30 | 193 | MU | Powai |  | 4501 | MU-4501 | 100 | 0 | 19.1201 | 72.895 | 19.1202 | 72.8953 | MCGM | L | GOLDENRAO | Golden Rays,Raheja Vihar Chandivali | INDUS | Fibmax | Co-build | Data mismatch | April'26 | #N/A | Yogesh Deshpande | Feasible | 10004837 | 2025-03-26 | 2026-03-26 | 64 | Ok | 64 | PO Released | - |  | Not created | CWIP-76911 | RFAI Awaited | PO Released | - |  | 0 | -64 | - |  | Yes
Fibmax | 2026-04-30 | 194 | MU | Sion |  | MA3132 | MU-MA3132 | 100 | 0 | 19.0416 | 72.8528 | 19.0416 | 72.8528 | MCGM | G/N | Aziz House_Suyog Rizwan | RP NAGAR, DHARAVI, DISTRICT-MUMBAI, STATE- MAHARASHTRA, PINCODE- 400017 | Suyog | Fibmax | Co-build | Data mismatch | April'26 | Prem Verma | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 100 | Ok | 100 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76912 | Received | PO Released | - |  | 0 | -100 | -
Fibmax | 2025-12-31 | 195 | MU | Navde |  | MB2765 | MU-MB2765 | 100 | 0 | 19.0493 | 73.103 | 19.0493 | 73.103 | PMC | - | Divya Sai Sahkari Gruhnirman Sanstha | Plot Number 51, Phase 2, Navde, Post office:- Navde, Police station:-Navde ,Navi Mumbai, Maharashtra 410208 | Netsol | Fibmax | Co-build | Data mismatch | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004786 | 2025-03-26 | 2026-03-26 | 560 | Ok | 560 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76914 | RFAI Awaited | PO Released | - |  | 0 | -560 | -
Fibmax | 2026-11-30 | 196 | MU | Sewri |  | MB1615 | MU-MB1615 | 100 | 0 | 18.9777 | 72.8421 | 18.9777 | 72.8421 | MCGM | E | KIF Tower B wing | B Wing ,KIF Tower, Keshrinath Ramchandra Mhatre Marg , Mazgaon , Near Reay Road Rly Station [ W ] Mumbai - 400010 | INDUS | Fibmax | Co-build | Data mismatch | April'26 | Narayan Parab | Prem Verma | Feasible | 10004834 | 2025-03-26 | 2026-03-26 | 482 | Ok | 482 | PO Released | Part of 99 |  | FF_NW2122_785481 | - | RFAI Awaited | PO Released | - |  | 0 | -482 | - |  | Yes
|  | 197 | MU | Malad |  | 6172 | MU-6172 | 100 | 0 | 19.1917 | 72.8502 | 19.1917 | 72.8502 | MCGM | P/N | CHANDRIKOF | Chandrika Apartment,Manchubhai Rd,Mahavir Nagar, Malad East,Mumbai, Maharashtra 400097 | INDUS | Fibmax | Co-build | Data mismatch | April'26 | Virendra | #N/A | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2026-05-31 | 198 | MU | Kharghar |  | 1734 | MU-1734 | 100 | 0 | 19.0487 | 73.0788 | 19.0487 | 73.0788 | PMC | - | Payal Heights | Payal Heights,Payal Heights,Kharghar. | ATC | Fibmax | Co-build | Data mismatch | May'25 | Narayan Parab | Praveen Nigam | Feasible | 10004811 | 2025-03-26 | 2026-03-26 | 302 | Ok | 302 | PO Released | Part of 99 |  | FF_NW2122_785482 | CWIP-76915 | Received | PO Released | - |  | 0 | -302 | Pending |  | Yes
Fibmax | 2026-10-31 | 199 | MU | Bamandongri |  | MA3759 | MU-MA3759 | 100 | 0 | 18.9762 | 73.0326 | 18.9762 | 73.0326 | PMC | - | Divine Royal | Plot No. 158, Sector-23, Ulwe, Navi Mumbai-410206 | INDUS | Fibmax | Co-build | Data mismatch | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004870 | 2025-03-26 | 2026-03-26 | 450 | Ok | 450 | PO Released | - |  | Not created | CWIP-76916 | RFAI Awaited | PO Released | - |  | 0 | -450 | - |  | Yes
Fibmax | 2026-04-30 | 200 | MU | Mulund |  | 5225 | MU-5225 | 100 | 0 | 19.1773 | 72.9622 | 19.1775 | 72.9625 | MCGM | T | SRIKRSHNOMM1 | 40 Feet Dp Road, Neelam Nagar, Mulund East, Mumbai-400081 | INDUS | Fibmax | Co-build | Data mismatch | April'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 100 | PO Pending |  | PO Released | - |  | Not created | CWIP-76917 | Received | PO Released | - |  | 0 | -100 | - |  | No
|  | 201 | MU | Saki Naka |  | MB1134 | MU-MB1134 | 177.736 | 0 | 19.0986 | 72.8844 | 19.0986 | 72.8844 | MCGM | L | Dattani_Plaza | Dattani Plaza, Mehra Compound Road, Safed Pul, Saki Naka, Mumbai, Maharashtra 400072 | Kasper | Fibmax | Co-build | Data mismatch | April'26 | Sabhajeet Maurya | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-10-31 | 202 | MU | Titwala |  | MA28 | MU-MA28 | 168 | 168 | 19.2955 | 73.2078 | 19.2958 | 73.2074 | KDMC | - | Ratnakar Patil Open Plot_Crack | Siddhivinayak Colony, Near Savarkar Nagar, Ganpati Mandir Road, Nimkar Naka,Titwala East, Titwala, Maharashtra 421605 | INDUS | Fibmax | Co-build | De-Scope_Feasible | March'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004783 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76918 | Received | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-10-31 | 203 | MU | Titwala |  | MB1591 | MU-MB1591 | 280 | 280 | 19.2845 | 73.1978 | 19.2833 | 73.1974 | KDMC | - | Hibiscus CHSL A¦Wing | Hibiscus CHSL A Wing , Baneli, Maharashtra 421102 | ATC | Fibmax | Co-build | De-Scope_Feasible | March'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004880 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76919 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-05-31 | 204 | MU | Shahad |  | MA312 | MU-MA312 | 112 | 112 | 19.2516 | 73.152 | 19.2511 | 73.1513 | KDMC | - | Prakriti-Suryakant Open Plot_Crack | NEAR BAJAJ PRAKRITI ANGAN, NEAR YOGIDHAM, GAURIPADA, KALYAN, MUMBAI, MAHARASHTRA 421301 | INDUS | Fibmax | Co-build | De-Scope_Feasible | March'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004690 | 2025-03-24 | 2026-03-24 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76920 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-11-30 | 205 | MU | Khadakpada |  | MA72 | MU-MA72 | 112 | 112 | 19.2476 | 73.15 | 19.2484 | 73.1494 | KDMC | - | Tusli Pushpa_Indus | TULSI PUSHPA, MILIND NAGER GAURUUPADA KALYAN (W),MUMBAI, MAHARASHTRA. | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004844 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785483 | CWIP-76921 | RFAI Awaited | PO Released | - |  | 0 | -112 | Pending |  | Yes
Fibmax | 2026-11-30 | 206 | MU | Khadakpada |  | MA6498 | MU-MA6498 | 168 | 168 | 19.2495 | 73.1491 | 19.2497 | 73.1492 | KDMC | - | SHRUTI COMPLEX B-WING | C.Wing, Gauri Pada Road, behind Birla College, Kalyan West | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004878 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15263 | CWIP-76922 | RFAI Awaited | PO Released | - |  | 0 | -168 | Pending |  | Yes
Fibmax | 2026-11-30 | 207 | MU | Khadakpada |  | MA1048 | MU-MA1048 | 280 | 280 | 19.2522 | 73.1367 | 19.253 | 73.1372 | KDMC | - | Orchid(Type J) | FLOWER VALLEY,KHADAK PADA CIRCLE,BIRLA COLLEGE ROAD,KALYAN(W).CONTACT NO 9821051520 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004830 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785484 | CWIP-76923 | RFAI Awaited | PO Released | 981839 |  | 127 | -153 | - |  | Yes
Fibmax | 2026-11-30 | 208 | MU | Khadakpada |  | MA6019 | MU-MA6019 | 280 | 280 | 19.2573 | 73.1303 | 19.2585 | 73.1308 | KDMC | - | Gaikar Bunglow | NITIN LONARI, SURVEY NO. 60, AUTO BABA, NEAR TVS SHOWROOM, NIKKI NAGAR,KALYAN WEST,421301 | ATC | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004867 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785485 | CWIP-76924 | RFAI Awaited | PO Released | - |  | 0 | -280 | Pending |  | Yes
Fibmax | 2026-10-31 | 209 | MU | Kalyan |  | MA5099 | MU-MA5099 | 224 | 224 | 19.25 | 73.1288 | 19.25 | 73.1277 | KDMC | - | Gajanan Maharaj Krupa_Indus | , DURGA NAGAR,BETURKAR PADA,KALYAN WEST, MUMBAI, MAHARASHTRA. | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004842 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76925 | Received | PO Released | - |  | 0 | -224 | - |  | Yes
|  | 210 | MU | Kalyan |  | 2366 | MU-2366 | 280 | 280 | 19.2542 | 73.1262 | 19.2535 | 73.1264 | KDMC | - | Shiv Darshan D-11 | Shiv Darshan D-11, Adharwadi Chowk, Kalyan(W), Maharashtra 421301 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 211 | MU | Kalyan |  | MA1730 | MU-MA1730 | 280 | 280 | 19.2416 | 73.122 | 19.2409 | 73.1213 | KDMC | - | Najam Palace | Anna Saheb Vartak Rd,Dudh naka, Bhoiwada, Kalyan, Maharashtra 421301, | Rakshit | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 212 | MU | Panvel |  | MA1227 | MU-MA1227 | 268.8 | 268.8 | 18.9867 | 73.1123 | 18.9879 | 73.1124 | PMC | - | Vasant Smruti - JK Plaza | JK PLAZA, PLOT NO 127, SUNDARAM SHIVA CHOWK, MTNL RD, OLD PANVEL,NAVI MUMBAI, DISTRICT-RAIGAD,410206 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2027-01-31 | 213 | MU | Dombivali |  | MB2863 | MU-MB2863 | 112 | 112 | 19.2197 | 73.1103 | 19.2204 | 73.1107 | KDMC | - | Rakesh Marble Plot | Tata Power Company Limited, Dombivli East, Dombivli, Maharashtra,Police station:-Dombivli,police station:-Dombivli | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004726 | 2025-03-24 | 2026-03-24 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76926 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2027-01-31 | 214 | MU | Roadpali |  | MA2049 | MU-MA2049 | 224 | 224 | 19.0393 | 73.1062 | 19.0389 | 73.1052 | PMC | - | Sapana | Sapana CHSL,Cremation Service,Kudupada, Kalamboli | ATC | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004754 | 2025-03-25 | 2026-03-25 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76927 | Received | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2027-02-28 | 215 | MU | Panvel |  | 4917 | MU-4917 | 11.2 | 11.2 | 18.9893 | 73.105 | 18.991 | 73.1048 | PMC | - | Adil Tower | Adil Tower,Kanchi Mahala Bandar Road,Panvel(Old)-410206 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004766 | 2025-03-25 | 2026-03-25 | 11 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-76928 | RFAI Awaited | PO Released | - |  | 0 | -11 | - |  | Yes
Fibmax | 2027-02-28 | 216 | MU | Navde |  | MB3502 | MU-MB3502 | 224 | 224 | 19.0505 | 73.1045 | 19.051 | 73.1041 | PMC | - | Shree Ganesh | Navde Rd, Navde, Taloja, Navi Mumbai, Maharashtra 410208,post office:-Navde,police station:-Navde | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76929 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2027-02-28 | 217 | MU | Dombivali |  | MA3832 | MU-MA3832 | 112 | 112 | 19.2019 | 73.0951 | 19.2015 | 73.0965 | KDMC | - | Om Sai Ganesh Plaza_Crack | 3, HIRAMAN DAMU MHATRE BUILDING, NEAR SAI BABA TEMPLE, MANPADA ROAD, DOMIVLI(EAST), MANPADA ROAD, SAGAON, DOMBIVLI EAST,421203 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004736 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76930 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2027-02-28 | 218 | MU | Dombivali |  | 2798 | MU-2798 | 168 | 168 | 19.2179 | 73.0878 | 19.219 | 73.087 | KDMC | - | MDUBANCIINI1 | Madhuban Cinema Kalyan, Dombivali ( E). Maharashtra 421201 | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004753 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76931 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-05-31 | 219 | MU | Taloja |  | MB3311 | MU-MB3311 | 224 | 224 | 19.0735 | 73.0765 | 19.0742 | 73.0763 | PMC | - | Sukh Samrudhi | SUKH SAMRUDHI,33FG+CJH, SECTOR 34C, KUTAK BANDHAN, KHARGHAR, NAVI MUMBAI, MAHARASHTRA | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004761 | 2025-03-25 | 2026-03-25 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76932 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-04-30 | 220 | MU | Kiravali |  | MB1584 | MU-MB1584 | 112 | 112 | 19.1081 | 73.0652 | 19.1096 | 73.0658 | PMC | - | Saif lifter | Plot No.36, NH Near Dhansar Bus Stop Mumbra At Adivali Kirwali, Taloja Bypass Nitalas Link Road, Panvel,Navi Mumbai, Maharashtra 410208 | ATC | Fibmax | Co-build | De-Scope_Feasible | Feb'26 | Jayhind Yadav | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76933 | Received | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-04-30 | 221 | MU | JNPT |  | MA2866 | MU-MA2866 | 246.4 | 246.4 | 18.9265 | 73.028 | 18.9256 | 73.0287 | JNPT | - | Nilkhant Gharat Open plot | Chirle Village, Paundkhar, Uran, Maharashtra 410206 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Feb'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004738 | 2025-03-25 | 2026-03-25 | 246 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76934 | RFAI Awaited | PO Released | - |  | 0 | -246 | - |  | Yes
Fibmax | 2026-11-30 | 222 | MU | Seawoods |  | MB1481 | MU-MB1481 | 280 | 280 | 19.0226 | 73.0176 | 19.0219 | 73.0159 | NMMC | - | L&T Seawoods¦Tower¦1 | L & T-Tower-1,Seawoods,Grand Central,40,Seawoods Station, Navi Mumbai-400 706. | ATC | Fibmax | Co-build | De-Scope_Feasible | April'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004756 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785486 | CWIP-76935 | Received | PO Released | - |  | 175 | -105 | - |  | Yes
Fibmax | 2026-11-30 | 223 | MU | Ghansoli |  | MA73 | MU-MA73 | 280 | 280 | 19.1166 | 73.0043 | 19.1166 | 73.0052 | NMMC | - | Mahesh Apartment | Shree Durga Complex,Charu Patil Marg,Savali, Ghansoli,Navi Mumbai, Maharashtra 400701 | ATC | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004740 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785487 | CWIP-76936 | Received | PO Released | - |  | 0 | -280 | - |  | Yes | Site under Relocation
Fibmax | 2026-11-30 | 224 | MU | Ghansoli |  | MA3055 | MU-MA3055 | 280 | 280 | 19.1271 | 73.0019 | 19.1257 | 73.0013 | NMMC | - | Mauli CHS | Mauli CHS, Talvali Naka, Ghansoli Gaon, Ghansoli, Navi Mumbai, Maharashtra- 400701 NAVI MUMBAI | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004752 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_25885 | CWIP-76937 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-11-30 | 225 | MU | Turbhe |  | 1640 | MU-1640 | 168 | 168 | 19.0809 | 72.9987 | 19.0805 | 72.998 | NMMC | - | SUNGRACEO | F-1, Sector -10, Vashi, Navi Mumbai - 400 703 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_14155 | CWIP-76938 | Received | PO Released | - |  | 0 | -168 | - |  | Yes
|  | 226 | MU | Ghansoli |  | MA6505 | MU-MA6505 | 280 | 280 | 19.1238 | 72.997 | 19.125 | 72.9975 | NMMC | - | Motiram Society | Chintamani Mangel Karyalaya Opposite Union Bank Ghansoli Villege Navi Mumbai-400701 | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'25 | Abdul Quadir | Praveen Nigam | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 227 | MU | Grant Rd |  | MA6340 | MU-MA6340 | 180.768 | 180.768 | 18.9638 | 72.8249 | 18.9643 | 72.824 | MCGM | E | Pujari Bldg | 262, Bapty Road, Kamatipura, 1st Lane, Kamatipura | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'26 | Narayan Parab | Prem Verma | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-11-30 | 228 | MU | Vashi |  | 4495 | MU-4495 | 134.4 | 134.4 | 19.0824 | 72.9964 | 19.083 | 72.9964 | NMMC | - | SHNTSAGROF | SHANTI SASGAR,BLDG NO -2,SECTOR-10,VASHI,NAVI -400703 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004743 | 2025-03-25 | 2026-03-25 | 134 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW2122_68240 | CWIP-76939 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2026-11-30 | 229 | MU | Ghansoli |  | MA3916 | MU-MA3916 | 280 | 280 | 19.1242 | 72.9933 | 19.1244 | 72.9923 | NMMC | - | Ramesh Patil ( alt of SHAM PATIL) | Ramesh Patil ,Asha Shyam Patil, Ghansoli, Koul Ali, navi Mumbai - 400 701 | ATC | Fibmax | Co-build | De-Scope_Feasible | April'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004746 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785488 | CWIP-76940 | Received | PO Released | - |  | 0 | -280 | - |  | Yes
|  | 230 | MU | Kalwa |  | MA3683 | MU-MA3683 | 280 | 280 | 19.2011 | 72.9905 | 19.1998 | 72.9911 | TMC | - | Matoshree Janki Plot | Opp. Chawl No. 8 & 9, Matoshree Jankinagar Rahivashi Sangh, Creek Road, Manisha Nagar, Kalwa (W.), Thane - 400 605 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | Received | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 231 | MU | Balkum |  | 2245 | MU-2245 | 280 | 280 | 19.2159 | 72.9898 | 19.2168 | 72.9909 | TMC | - | MADVI BUILDING | Saket Rd, Laxmi Nagar, Balkum, Majiwada, Thane W | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-11-30 | 232 | MU | Thane |  | MA943 | MU-MA943 | 168 | 168 | 19.2536 | 72.9864 | 19.2537 | 72.9856 | TMC | - | HIRANANDANI Labour Camp_ Naik Open Plot | PALM TREE LANE, HIRANANDANI ESTATE, THANE W, THANE MUMBAI, MAHARASHTRA. 400607 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004757 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785489 | CWIP-76941 | Received | PO Released | - |  | 0 | -168 | Pending |  | Yes
|  | 233 | MU | Thane |  | MB3890 | MU-MB3890 | 280 | 280 | 19.2404 | 72.9814 | 19.2401 | 72.9809 | TMC | - | BHARMAND PHASE 1 CHS | BHARMAND PHASE 1 CHS,BRAHMAND PHASE1, SANDOZ BAUG, THANE WEST, THANE,POST OFFICE-SANDOZ BAUG POST OFFICE,POLICE STATION-MANORAMA NAGAR POLICE CHOWKI | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 234 | MU | Thane |  | MA3180 | MU-MA3180 | 280 | 280 | 19.1873 | 72.9783 | 19.1877 | 72.977 | TMC | - | Earth Galaxy | Behind S. T. Bus Depot,, Chendani, Koliwada, Thane West, Maharashtra 400602 | ATC | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-04-30 | 235 | MU | Mulund |  | 5286 | MU-5286 | 56 | 56 | 19.1736 | 72.9644 | 19.1737 | 72.9642 | MCGM | T | AKSHAYAPOF | Akshay Apartment, Gavanpada Road, Mulund East, Mumbai, Maharashtra 400081 MUMBAI | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004702 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released | - |  | Not created | CWIP-76942 | Received | PO Released | - |  | 0 | -56 | - |  | Yes
Fibmax | 2026-10-31 | 236 | MU | Santacruz |  | MB4482 | MU-MB4482 | 112 | 112 | 19.22 | 72.9621 | 19.22 | 72.9624 | TMC | - | Bethany hospital | Bethany Hospital, Pokharan Rd Number 2, Shastri Nagar, Thane West, Thane, Maharashtra 400606 | Crest Digitel | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004749 | 2025-03-25 | 2026-03-25 | 112 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76943 | RFAI Awaited | PO Released | - |  | 0 | -112 | -
Fibmax | 2026-04-30 | 237 | MU | Mulund |  | 1788 | MU-1788 | 168 | 168 | 19.1764 | 72.9599 | 19.1777 | 72.9598 | MCGM | T | Nirmal Ecstacy (Spacetelelink Sharing) | Ecstasy Business Park, City of Joy, Jata Shankar Dosa Road, Mulund West, Mumbai, Maharashtra-400080 | Crest Digitel | Fibmax | Co-build | De-Scope_Feasible | April'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004700 | 2025-03-24 | 2026-03-24 | 168 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76944 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  |  | Site under Relocation
Fibmax | 2026-04-30 | 238 | MU | Trombay |  | 4014 | MU-4014 | 168 | 168 | 19.035 | 72.9492 | 19.0359 | 72.9486 | MCGM | M/E | SOYUZCMPO | Trombay koliwala,sion trombay road,Mum-88 | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'26 | Sandeep randive | Prem Verma | Feasible | 10004737 | 2025-03-25 | 2026-03-25 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76945 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-04-30 | 239 | MU | Vikroli |  | 2122 | MU-2122 | 112 | 112 | 19.1175 | 72.9383 | 19.1176 | 72.9381 | MCGM | S | Sanman A Wing | sanman,Opp. Maharashtra Kamgar Kalyan Mandal. | ATC | Fibmax | Co-build | De-Scope_Feasible | April'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004759 | 2025-03-25 | 2026-03-25 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76946 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-05-31 | 240 | MU | Mulund |  | 6169 | MU-6169 | 280 | 280 | 19.1767 | 72.9372 | 19.1782 | 72.9381 | MCGM | T | Mulund Gurudwara | MULUND GURUDWARA, HANUMAN PADA, MULUND WEST, MUMBAI, MAHARASHTRA 400082 | INDUS | Fibmax | Co-build | De-Scope_Feasible | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004745 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76947 | Received | PO Released | In-Process |  | 0 | -280 | - |  | Yes
Fibmax | 2026-05-31 | 241 | MU | Vikroli |  | MA4100 | MU-MA4100 | 280 | 280 | 19.1154 | 72.933 | 19.1147 | 72.9344 | MCGM | S | Maqsood House_Netsol | Lane NO-08B, Tagore Nagar, Vikhroli East, Mumbai, Maharashtra 400083 | Netsol | Fibmax | Co-build | De-Scope_Feasible | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004691 | 2025-03-24 | 2026-03-24 | 280 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76948 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
Fibmax | 2026-05-31 | 242 | MU | Vikroli |  | MA5495 | MU-MA5495 | 134.4 | 134.4 | 19.1194 | 72.9298 | 19.1192 | 72.9303 | MCGM | S | Jamaluddin House | 309, BUDDH VIHAR RD, SONA INTP COLONY, TAGORE NAGAR,VIKHROLI, MUMBAI, 400083 | Suyog | Fibmax | Co-build | De-Scope_Feasible | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004751 | 2025-03-25 | 2026-03-25 | 134 | Ok | -0.4 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76949 | Received | PO Released | - |  | 0 | -134 | -
Fibmax | 2026-04-30 | 243 | MU | Govandi |  | 5682 | MU-5682 | 224 | 224 | 19.0648 | 72.924 | 19.066 | 72.9239 | MCGM | M/E | IMRAN HOUSE NO-1 | Imran House No-1,Road No-5,Nr Anvar Jama Masjid,Shivaji Nagar,Govandi, Mumbai, Maharashtra 400043 | ATC | Fibmax | Co-build | De-Scope_Feasible | April'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004758 | 2025-03-25 | 2026-03-25 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76950 | Received | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-04-30 | 244 | MU | Govandi |  | 3901 | MU-3901 | 280 | 280 | 19.0628 | 72.9237 | 19.0612 | 72.9246 | MCGM | M/E | JAMATE BAITUL | Saibaba Nagar, Road No.6, Shivaji nagar, Ghatkopar Mankhurd Link Road | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004755 | 2025-03-25 | 2026-03-25 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76951 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-04-30 | 245 | MU | Ghatkoper |  | 2510 | MU-2510 | 134.4 | 134.4 | 19.0889 | 72.8979 | 19.0882 | 72.8983 | MCGM | N | MADHU MANSION | Madhu Chirag Nagar,Chirag Nagar,Gatkopar(W),Mumbai-400086 | INDUS | Fibmax | Co-build | De-Scope_Feasible | April'26 | Ranjit Wadkar | Yogesh Deshpande | Feasible | 10004694 | 2025-03-24 | 2026-03-24 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76952 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2026-05-31 | 246 | MU | Kurla |  | 3107 | MU-3107 | 291.2 | 291.2 | 19.0833 | 72.8891 | 19.0848 | 72.8888 | MCGM | L | BABA APARTMENT | A Wing, Navapada Lane, Kurla Kamani, Kurla West, Mumbai 400 070 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004724 | 2025-03-24 | 2026-03-24 | 291 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-76953 | RFAI Awaited | PO Released | - |  | 0 | -291 | - |  | Yes
Fibmax | 2026-05-31 | 247 | MU | Andheri |  | 744 | MU-744 | 112 | 112 | 19.1153 | 72.8809 | 19.1159 | 72.8812 | MCGM | K/E | SUMERPLZINI1 | Marol, Andheri East, Mumbai, Maharashtra | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004708 | 2025-03-24 | 2026-03-24 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-76954 | RFAI Awaited | PO Released | - |  | 0 | -112 | - |  | Yes
Fibmax | 2026-05-31 | 248 | MU | Kandivali |  | 1659 | MU-1659 | 224 | 224 | 19.2057 | 72.8773 | 19.2068 | 72.8772 | MCGM | R/S | Universal | UNIVERSAL THAKUR SHAYAM NARAYN MARG THAKUR VILLAJE,Kandivali East Mumbai | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004696 | 2025-03-24 | 2026-03-24 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76955 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-05-31 | 249 | MU | Andheri |  | 1365 | MU-1365 | 134.4 | 134.4 | 19.1046 | 72.8707 | 19.1056 | 72.8703 | MCGM | K/E | ROYALMERO | Hotel Le Meridian, Sahar Airport Road, Andheri (E) | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76956 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2026-05-31 | 250 | MU | Miraroad |  | MA184 | MU-MA184 | 291.2 | 291.2 | 19.2772 | 72.8645 | 19.2777 | 72.8643 | MBMC | - | Ashok nill chs | ASHOK NILL CHS , POONAM COMPLEX, MIRA ROAD, MIRA BHAYANDAR, MUMBAI, MAHARASHTRA 401107 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004698 | 2025-03-24 | 2026-03-24 | 291 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-76957 | RFAI Awaited | PO Released | In-Process |  | 259 | -32 | - |  | Yes
Fibmax | 2026-03-31 | 251 | MU | Miraroad |  | 596 | MU-596 | 134.4 | 134.4 | 19.2992 | 72.8605 | 19.2985 | 72.8612 | MBMC | - | Gandhi Udyan | Gandhi Udyan, SONAM SHAKTI,New Golden Nest,Phase 9, Bldg.9, Mira Bhayandar Road,Bhayandar(East), Dist.Thane - 401 105. | ATC | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004695 | 2025-03-24 | 2026-03-24 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76958 | Received | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2026-10-31 | 252 | MU | Borivali |  | 6154 | MU-6154 | 246.4 | 246.4 | 19.2236 | 72.86 | 19.2241 | 72.8583 | MCGM | R/C | Govind | Jaya Nagar Rd, Rajendra Nagar, Borivali East, Mumbai, Maharashtra 400066 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004760 | 2025-03-25 | 2026-03-25 | 246 | PO Pending |  | PO Released | - |  | Not created | CWIP-76959 | Received | PO Released | - |  | 0 | -246 | - |  | No
Fibmax | 2026-10-31 | 253 | MU | Borivali |  | 5980 | MU-5980 | 44.8 | 44.8 | 19.2405 | 72.8599 | 19.2403 | 72.8596 | MCGM | R/N | JETHETWROF | Jethe Tower,S V Road Ambavadi Dahisar E | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004762 | 2025-03-25 | 2026-03-25 | 45 | Ok | 0.2 | PO Released | - |  | Not created | CWIP-76960 | Received | PO Released | - |  | 0 | -45 | - |  | Yes
Fibmax | 2026-11-30 | 254 | MU | Dahisar |  | MB2495 | MU-MB2495 | 224 | 224 | 19.2454 | 72.8587 | 19.2468 | 72.8591 | MCGM | R/N | GURUKUL A WING CHS | Gurukul Wing-A CHS Ltd.- Jaiwant Sawant RoadGurukul Apartment, Leo Peter Wadi, Dahisar West, Mumbai, Maharashtra 400068,Post office:- Dahisar,Police station:- Dahisar | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Hari Yadav | Satish Singh | Feasible | 10004717 | 2025-03-24 | 2026-03-24 | 224 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785490 | CWIP-76961 | Received | PO Released | 124158 | Santosh Yadav | 172 | -52 | - |  | Yes
|  | 255 | MU | Borivali |  | 6015 | MU-6015 | 280 | 280 | 19.2294 | 72.8582 | 19.2277 | 72.858 | MCGM | R/C | UOMAYASHOF | Kasturba Cross Rd Number 7,Chinchpada, Borivali,Mumbai, Maharashtra 400066 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2027-02-28 | 256 | MU | Airoli |  | MA4977 | MU-MA4977 | 257.6 | 257.6 | 19.1635 | 72.9967 | 19.1632 | 72.9954 | NMMC | - | SAINI TOWER | Sector-02,Airoli Navi Mumbai | Suyog | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004747 | 2025-03-25 | 2026-03-25 | 258 | Ok | 0.4 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76962 | Received | PO Released | - |  | 0 | -258 | -
Fibmax | 2026-05-31 | 257 | MU | Wadala East |  | MB2505 | MU-MB2505 | 256.704 | 256.704 | 19.0143 | 72.8529 | 19.0152 | 72.8518 | MCGM | F/N | Wadala_BEST | Wadala Depot,Plot No:-02,Opposite Ambedkar College, GD Ambekar Marg, Sahkar Nagar, Wadala, Mumbai, Maharashtra 400031. Post Office:-Wadala, Police Station:-Wadala | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Sandeep randive | Prem Verma | Feasible | 10004750 | 2025-03-25 | 2026-03-25 | 257 | Ok | 0.296 | PO Released | - |  | Not created | CWIP-76963 | RFAI Awaited | PO Released | - |  | 0 | -257 | - |  | Yes
Fibmax | 2026-05-31 | 258 | MU | Dharavi |  | 6479 | MU-6479 | 190.4 | 190.4 | 19.0425 | 72.852 | 19.0416 | 72.8528 | MCGM | G/N | GOLDEN SUNRISE | Golden Sunrise,Dharavi Cross Rd,Nr 60 feet rd,Dharavi,Mum 17 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Sandeep randive | Prem Verma | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 190 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76964 | RFAI Awaited | PO Released | - |  | 0 | -190 | - |  | Yes
Fibmax | 2026-05-31 | 259 | MU | Santacruz |  | 2477 | MU-2477 | 134.4 | 134.4 | 19.0759 | 72.8518 | 19.0755 | 72.851 | MCGM | H/E | Shanti Nagar Coop India Ltd | OPP GRAND HYATT HOTEL,VAKOLA,SANTACRUZ,(E),MUMBAI | ATC | Fibmax | Co-build | De-Scope_Feasible | May'26 | Hari Yadav | Satish Singh | Feasible | 10004820 | 2025-03-26 | 2026-03-26 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76965 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2027-02-28 | 260 | MU | Miraroad |  | MA366 | MU-MA366 | 224 | 224 | 19.3037 | 72.8515 | 19.3042 | 72.8523 | MBMC | - | Pallavi CHSL | PALLAVI CHS , 60 FEET ROAD NR JAIN MANDIR BHYANDER EAST, MUMBAI, MAHARASHTRA. 401101 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004722 | 2025-03-24 | 2026-03-24 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76966 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2025-10-31 | 261 | MU | Miraroad |  | MA2282 | MU-MA2282 | 89.6 | 89.6 | 19.2995 | 72.8489 | 19.2999 | 72.8482 | MBMC | - | SALASAR CHS. | Near Nagar Bhawan X ing, Bhayander West, Mumbai | INDUS | Fibmax | Co-build | De-Scope_Feasible | Oct'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004823 | 2025-03-26 | 2026-03-26 | 90 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-76967 | RFAI Awaited | PO Released | - |  | 0 | -90 | - |  | Yes
|  | 262 | MU | Vile Parle |  | 5155 | MU-5155 | 145.6 | 145.6 | 19.1135 | 72.8486 | 19.113 | 72.8478 | MCGM | K/E | TIRUPATIONM1 | Tirupathi Balaji Chs,Sahar Road,Near Vijay Nagar Hall,Andheri (E),Mumbai-400053 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Hari Yadav | Satish Singh | Not feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 263 | MU | Bandra |  | 5898 | MU-5898 | 134.4 | 134.4 | 19.0667 | 72.8486 | 19.0657 | 72.8494 | MCGM | H/E | RAJASRI SAHU MAHARAJ VIDHRATHI VASTI GRUH | RAJASRI SAHU MAHARAJ VIDHRATHI VASTI GRUH,SARDA DEVI ROAD,BANDRA(E),MUMBAI | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Prem Verma | Prem Verma | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2027-02-28 | 264 | MU | Miraroad |  | 5627 | MU-5627 | 161.28 | 161.28 | 19.3031 | 72.8477 | 19.3018 | 72.8483 | MBMC | - | HUSSAINIONM1 | Teheri Hussaini,Teheri Hussaini,fakhri colony,bhayander-w | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004861 | 2025-03-26 | 2026-03-26 | 161 | Ok | -0.28 | PO Released | - |  | Not created | CWIP-76968 | Received | PO Released | - |  | 0 | -161 | - |  | Yes
Fibmax | 2026-11-30 | 265 | MU | Bandra |  | 3386 | MU-3386 | 280 | 280 | 19.0615 | 72.8389 | 19.0615 | 72.8374 | MCGM | H/W | GAIETYQQIUI1 | Gaity Galaxy, Bandra (W), Mumbai-400050 | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | May'25 | VIJAY NIKAM | Prem Verma | Feasible | 10004879 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_14256 | CWIP-76969 | RFAI Awaited | PO Released | 79718 | Santosh Yadav | 186 | -94 | - |  | Yes
Fibmax | 2026-05-31 | 266 | MU | Dadar |  | MB5491 | MU-MB5491 | 224 | 224 | 19.0202 | 72.8361 | 19.0217 | 72.8351 | MCGM | G/N | Saraswati Dham | Vijay Manjrekar Rd, Chandrakant Dhuru Wadi, Dadar, Mumbai, Maharashtra 400028 | ATC | Fibmax | Co-build | De-Scope_Feasible | May'26 | Swapnil Salvi | Prem Verma | Feasible | 10004797 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76970 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-11-30 | 267 | MU | Vile Parle |  | MA4076 | MU-MA4076 | 89.6 | 89.6 | 19.107 | 72.8359 | 19.1072 | 72.8367 | MCGM | K/W | Heena Smruti | HEENA SMRUTI, INDRAVADAN OZA RD,JVPD SCHEME, JUHU,MUMBAI,VILEPARLE (W) MAHARASHTRA 400056 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Hari Yadav | Satish Singh | Feasible | 10004814 | 2025-03-26 | 2026-03-26 | 90 | Ok | 0.4 | PO Released | Part of 99 |  | FF_NW2122_785491 | CWIP-76971 | RFAI Awaited | PO Released | - | Santosh Yadav | 96 | 6 | LA Considered |  | Yes
Fibmax | 2026-05-31 | 268 | MU | Colaba |  | 3604 | MU-3604 | 56 | 56 | 18.9219 | 72.8285 | 18.9219 | 72.8281 | MCGM | A | TAJWLIFTLMI1 | Taj Wellington, Nathalal Parikh Road, Colba Causeway, Churchgate, Mumbai | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | May'26 | Prem Verma | Prem Verma | Feasible | 10004707 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released | - |  | Not created | CWIP-76972 | RFAI Awaited | PO Released | - | Shrikant Chavan | 30 | -26 | - |  | Yes
Fibmax | 2026-11-30 | 269 | MU | Bandra |  | 5541 | MU-5541 | 235.2 | 235.2 | 19.0598 | 72.8261 | 19.0597 | 72.8245 | MCGM | H/W | Winnie Apatment CHSL | Winnie Apatment CHSL, Turner road opp D monte park bandra west -40050 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Prem Verma | Prem Verma | Feasible | 10004701 | 2025-03-24 | 2026-03-24 | 235 | Ok | -0.2 | PO Released | Part of 99 |  | FF_NW2122_785492 | CWIP-76973 | RFAI Awaited | PO Released | 919813 | Santosh Yadav | 230 | -5 | Pending |  | Yes
Fibmax | 2026-10-31 | 270 | MU | Thane |  | MA4416 | MU-MA4416 | 280 | 280 | 19.2654 | 72.9652 | 19.2664 | 72.9656 | TMC | - | TATA Business Support -BMC Park | TATA Business Support Near G corp Blg Kasarwadawadi Ghodbandar road,MBC Park,Cwing Thane W | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004792 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76974 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-10-31 | 271 | MU | Thane |  | 2628 | MU-2628 | 168 | 168 | 19.2019 | 72.9513 | 19.2006 | 72.9515 | TMC | - | Gajanan chaya | Gajanan Chaya,Sathe Nagar,Road No-34,Wagle Estate,Thane(W) | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004713 | 2025-03-24 | 2026-03-24 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76975 | Received | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-03-31 | 272 | MU | Govandi |  | MA2512 | MU-MA2512 | 56 | 56 | 19.0598 | 72.9163 | 19.0598 | 72.9164 | MCGM | M/E | Shrinath Gupta | NEW GAUTAM NAGAR, PLOT NO 1 SHIVAJI NAGAR, ROAD GOVANDI, MUMBAI, MAHARASHTRA.- 43 | ATC | Fibmax | Co-build | De-Scope_Feasible | March'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004727 | 2025-03-24 | 2026-03-24 | 56 | Ok | 0 | PO Released | - |  | Not created | CWIP-76976 | RFAI Awaited | PO Released | - |  | 0 | -56 | - |  | Yes
Fibmax | 2026-04-30 | 273 | MU | Chembur |  | 2958 | MU-2958 | 224 | 224 | 19.0587 | 72.9024 | 19.0586 | 72.9006 | MCGM | M/W | Mahesh Kutir | MAHESH KUTIR, 12th ROAD, NEAR DRAMBEDKAR GARDEN, CHEMBUR(E) | ATC | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004801 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785493 | CWIP-76977 | RFAI Awaited | PO Released | 712961 |  | 210 | -14 | Pending |  | Yes
Fibmax | 2026-04-30 | 274 | MU | Dahisar |  | MA4828 | MU-MA4828 | 230.72 | 230.72 | 19.2483 | 72.87 | 19.2494 | 72.8702 | MCGM | R/N | Marble Heights_Crack | Ambica Society, Ghartan Pada,Rawal Pada, Dahisar East, Mumbai, Maharashtra 400068 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004723 | 2025-03-24 | 2026-03-24 | 231 | Ok | 0.28 | PO Released | Part of 99 |  | FF_NW2122_785494 | CWIP-76978 | RFAI Awaited | PO Released | 356844 | Santosh Yadav | 198 | -33 | - |  | Yes
Fibmax | 2027-02-28 | 275 | MU | Miraroad |  | MA6274 | MU-MA6274 | 156.8 | 156.8 | 19.2994 | 72.8677 | 19.3005 | 72.8683 | MBMC | - | Sagar Garden Plaza | 7/8, GARDEN PLAZA, DEEPAK HOSPITAL RD, RAMDEV PARK, INDRALOK, BHAYANDAR EAST,THANE, 401105 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004712 | 2025-03-24 | 2026-03-24 | 157 | Ok | 0.2 | PO Released | - |  | Not created | CWIP-76979 | RFAI Awaited | PO Released | - |  | 0 | -157 | - |  | Yes
Fibmax | 2026-04-30 | 276 | MU | Mahim |  | MB1785 | MU-MB1785 | 162.848 | 162.848 | 19.0376 | 72.8429 | 19.0369 | 72.8417 | MCGM | G/N | Suraj Venture A-Wing | Suraj Ventures, Behind Paradise Cinema, Bhagoji Kheer Marg, Mahim (W, Geeta Nagar, Wanjawadi, New Dinkar Co Operative Housing Society, Mahim, Mumbai, Maharashtra 400016,post office:-Mahim,police:-Mahim | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Prem Verma | Prem Verma | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 163 | Ok | 0.152 | PO Released | Part of 99 |  | FF_NW2122_785495 | CWIP-76980 | RFAI Awaited | PO Released | - |  | 0 | -163 | - |  | Yes
Fibmax | 2026-05-31 | 277 | MU | Santacruz |  | 142 | MU-142 | 145.6 | 145.6 | 19.0795 | 72.8409 | 19.0806 | 72.8409 | MCGM | H/W | Landmark CHS | Landmark ,1st Hasina baugLane, Santacruz (w) | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Hari Yadav | Satish Singh | Feasible | 10004705 | 2025-03-24 | 2026-03-24 | 146 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-76981 | RFAI Awaited | PO Released | - |  | 0 | -146 | - |  | Yes
Fibmax | 2026-04-30 | 278 | MU | Andheri |  | MA3580 | MU-MA3580 | 190.4 | 190.4 | 19.1118 | 72.8369 | 19.1127 | 72.8371 | MCGM | K/W | Diwani Mahal | Diwani Mahal,Plot No. 6, Opp. Irla Masjid, Gulmohar Road No.1, JVPD Scheme, Vile Parle West, Mumbai 400057 | ATC | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Hari Yadav | Satish Singh | Feasible | 10004798 | 2025-03-26 | 2026-03-26 | 190 | Ok | -0.4 | PO Released | Part of 99 |  | FF_NW1920_15424 | CWIP-76982 | RFAI Awaited | PO Released | - | Santosh Yadav | 0 | -190 | - |  | Yes
Fibmax | 2026-04-30 | 279 | MU | Khadakpada |  | MA3442 | MU-MA3442 | 168 | 168 | 19.2567 | 73.1386 | 19.2568 | 73.139 | KDMC | - | Wayale Sports Club | WAYALE SPORTS CLUB, NR RAJARAM HALL, AMRUT NAGRI ROAD, KHADAKPADA, KALYAN,W, MUMBAI, MAHARASHTRA 421301 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004826 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | Part of 99 |  | FF_NW1920_15423 | CWIP-76983 | Received | PO Released | - |  | 0 | -168 | Pending |  | Yes
Fibmax | 2027-02-28 | 280 | MU | Dombivali |  | 5590 | MU-5590 | 224 | 224 | 19.2223 | 73.0867 | 19.2229 | 73.0867 | KDMC | - | MATHURABOF | Mahatma Phule Rd, Opp Hindustan Bank, Dombivali(W)-421202 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004800 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76984 | Received | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-03-31 | 281 | MU | Dombivali |  | MA5750 | MU-MA5750 | 168 | 168 | 19.23 | 73.0835 | 19.2305 | 73.0836 | KDMC | - | KANCHAN BUNGLOW OPEN PLOT | KANCHAN BUNGLOW OPEN PLOT, SAI DHAM COLONY,DEVI CHA WADA, MAHATMA FULE RD,GARIBACHAWADA ,DOMBIVLI W MUMBAI, MAHARASHTRA. | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76985 | Received | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-04-30 | 282 | MU | Kharghar |  | MA3897 | MU-MA3897 | 224 | 224 | 19.0543 | 73.0648 | 19.0528 | 73.065 | PMC | - | CIDCO - Opp Iskon Temple (Next Navjeevan Hospital) | Utsav Chowk - CISF Rd, Sector 23, Kharghar, Navi Mumbai, Maharashtra 410210 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785496 | CWIP-76986 | RFAI Awaited | PO Released | - |  | 0 | -224 | Pending |  | Yes
|  | 283 | MU | Thane |  | MA658 | MU-MA658 | 168 | 168 | 19.2021 | 72.9461 | 19.2016 | 72.9467 | TMC | - | Pawan Athwal House_Crack | PAWAN ATHWAL HOUSE, HANUMAN NAGAR, WAGLE INDUSTRIAL ESTATE, THANE WEST, THANE, MUMBAI, MAHARASHTRA 400604 | Purple Soil | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-05-31 | 284 | MU | Bhandup |  | 1924 | MU-1924 | 280 | 280 | 19.1487 | 72.9279 | 19.1472 | 72.9275 | MCGM | S | OSAIPRASO | Patil Compound, Gadav Naka, Tembhipada Road, Bhandup West, Mumbai-78 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10005005 | 2025-05-07 | 2026-05-07 | 280 | Old PO 10004859 Cancellled and new added on dated 7 May 25 | 0 | PO Released | - |  | Not created | CWIP-76987 | RFAI Awaited | PR in Process | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-05-31 | 285 | MU | Chembur |  | 1490 | MU-1490 | 280 | 280 | 19.044 | 72.9093 | 19.0454 | 72.9095 | MCGM | M/E | SPACEAGEO | Shivaji Chowk, Deonar Circle, Mumbai-400085 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76988 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
Fibmax | 2026-05-31 | 286 | MU | Saki Naka |  | 5687 | MU-5687 | 280 | 280 | 19.1013 | 72.8956 | 19.1 | 72.8962 | MCGM | L | ABDULKRMOF | New India Market, Wajid Ali Compound, Khairani Road, Sakinaka, Mumbai -400072 | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Swapnil Salvi | Yogesh Deshpande | Feasible | 10004793 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | - |  | Not created | CWIP-76989 | RFAI Awaited | PO Released | - |  | 0 | -280 | - |  | Yes
|  | 287 | MU | Kandivali |  | 2367 | MU-2367 | 179.2 | 179.2 | 19.2025 | 72.8535 | 19.2016 | 72.8531 | MCGM | R/S | Kandiwali East skywalk | Apna Nagar, Kandivali East,Kandiwali East Skywalk | Suyog | Fibmax | Co-build | De-Scope_Feasible | May'26 | Sabhajeet Maurya | Satish Singh | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-10-31 | 288 | MU | Borivali |  | MB3106 | MU-MB3106 | 190.4 | 190.4 | 19.2351 | 72.8518 | 19.2352 | 72.8533 | MCGM | R/C | Girnar Apt | Building No-22,Girnar Apartments, Gymkhana Road, Himmat Nagar, Borivali West, Mumbai, Maharashtra 400091,Post office :-Borivali,Police station:-Borivali | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Sabhajeet Maurya | Satish Singh | Feasible | 10004689 | 2025-03-24 | 2026-03-24 | 190 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76990 | RFAI Awaited | PO Released | - |  | 0 | -190 | - |  | Yes
|  | 289 | MU | Kandivali |  | 4131 | MU-4131 | 224 | 224 | 19.2506 | 72.8504 | 19.2496 | 72.8497 | MCGM | R/N | GAURAVQ | Gaurav CHS -C, Municipal Empoees Gaurav CHSL, Holy Cross Road, IC Colony, Borivali (W),Mumbai | INDUS | Fibmax | Co-build | De-Scope_Feasible | May'26 | Sabhajeet Maurya | Satish Singh | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 290 | MU | Miraroad |  | MA1939 | MU-MA1939 | 134.4 | 134.4 | 19.3041 | 72.8475 | 19.3047 | 72.8479 | MBMC | - | Mahavir Nagar | FAKHRI COLONY, SHASHIKANTH NAGAR, BHAYANDAR WEST,THANE, STATE-MAHARASHTRA, PINCODE- 401101 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Sabhajeet Maurya | Satish Singh | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-05-31 | 291 | MU | Pali Hill |  | 400 | MU-400 | 156.8 | 156.8 | 19.0647 | 72.8305 | 19.0643 | 72.8297 | MCGM | H/W | West Wind CHSL | Palli Village,16th Rd, Pali Village, Khar West, Mumbai, Maharashtra 400050 | ATC | Fibmax | Co-build | De-Scope_Feasible | May'26 | Prem Verma | Satish Singh | Feasible | 10004795 | 2025-03-26 | 2026-03-26 | 157 | Ok | 0.2 | PO Released | - |  | Not created | CWIP-76991 | RFAI Awaited | PO Released | - |  | 0 | -157 | - |  | Yes
Fibmax | 2026-10-31 | 292 | MU | Nariman Point |  | 3398 | MU-3398 | 134.4 | 134.4 | 18.9264 | 72.823 | 18.9258 | 72.8228 | MCGM | A | CROSSRD2IFI1 | Behind Mantralay, Churchgate | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Oct'26 | Prem Verma | Prem Verma | Feasible | 10004862 | 2025-03-26 | 2026-03-26 | 134 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-76992 | RFAI Awaited | PO Released | - |  | 0 | -134 | - |  | Yes
Fibmax | 2026-04-30 | 293 | MU | Bandra |  | 6006 | MU-6006 | 145.6 | 145.6 | 19.0593 | 72.8427 | 19.0584 | 72.843 | MCGM | H/E | TRIMURTIO | Trimurti,BULDING NO.27 PLOT NO 27 ROAD NO.8 KHER NAGAR KHERWADI BANDRA WEST MUMBAI | INDUS | Fibmax | Co-build | De-Scope_Feasible | Dec'25 | Prem Verma | Prem Verma | Feasible | 10005004 | 2025-05-07 | 2026-05-07 | 150 | Old PO 10004860 Cancellled and new added on dated 7 May 25 | 4.4 | PO Released | Part of 99 |  | FF_NW2122_785497 | CWIP-76993 | RFAI Awaited | PR in Process | - |  | 0 | -150 | - |  | Yes
Fibmax | 2026-03-31 | 294 | MU | Vitthalwadi |  | MB3226 | MU-MB3226 | 168 | 168 | 19.2217 | 73.146 | 19.2228 | 73.1459 | KDMC | - | Vaishnavi Park CHS A-6 | VAISHNAVI PARK CHSA-6,A3/301 VAISHNAVI PARK, SHANKAR PAWSHE RD, SAI BABA NAGAR, KATEMANIVALI, KALYAN EAST, KALYAN, MAHARASHTRA ,POST OFFICE :-KALYAN,POLICE STATION :-KALYAN | INDUS | Fibmax | Co-build | De-Scope_Feasible | March'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004875 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76994 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
Fibmax | 2026-04-30 | 295 | MU | Panvel |  | MA4786 | MU-MA4786 | 291.2 | 291.2 | 18.9951 | 73.1083 | 18.9944 | 73.1071 | PMC | - | Sneh Building | Sneh Building, Swami Nityanand Marg, Near Sahasrabuddhe Hospital, HOC Colony, Old Panvel, Navi Mumbai, Maharashtra- 410206 PANVEL | INDUS | Fibmax | Co-build | De-Scope_Feasible | Feb'26 | Abdul Quadir | Praveen Nigam | Feasible | 10004720 | 2025-03-24 | 2026-03-24 | 291 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-76995 | RFAI Awaited | PO Released | - |  | 0 | -291 | - |  | Yes
Fibmax | 2027-02-28 | 296 | MU | Dombivali |  | MA4011 | MU-MA4011 | 224 | 224 | 19.2169 | 73.0865 | 19.2159 | 73.0868 | KDMC | - | DOMBIVALI POLICE STATION (Ram Nagar) | Ram Nagar police station,Near Dombivali Station,Dombivali E | INDUS | Fibmax | Co-build | De-Scope_Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004828 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76996 | Received | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-04-30 | 297 | MU | Belapur |  | MA3567 | MU-MA3567 | 280 | 280 | 19.0223 | 73.0323 | 19.0213 | 73.0332 | NMMC | - | MAYOR BUNGLOW | Sector 30, CBD Belapur, Navi Mumbai, Maharashtra | ATC | Fibmax | Co-build | De-Scope_Feasible | May'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 280 | Ok | 0 | PO Released | Part of 99 |  | FF_NW2122_785498 | CWIP-76997 | RFAI Awaited | PO Released | - |  | 0 | -280 | Pending |  | Yes
Fibmax | 2026-10-31 | 298 | MU | Vartak Nagar |  | MA2370 | MU-MA2370 | 224 | 224 | 19.2103 | 72.9648 | 19.2097 | 72.9646 | TMC | - | Raymond-Thane(w) | Raymond- Solitaire, IT And ISS Bldg,,Vartak Nagar,Pokhran Road No-2,Thane(w) | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004872 | 2025-03-26 | 2026-03-26 | 224 | Ok | 0 | PO Released | - |  | Not created | CWIP-76998 | RFAI Awaited | PO Released | - |  | 0 | -224 | - |  | Yes
Fibmax | 2026-10-31 | 299 | MU | Thane |  | 4198 | MU-4198 | 168 | 168 | 19.1994 | 72.9458 | 19.2 | 72.9459 | TMC | - | ABSCUST | Abacus Textiles,A-3,Road No 27,Thane(Wagle)Industrial Estate,Thane-west | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | Feasible | 10004806 | 2025-03-26 | 2026-03-26 | 168 | Ok | 0 | PO Released | - |  | Not created | CWIP-76999 | RFAI Awaited | PO Released | - |  | 0 | -168 | - |  | Yes
|  | 300 | MU | Govandi |  | MA6546 | MU-MA6546 | 280 | 280 | 19.0598 | 72.9273 | 19.0609 | 72.9284 | MCGM | M/E | Irfan House | Govandi West, Shivaji Nagar Mumbai, Maharashtra 400043 | Suyog | Fibmax | Co-build | De-Scope_Feasible | Oct'26 | Swapnil Salvi | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 301 | MU | Govandi |  | MA2096 | MU-MA2096 | 112 | 112 | 19.0606 | 72.917 | 19.0608 | 72.9165 | MCGM | M/E | City Hospital | CITY HOSPITAL, NEW GOWTHAM NAGAR, GOVANDI, MUMBAI, MAHARASHTRA 400043 | Suyog | Fibmax | Co-build | De-Scope_Feasible | Oct'26 | Swapnil Salvi | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
|  | 302 | MU | Chandivali |  | MA3601 | MU-MA3601 | 280 | 280 | 19.1094 | 72.8937 | 19.1111 | 72.8933 | MCGM | L | Soheb Shaikh House | Plot No. 23 Yadav Nagar, Chandivali, Powai, Mumbai, Maharashtra 400072 | Suyog | Fibmax | Co-build | De-Scope_Feasible | Oct'26 | Swapnil Salvi | Yogesh Deshpande | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-10-31 | 303 | MU | Kurla |  | MB3457 | MU-MB3457 | 78.4 | 78.4 | 19.0798 | 72.8878 | 19.0808 | 72.8885 | MCGM | L | Premier Exotica 1-E-Wing | PREMIER EXOTICA 1-E-WING,NETAJI NAGAR, KURLA WEST, KURLA, MUMBAI, MAHARASHTRA . POST OFFICE:-KURLA, POLICE STATION:-KURLA | INDUS | Fibmax | Co-build | De-Scope_Feasible | Oct'26 | Manoj Ligade | Yogesh Deshpande | Feasible | 10004812 | 2025-03-26 | 2026-03-26 | 78 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-77000 | RFAI Awaited | PO Released | - |  | 0 | -78 | - |  | Yes
Fibmax | 2026-11-30 | 304 | MU | Kandivali |  | 379 | MU-379 | 190.4 | 190.4 | 19.2014 | 72.8707 | 19.2006 | 72.872 | MCGM | R/S | MAHINDRA & MAHINDRA (AADHAR BUILDING) | MAHINDRA & MAHINDRA AADHAR BUILDING OPP LOKHANDWALA COMPOUND KANDIVALI (E) Mumbai, Maharashtra 400101 | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004813 | 2025-03-26 | 2026-03-26 | 190 | Ok | -0.4 | PO Released | - |  | Not created | CWIP-77001 | RFAI Awaited | PO Released | - |  | 0 | -190 | - |  | Yes
Fibmax | 2026-04-30 | 305 | MU | Miraroad |  | MB2981 | MU-MB2981 | 257.6 | 257.6 | 19.2801 | 72.8676 | 19.2801 | 72.8673 | MBMC | - | OM PALACE CHS | SHREE OM PALACE O-50, HAPPY HOME COMPLEX, Shanti Park, Mira Road, Mira Bhayandar, Maharashtra 401107Post office:-Mira Bhayandar,Police station:-Mira Bhayandar | INDUS | Fibmax | Co-build | De-Scope_Feasible | Feb'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004845 | 2025-03-26 | 2026-03-26 | 258 | Ok | 0.4 | PO Released | - |  | Not created | CWIP-77002 | Received | PO Released | - |  | 0 | -258 | - |  | Yes
Fibmax | 2026-04-30 | 306 | MU | Miraroad |  | 721 | MU-721 | 112 | 112 | 19.3072 | 72.8617 | 19.3071 | 72.8628 | MBMC | - | Navoday Kiran CHS | Navghar Rd, Salasar Nagar, Navghar Naka, Bhayandar East, Mira Bhayandar, Maharashtra 401105 MIRA-BHAYENDER | INDUS | Fibmax | Co-build | De-Scope_Feasible | Feb'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004799 | 2025-03-26 | 2026-03-26 | 112 | Ok | 0 | PO Released | - |  | Not created | CWIP-77003 | RFAI Awaited | PO Released | In-Process |  | 112 | 0 | - |  | Yes
Fibmax | 2026-11-30 | 307 | MU | Vile Parle |  | MA4210 | MU-MA4210 | 11.2 | 11.2 | 19.0858 | 72.855 | 19.0846 | 72.855 | MCGM | H/E | Mishra House | E-13, Pipeline Rd, P and T Colony, Sector 1, Santacruz East, Mumbai, Maharashtra 400047 | Netsol | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Hari Yadav | Satish Singh | Feasible | 10004881 | 2025-03-26 | 2026-03-26 | 11 | Ok | -0.2 | PO Released-Hold by Airtel | - |  | Not created | CWIP-77004 | RFAI Awaited | PO Released | - |  | 0 | -11 | -
Fibmax | 2026-11-30 | 308 | MU | Vile Parle |  | 3411 | MU-3411 | 16.8 | 16.8 | 19.0967 | 72.8537 | 19.0963 | 72.8538 | MCGM | K/E | BAWAINQQINI1 | BAWA HOTEL, Plot No, T1, Near, 2087, Nehru Rd,,WESTERN EXPRESS HIGHWAY,VILE PARLE W | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Hari Yadav | Satish Singh | Feasible | 10004831 | 2025-03-26 | 2026-03-26 | 17 | Ok | 0.2 | PO Released | - |  | Not created | CWIP-77005 | RFAI Awaited | PO Released | - |  | 0 | -17 | - |  | Yes
|  | 309 | MU | Khar |  | MA701 | MU-MA701 | 168 | 168 | 19.0673 | 72.8445 | 19.0664 | 72.8433 | MCGM | H/E | Vaishali Borade House | VAISHALI BORADE HOUSE, TOPIWALA CHAWL, PIPE LINE, JAWAHAR NAGAR, KHAR EAST, MUMBAI, MAHARASHTRA 400051 | Rakshit | Fibmax | Co-build | De-Scope_Feasible | Nov'25 | Hari Yadav | Satish Singh | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
|  | 310 | MU | Lower Parel |  | 111 | MU-111 | 25.088 | 25.088 | 18.9903 | 72.8384 | 18.9903 | 72.8385 | MCGM | F/S | NARYANUDGMCRGF3G | Chiwda Galli , Lalbaug, 400012 | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Narayan Parab | Prem Verma | Not feasible | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | Yes
Fibmax | 2026-11-30 | 311 | MU | Gorai |  | MA4632 | MU-MA4632 | 291.2 | 291.2 | 19.2247 | 72.8303 | 19.2261 | 72.8301 | MCGM | R/C | TEJAS BUNGLOW | GORAI, BORIVALI, Mumbai | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Sabhajeet Maurya | Satish Singh | Feasible | 10004704 | 2025-03-24 | 2026-03-24 | 291 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-77006 | RFAI Awaited | PO Released | - |  | 0 | -291 | - |  | Yes
Fibmax | 2026-11-30 | 312 | MU | Santacruz |  | 5237 | MU-5237 | 11.2 | 11.2 | 19.0802 | 72.8298 | 19.0801 | 72.8297 | MCGM | H/W | GURUKRIPOMM1 | S B Patil Road, Gazdhar Bandh, Santacruz, Mumbai 400054 | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004840 | 2025-03-26 | 2026-03-26 | 11 | Ok | -0.2 | PO Released | - |  | Not created | CWIP-77007 | RFAI Awaited | PO Released | - |  | 0 | -11 | - |  | Yes
Fibmax | 2026-11-30 | 313 | MU | Mumbai Central |  | MA960 | MU-MA960 | 234.9312 | 234.9312 | 18.9671 | 72.8265 | 18.9672 | 72.8279 | MCGM | E | Alexandra Building | Building No.44/46, Manaji Rauji Road, 14th Ln, Kamathipura, Mumbai, Maharashtra 400008 | Purple Soil | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Vaijesh Patil | Prem Verma | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 235 | Ok | 0.0688 | PO Released-Hold by Airtel | - |  | Not created | CWIP-77008 | RFAI Awaited | PO Released | - |  | 0 | -235 | -
Fibmax | 2026-11-30 | 314 | MU | Churchgate |  | 3071 | MU-3071 | 156.8 | 156.8 | 18.9339 | 72.8249 | 18.9336 | 72.8239 | MCGM | A | AMBSSDRQIMI1 | Bharti Veer Nariman Road, Marine Line, Churchgate, Mumbai 400020 | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Prem Verma | Prem Verma | Feasible | 10004848 | 2025-03-26 | 2026-03-26 | 157 | Ok | 0.2 | PO Released | - |  | Not created | CWIP-77009 | RFAI Awaited | PO Released | - |  | 122 | -35 | - |  | Yes
|  | 315 | MU | Marine Line |  | 2996 | MU-2996 | 62.72 | 62.72 | 18.9373 | 72.8248 | 18.937 | 72.8246 | MCGM | A | Krishna Mahal | 63, Netaji Subhash Chandra Bose Rd Churchgate Mumbai, Maharashtra | INDUS | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Vaijesh Patil | Prem Verma | Feasible | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
Fibmax | 2026-04-30 | 316 | MU | Nariman Point |  | 2010 | MU-2010 | 250.88 | 250.88 | 18.9271 | 72.8204 | 18.9268 | 72.821 | MCGM | A | OBROIQQQIFI1 | Oberoi, R N Goneka Marg, Churchgate, Mumbai | Airtel Own | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Narayan Parab | Prem Verma | Feasible | 10004779 | 2025-03-26 | 2026-03-26 | 251 | Ok | 0.12 | PO Released | Part of 99 |  | FF_NW1920_14167 | CWIP-77010 | RFAI Awaited | PO Released | - |  | 0 | -251 | - |  | Yes
Fibmax | 2026-04-30 | 317 | MU | Malad |  | 341 | MU-341 | 121 | 0 | 19.1825 | 72.8164 | 19.1823 | 72.8173 | MCGM | P/N | Safee House | Safee House, 08/858, Gayakwad Nagarg,Gate No-8 , Malwani Malad E , Near AC- DC Masjid, | Suyog | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Virendra | Satish Singh | Feasible | 10004721 | 2025-03-24 | 2026-03-24 | 121 | PO length is greater than Feasibility Length | 121 | PO Released-Hold by Airtel | Part of 99 |  | Not created | CWIP-77011 | Received | PO Released | - |  | 122 | 1 | Pending
Fibmax | 2026-11-30 | 318 | MU | Santacruz |  | MA1794 | MU-MA1794 | 187 | 0 | 19.0779 | 72.8291 | 19.079 | 72.8292 | MCGM | H/W | Patel House | GAZDAR BANDH NORTH AVENUE SANTACRUZ WEST, INDRAJIT SOCIETY, VITHALDAS NAGAR, SANTACRUZ WEST, MUMBAI, MAHARASHTRA 400054 | ATC | Fibmax | Co-build | De-Scope_Feasible | Nov'26 | Dudhnath Tiwari | Satish Singh | Feasible | 10004824 | 2025-03-26 | 2026-03-26 | 187 | Ok | 187 | PO Released | - |  | Not created | CWIP-77012 | RFAI Awaited | PO Released | - |  | 0 | -187 | - |  | Yes
|  | 319 | MU | Juinagar |  | MB36 | MU-MB36 | 2000 | 0 | 19.0507 | 73.0142 | #N/A | #N/A | NMMC | - | Shree Samarth | Near Yogi's Kitchen,Sitabia Hira Naik Marg, Jui Gaon, Sector 23, Juinagar, Navi Mumbai, Maharashtra 400705 | INDUS | Fibmax | Co-build | Not Feasible | Dec'25 | Abdul Quadir | #N/A | #N/A | - | - | - | 0 | PO Pending |  | Not Feasible by BG | - |  | Not created | - | - | Not Feasible by BG | - |  | 0 | 0 | - |  | No
Fibmax | 2025-12-31 | 320 | MU | Navi Mumbai |  | 3273 | MU-3273 | 480 | 0 | 19.0882 | 73.0015 | #N/A | #N/A | NMMC | - | Kusum Apt | Kusum,sec 11,near icici bank,vashi | ATC | Fibmax | Co-build | Newly Add | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 480 | Ok | 480 | PO Released | - |  | Not created | CWIP-77013 | Received | PO Released | - |  | 0 | -480 | - |  | No
Fibmax | 2025-12-31 | 321 | MU | Navi Mumbai |  | 3144 | MU-3144 | 460 | 0 | 19.0251 | 73.047 | #N/A | #N/A | NMMC | - | Gurudwara | Plot No 16/A, Sector-8/B, CBD Belapur, Navi Mumbai - 400 614 | INDUS | Fibmax | Co-build | Newly Add | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 460 | Ok | 460 | PO Released | - |  | Not created | CWIP-77014 | RFAI Awaited | PO Released | - |  | 0 | -460 | - |  | Yes
Fibmax | 2025-12-31 | 322 | MU | Navi Mumbai |  | 1797 | MU-1797 | 460 | 0 | 19.0277 | 73.0231 | #N/A | #N/A | NMMC | - | Suyog CHSl | SUYOG CHS, Kamladevi Birajdar Marg, Sector 19A, Nerul, Navi Mumbai, Maharashtra | INDUS | Fibmax | Co-build | Newly Add | Dec'25 | Abdul Quadir | Praveen Nigam | Feasible | 10004888 | 2025-03-26 | 2026-03-26 | 460 | Ok | 460 | PO Released | - |  | Not created | CWIP-5697 | RFAI Awaited | PO Released | - |  | 0 | -460 | - |  | Yes
| 2026-02-28 | 323 | MU | Airoli | MA5656 | MA5656 | MU-MA5656 | 605 | 605 | 19.1522 | 72.9998 | MUM_Route_68 | MA5656_LM | NMMC | - | Hardik Veera Apt | Sector 4, Airoli, Navi Mumbai, Maharashtra | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 20 | PO length is less than Feasibility length | -585 | PO Released | - |  | Not created | CWIP-76752 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-10-31 | 324 | MU | Chembur | 4474 | 4474 | MU-4474 | 275 | 275 | 19.0544 | 72.8933 | MUM_Route_19 | 4474_LM | MCGM | M/W | New Vijay Cinema | Opposite Akbar Ali, Near MTNL Exchange, Chembur Naka-400071 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 80 | PO length is less than Feasibility length | -195 | PO Released | - |  | Not created | CWIP-76404 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2025-12-31 | 325 | MU | Churchgate | 6369 | 6369 | MU-6369 | 11 | 11 | 18.9305 | 72.8255 | MUM_Route_99 | 6369_LM | MCGM | A | Ravindra Mansion | Junction Of J Tata Road, Oppsite Rasa Pub, Churchgate, Mumbai-400021 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 40 | PO length is greater than Feasibility Length | 29 | PO Released | - |  | Not created | CWIP-76669 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-02-28 | 326 | MU | Majiwada | 3354 | 3354 | MU-3354 | 110 | 110 | 19.2209 | 72.9773 | MUM_Route_42 | 3354_LM | TMC | - | CINEWONDO | Kapurbawdi ,Ghodbunder Road | Airtel Own | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76710 | RFAI Awaited | PO Modification WIP | - |  | 0 | -110 | -
| 2026-02-28 | 327 | MU | Vitawa | #N/A | MA1751 | MU-MA1751 | 275 | 275 | 19.1836 | 72.9947 | MUM_Route_42 | MA1751_LM | TMC | - | Madhosh Bar | INDAL COLONY, VITAWA, KALWA ,THANE, STATE-MAHARASHTRA, PINCODE- 400605 | Purple Soil | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 180 | PO length is less than Feasibility length | -95 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76711 | RFAI Awaited | PO Released | - |  | 0 | -180 | -
| 2026-02-28 | 328 | MU | Digha | #N/A | MA3495 | MU-MA3495 | 110 | 110 | 19.1779 | 72.9964 | MUM_Route_42 | MA3495_LM | TMC | - | Sadanand_Lodge_Crack | KALWA, MUKUND NAGAR, DIGHE, NAVI MUMBAI, DISTRICT-THANE, STATE- MAHARASHTRA, PINCODE- 400708 | Purple Soil | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 110 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76712 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-02-28 | 329 | MU | Thane | 2587 | 2587 | MU-2587 | 275 | 275 | 19.1977 | 72.9818 | MUM_Route_42 | 2587_LM | TMC | - | KALWA -Police Station | THANE RAILWAY Stn TO JAMBHALI NAKA, COURT NAKA, HEAD QUARTER, KALWA POLICE Stn,Maharashtra | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 120 | PO length is less than Feasibility length | -155 | PO Released | - |  | Not created | CWIP-76713 | Received | PO Released | - |  | 0 | -120 | -
| 2026-02-28 | 330 | MU | Thane | MA5212 | MA5212 | MU-MA5212 | 275 | 275 | 19.1994 | 72.978 | MUM_Route_42 | MA5212_LM | TMC | - | Shreeyog CHSL_Crack | CIVIL-K VILLA RD,THANE WEST, 400601 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76714 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-02-28 | 331 | MU | Thane | 4378 | 4378 | MU-4378 | 110 | 110 | 19.2065 | 72.9775 | MUM_Route_42 | 4378_LM | TMC | - | NAVBHARTOF | Azad Nagar, LBS Road, Thane West | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 60 | PO length is less than Feasibility length | -50 | PO Released | - |  | Not created | CWIP-76715 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-02-28 | 332 | MU | Thane | MA4138 | MA4138 | MU-MA4138 | 110 | 110 | 19.2115 | 72.977 | MUM_Route_42 | MA4138_LM | TMC | - | Alij Chambers (Alt of Cosmos Tower) | GOKUL NAGAR, THANE WEST, THANE, MUMBAI, MAHARASHTRA 400601 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Not created | CWIP-76716 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-02-28 | 333 | MU | kalwa | 5357 | 5357 | MU-5357 | 495 | 495 | 19.1936 | 72.9883 | MUM_Route_42 | 5357_LM | TMC | - | ALSAFAQ | OPP MUNICIPAL SCHOOL, BEHIND KATHERIN VILLA, OLD THANE-BELAPUR ROAD, KALWA. | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 360 | PO length is less than Feasibility length | -135 | PO Released | - |  | Not created | CWIP-76717 | RFAI Awaited | PO Released | - |  | 0 | -360 | -
| 2026-02-28 | 334 | MU | kalwa | MA2152 | MA2152 | MU-MA2152 | 110 | 110 | 19.1919 | 72.9881 | MUM_Route_42 | MA2152_LM | TMC | - | Sharshwati Apt | SHARSHWATI APT, THANE - BELAPUR RD,KALWA WEST, BUDHAJI NAGAR, KALWA, MUMBAI, MAHARASHTRA 400605 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76718 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-02-28 | 335 | MU | Vitawa | MA1036 | MA1036 | MU-MA1036 | 275 | 275 | 19.1876 | 72.9882 | MUM_Route_42 | MA1036_LM | TMC | - | Siddhivinayak CHS | Near Vithal Mandir, Vitava - Koliwada, Thane west 400605 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76719 | Received | PO Released | - |  | 0 | -280 | -
| 2026-02-28 | 336 | MU | Vitawa | #N/A | MB6417 | MU-MB6417 | 220 | 220 | 19.1848 | 72.9914 | MUM_Route_42 | MB6417_LM | TMC | - | RISHI PARK CHS | RISHI PARK CHS, NEAR SWAMI DARSHAN SUPER MARKET, SHOP NO-01, JAYANTI APR., SAHAJI DAMAR VITWKARMARG, KALWA,VITAWA, THANE, POST OFFICE-KALWA, POLICE STATION-KALW | Netsol | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 220 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76720 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-02-28 | 337 | MU | Digha | 6094 | 6094 | MU-6094 | 165 | 165 | 19.1799 | 72.9952 | MUM_Route_42 | 6094_LM | TMC | - | KATCOGBTO | Airoli, Thane Belapur Road, Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004961 | 2025-04-08 | 2026-04-08 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76721 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-01-31 | 338 | MU | Mulund |  | MB4464 | MU-MB4464 | 55 | 55 | 19.1519 | 72.9741 | MUM_Route_80 | MB4464_LM | MSRDC | - | Airoli Bridge | AIROLI BRIDGE,MULUND - AIROLI RD, MULUND EAST, MUMBAI, MAHARASHTRA | OSR | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-01-31 | 339 | MU | Mulund |  | MB2248 | MU-MB2248 | 55 | 55 | 19.1507 | 72.9803 | MUM_Route_80 | MB2248_LM | MSRDC | - | Airoli Bridge | Airoli - Mulund Bridge,Pole No:-AMSP-31,Sector 14,Mulund-Airoli Rd,Airoli, Navi Mumbai, Maharashtra 400708 | OSR | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-01-31 | 340 | MU | Mulund |  | MB4458 | MU-MB4458 | 77 | 77 | 19.1539 | 72.9648 | MUM_Route_80 | MB4458_LM | MSRDC | - | Airoli Toll Naka | AIROLI TOLL NAKA,5X37+HRH, MULUND EAST, MUMBAI, MAHARASHTRA | OSR | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-01-31 | 341 | MU | Vashi | MA5118 | MA5118 | MU-MA5118 | 55 | 55 | 19.1487 | 72.9912 | MUM_Route_80 | MA5118_LM | NMMC | - | Airoli Sector 16, Kunal CHS | Kunal Apartment, Service Rd, Panchatara Co Housing Society, Diva Gaothan, Sector 9, Airoli, Navi Mumbai, Maharashtra 400708 | ATC | Route LM | Co-Build | Feasible | Nov'25 | Abdul Quadir | #N/A | - | 10004627 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76655 | Received | PO Released | - |  | 0 | -60 | -
| 2026-02-28 | 342 | MU | Rabale | MA4147 | MA4147 | MU-MA4147 | 385 | 385 | 19.1498 | 72.9999 | MUM_Route_68 | MA4147 | NMMC | - | Sant Savata Bhavan | Sant Savata Mali Mandal Sector 5, Airoli, Navi Mumbai, MH 400708 | INDUS | Route LM | Co-Build | Feasible | Nov'25 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 50 | PO length is less than Feasibility length | -335 | PO Released | - |  | Not created | CWIP-76753 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2027-02-28 | 343 | MU | Mumbra | MA2824 | MA2824 | MU-MA2824 | 220 | 220 | 19.1642 | 73.0288 | MUM_Route_45 | MA2824_LM | TMC | - | Shimla Park CHSL_Indus | KAUSA, MUMBRA, THANE, STATE-MAHARASHTRA PINCODE-400612 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -70 | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2027-02-28 | 344 | MU | Mumbra | MA1907 | MA1907 | MU-MA1907 | 110 | 110 | 19.1803 | 73.0223 | MUM_Route_45 | MA1907_LM | TMC | - | Mateen APT | REHNUMA COMPLEX CO-OP HSG SOC LTD,SANJAY NAGAR,MUMBRA,THANE-400612 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 20 | PO length is less than Feasibility length | -90 | PO Released | - |  | Not created | #N/A | Received | PO Released | - |  | 0 | -20 | -
| 2027-02-28 | 345 | MU | MUMBRA | 1677 | 1677 | MU-1677 | 220 | 220 | 19.1749 | 73.0232 | MUM_Route_45 | 1677_LM | TMC | - | KAUSARMAO | Mumbai - Pune RdAmrut Nagar, Kausa, MumbraThane, Maharashtra | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 220 | Ok | 0 | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2027-02-28 | 346 | MU | Mumbra | MB1711 | MB1711 | MU-MB1711 | 275 | 275 | 19.1603 | 73.0304 | MUM_Route_45 | MB1711_LM | TMC | - | Al Ghadeer Palace CHSL | Al Ghadeer Palace,Building No:-01,Mumbai-Pune Rd, Rashid Compound, Kausa, Mumbra, Thane, Maharashtra 400612. Police Station:-Mumbra, Post Office:-Mumbra. | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -125 | PO Released | - |  | Not created | #N/A | Received | PO Released | - |  | 0 | -150 | -
| 2027-02-28 | 347 | MU | Mumbra | 496 | 496 | MU-496 | 110 | 110 | 19.1674 | 73.0259 | MUM_Route_45 | 496_LM | TMC | - | FARID CHS | FARID CHS MUMBRA | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Not created | #N/A | Received | PO Released | - |  | 0 | -50 | -
| 2027-02-28 | 348 | MU | Mahape | 3817 | 3817 | MU-3817 | 220 | 220 | 19.108 | 73.0282 | MUM_Route_45 | 3817_LM | NMMC | - | Unique House | EL120, Unique House, TTC Industrial Area, Electronic Zone, MIDC Industrial Area, Mahape, Navi Mumbai, Maharashtra 400701 | INDUS | Route LM | Co-Build | Feasible | April'25 | Abdul Quadir | #N/A | - | 10004670 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -70 | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2027-02-28 | 349 | MU | Shilphata | 2213 | 2213 | MU-2213 | 352 | 352 | 19.1648 | 73.0305 | MUM_Route_45 | 2213_LM | TMC | - | SAYOG PARK | Sahyog park,Talao pali road,kausa mumbra | INDUS | Route LM | Co-Build | Feasible |  | Ranjit Wadkar | #N/A | - | 10004670 | 2025-03-24 | 2026-03-24 | 350 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -350 | -
| 2027-02-28 | 350 | MU | Mumbra | #N/A | MA638 | MU-MA638 | 275 | 0 | 19.144 | 73.0396 | MUM_Route_45 | MA638_LM | TMC | - | Madhavi Plot | THAKUR PADA, SHIL PHATA - MAHAPE RD, SHILPHATA, NAVI MUMBAI, MAHARASHTRA 421204 | Suyog | Route LM | Co-Build | De-scope |  | Jayhind Yadav | Yogesh Deshpande | - | 10004670 | 2025-03-24 | 2026-03-24 | 200 | PO length is greater than Feasibility Length | 200 | PO Released-Hold by Airtel | - |  | Not created | - | RFAI Awaited | PO Released | - |  | 0 | -200 | -
| 2027-02-28 | 351 | MU | Mahape | MB2815 | MB2815 | MU-MB2815 | 110 | 110 | 19.1089 | 73.0256 | MUM_Route_45 | MB2815_LM | NMMC | - | CTRL Data center-DC4 | PLOT NO- 229/1A,TCC MIDC MAHAPE,NAV MUMBAI -400701 | Airtel Own | Route LM | Co-Build | Feasible | April'25 | Abdul Quadir | #N/A | - | 10004670 | 2025-03-24 | 2026-03-24 | 180 | PO length is greater than Feasibility Length | 70 | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -180 | -
| 2026-12-31 | 352 | MU | Pawne | MB5991 | MB5991 | MU-MB5991 | 200 | 200 | 19.0894 | 73.0207 | MUM_Route_81 | MB5991_LM | NMMC | - | Sutar House | pawane gaon, Navi Mumbai, Maharashtra 400705 | INDUS | Route LM | Co-Build | Not Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 200 | Ok | 0 | PO Released | - |  | Not created | CWIP-76761 | RFAI Awaited | PO Released | - |  | 0 | -200 | -
| 2026-12-31 | 353 | MU | Koparkhairane |  | 4139 | MU-4139 | 55 | 55 | 19.0952 | 73.0126 | MUM_Route_81 | 4139_LM | NMMC | - | SAIDARSHOF | Sai Dar Shan, Bonkade Road, Koperkhairance,New Mumbai-400709 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-12-31 | 354 | MU | Koparkhairane | MB2459 | MB2459 | MU-MB2459 | 220 | 220 | 19.1098 | 73.0019 | MUM_Route_81 | MB2459_LM | NMMC | - | Shivneri CHSL | Plot No101,Shivneri Chambers Limited, Kopar Khairane Ghansoli Station Rd, Sector 2A, Kopar Khairane, Navi Mumbai, Maharashtra 400709. Post Office:-Kopar Khairane, Police Station:-Kopar Khairane, Thane | ATC | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -70 | PO Released | - |  | Not created | CWIP-76762 | Received | PO Released | - |  | 0 | -150 | -
| 2026-12-31 | 355 | MU | Koparkhairane | MB3220 | MB3220 | MU-MB3220 | 110 | 110 | 19.1106 | 73.0043 | MUM_Route_81 | MB3220_LM | NMMC | - | City Enclave | CITY ENCLAVE,CITY ENCLAVE 1, PLOT NO 9, SECTOR 2, KOPAR KHAIRANE, NAVI MUMBAI,POST OFFICE:- KOPAR KHAIRANE,POLICE STATION:- KOPAR KHAIRANE | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76763 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-12-31 | 356 | MU | Pawne | MA2619 | MA2619 | MU-MA2619 | 165 | 165 | 19.0891 | 73.0235 | MUM_Route_81 | MA2619_LM | NMMC | - | Supreme Cold Fresh Storage | C 23, Pawneshwar Marg, MIDC Industrial Area, Pawne, Navi Mumbai, 400705 | INDUS | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76764 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-12-31 | 357 | MU | Pawne | MB1795 | MB1795 | MU-MB1795 | 165 | 165 | 19.0864 | 73.0239 | MUM_Route_81 | MB1795_LM | NMMC | - | Supreme Cold Storage | Supreme Cold Storage,Pawneshwar Marg, T.T.C. Industrial Area, Midc Industrial Area, Pawne, Navi Mumbai, Maharashtra 400705 | ATC | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76765 | Received | PO Released | - |  | 0 | -170 | -
| 2026-12-31 | 358 | MU | Ghansoli | 4973 | 4973 | MU-4973 | 297 | 297 | 19.1309 | 72.9949 | MUM_Route_81 | 4973_LM | NMMC | - | NPATILHSOF | N Patil House,Talvali Gaon,, Ghansoli | INDUS | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 380 | PO length is greater than Feasibility Length | 83 | PO Released | - |  | Not created | CWIP-76766 | RFAI Awaited | PO Released | - |  | 0 | -380 | -
| 2026-12-31 | 359 | MU | Ghansoli | #N/A | 6224 | MU-6224 | 275 | 275 | 19.1324 | 72.9983 | MUM_Route_81 | 6224_LM | NMMC | - | Hotel yash | Hotel Yash, Hotel Yash,Rabale | Suyog | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -125 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76767 | Received | PO Released | - |  | 0 | -150 | - |  |  | Site under Relocation
| 2026-12-31 | 360 | MU | Koparkhairane | 2342 | 2342 | MU-2342 | 110 | 110 | 19.0982 | 73.0128 | MUM_Route_81 | 2342_LM | NMMC | - | T.K. Appartment | T.K. APARTMENT , sec. 12-D, ram nagar, koperkhairane. | INDUS | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76768 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-12-31 | 361 | MU | Ghansoli |  | MA4523 | MU-MA4523 | 220 | 220 | 19.1326 | 73.0024 | MUM_Route_81 | MA4523_LM | NMMC | - | Rathod Chawl | 180, Talvali Rd Shanti Nagar, Sector 21, Ghansoli Gaon, Ghansoli Navi Mumbai, Maharashtra 400701 | UNITY | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-12-31 | 362 | MU | Ghansoli | #N/A | MB1266 | MU-MB1266 | 198 | 198 | 19.1254 | 72.9913 | MUM_Route_81 | MB1266_LM | NMMC | - | Atmaram Apt | BHARTI AIRTEL LTD., C/O., KAKA SAHEB KHALDE SANKUL,SHOP NO 5 /4B, MARUTI MANDIR CHOWK,NEAR ICICI BANK, TALEGOAN DABHADE | Excel Telesonic (Bombay Gas) | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -48 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76769 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-12-31 | 363 | MU | Koparkhairane | MB2903 | MB2903 | MU-MB2903 | 220 | 220 | 19.0927 | 73.0135 | MUM_Route_81 | MB2903_LM | NMMC | - | Sai Leela Apt | Sai Leela Apartment,Sector 11, Kopar Khairane, Navi Mumbai, Maharashtra 400709,post office:-Kopar Khairane,police station:-Kopar Khairane | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 190 | PO length is less than Feasibility length | -30 | PO Released | - |  | Not created | CWIP-76770 | RFAI Awaited | PO Released | - |  | 0 | -190 | -
| 2026-12-31 | 364 | MU | Ghansoli | MB3271 | MB3271 | MU-MB3271 | 165 | 165 | 19.1125 | 73.0014 | MUM_Route_81 | MB3271_LM | NMMC | - | Narayan Nagpur House | NARAYAN NAGPUR HOUSE,SECTOR-1, PLOT NO-20, NAVI MUMBAI, MAHARASHTRA | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 100 | PO length is less than Feasibility length | -65 | PO Released | - |  | Not created | CWIP-76771 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-12-31 | 365 | MU | Ghansoli | 2253 | 2253 | MU-2253 | 55 | 55 | 19.1386 | 73.0015 | MUM_Route_81 | 2253_LM | NMMC | - | Chandrabhaga Apt | Chandrabhaga Apt,B.K Marg Rabale | ATC | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76772 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-12-31 | 366 | MU | Ghansoli | 1392 | 1392 | MU-1392 | 275 | 275 | 19.1286 | 72.9959 | MUM_Route_81 | 1392_LM | NMMC | - | Bhawna Kunj | Bhavna Kunj, Sector 21, Talavali, Ghansoli Gaon, Chatrapati Shivaji Marg, Navi Mumbai, Maharashtra- 400701 NAVI MUMBAI | ATC | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 180 | PO length is less than Feasibility length | -95 | PO Released | - |  | Not created | CWIP-76773 | Received | PO Released | - |  | 0 | -180 | -
| 2026-03-31 | 367 | MU | Kalyan |  | 2910 | MU-2910 | 71.5 | 71.5 | 19.2299 | 73.123 | Mumbai_Coverage_Route9 | 2910_LM | KDMC | - | Metro Junction Mall (Outdoor) | SAHIL ROAD,NEXT TO PATRIPUL BRIDGE,BEFORE BABA SAHEB AMBEDKAR CHOWK,KALYAN (E | Airtel Own | Route LM | Co-Build | Feasible | Feb'26 | Ranjit Wadkar | #N/A | - | - | - | - | 0 | PO Pending |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 368 | MU | Kalyan | 4794 | 4794 | MU-4794 | 220 | 220 | 19.2272 | 73.1069 | Mumbai_Coverage_Route9 | 4794_LM | KDMC | - | MUNDE NIWAS | MUNDE NIWAS, Khambalpada,Thakurli(E) | ATC | Route LM | Co-Build | Feasible | Feb'26 | Ranjit Wadkar | #N/A | - | 10004537 | 2025-03-13 | 2026-03-13 | 220 | Ok | 0 | PO Released | - |  | Not created | CWIP-76560 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-03-31 | 369 | MU | Thakurli | 4553 | 4553 | MU-4553 | 55 | 55 | 19.2268 | 73.1018 | Mumbai_Coverage_Route9 | 4553_LM | KDMC | - | MAHALAXMO | Masoba Nagar,Nr Thakurli Station,Thakurli(W)-421201 | INDUS | Route LM | Co-Build | Feasible | April'26 | Jayhind Yadav | Yogesh Deshpande | - | 10004537 | 2025-03-13 | 2026-03-13 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76561 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-03-31 | 370 | MU | Thakurli | MB3309 | MB3309 | MU-MB3309 | 143 | 143 | 19.2253 | 73.098 | Mumbai_Coverage_Route9 | MB3309_LM | KDMC | - | Sai Guru Kripa Building | plot no 58, Thakurli Station Rd, Thakurli, Railway Colony, Dombivli, Maharashtra 421201 | INDUS | Route LM | Co-Build | Feasible | April'26 | Abdul Quadir | #N/A | - | 10004537 | 2025-03-13 | 2026-03-13 | 140 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76562 | RFAI Awaited | PO Released | - |  | 0 | -140 | -
| 2026-03-31 | 371 | MU | Kalyan | MB2965 | MB2965 | MU-MB2965 | 121 | 121 | 19.2297 | 73.113 | Mumbai_Coverage_Route9 | MB2965_LM | KDMC | - | Kashish Galaxy J wing Chsl | Kashish Galaxy J wing Chsl BLOCK-H, AMBER PRIT, Kachore Gaon, Kalyan, Maharashtra 421301,Post office:Kalyan,Police station:-Kalyan | ATC | Route LM | Co-Build | Feasible | Jan'26 | Ranjit Wadkar | #N/A | - | 10004537 | 2025-03-13 | 2026-03-13 | 120 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76563 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2025-06-30 | 372 | MU | Kalyan | MB1259 | MB1259 | MU-MB1259 | 33 | 33 | 19.2176 | 73.1408 | Mumbai_Coverage_Route7 | MB1259_LM | KDMC | - | Saket Harmony | 7, Mhatre Naka Rd, Neelkanthnagar, Chinchpada Gaon, Kalyan, Maharashtra 421306 | ATC | Route LM | Co-Build | Feasible | Jan'26 | Ranjit Wadkar | #N/A | - | 10004531 | 2025-05-21 | 2026-05-21 | 30 | Old PO-10004521,revised PO received on 21-05-2025 | -3 | PO Released | - |  | FF_NW2122_73579 | CWIP-76554 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2025-06-30 | 373 | MU | Kalyan | MA2218 | MA2218 | MU-MA2218 | 22 | 22 | 19.2209 | 73.1398 | Mumbai_Coverage_Route7 | MA2218_LM | KDMC | - | GAJANAN KRUPA APT | Chinch Pada Road, Kalyan East 421306 | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Ranjit Wadkar | #N/A | - | 10004531 | 2025-05-21 | 2026-05-21 | 20 | Old PO-10004521,revised PO received on 21-05-2025 | -2 | PO Released | - |  | FF_NW2122_785421 | CWIP-76555 | Received | PO Released | - |  | 20 | 0 | -
| 2025-06-30 | 374 | MU | Kalyan | MB1589 | MB1589 | MU-MB1589 | 88 | 88 | 19.219 | 73.1396 | Mumbai_Coverage_Route7 | MB1589_LM | KDMC | - | Nana Mhatre Open Plot | Chinchpada, Besides Sumangal Hospital, Near Matre Naka, Chinchpada Road, Kalyan, | ATC | Route LM | Co-Build | Feasible | Jan'26 | Ranjit Wadkar | #N/A | - | 10004531 | 2025-05-21 | 2026-05-21 | 90 | Old PO-10004521,revised PO received on 21-05-2025 | 2 | PO Released | - |  | FF_NW2122_785422 | CWIP-76556 | RFAI Awaited | PO Released | - |  | 75 | -15 | -
| 2025-06-30 | 375 | MU | Khadakpada | MA5147 | MA5147 | MU-MA5147 | 143 | 143 | 19.218 | 73.1327 | Mumbai_Coverage_Route7 | MA5147_LM | KDMC | - | Sai Leela Building | SAI LEELA BUILDING, 201, KRISHNA PARADISE A-8, CITY-KALYAN EAST, DISTRICT-THANE, STATE-MAHARASHTRA, PINCODE- 421306 | ATC | Route LM | Co-Build | Feasible | May'25 | Vaijesh Patil | Prem Verma | - | 10004531 | 2025-05-21 | 2026-05-21 | 140 | Old PO-10004521,revised PO received on 21-05-2025 | -3 | PO Released | - |  | FF_NW2122_785423 | CWIP-76557 | Received | PO Released | - |  | 0 | -140 | -
| 2025-06-30 | 376 | MU | Kalyan | MA5051 | MA5051 | MU-MA5051 | 22 | 22 | 19.2229 | 73.1401 | Mumbai_Coverage_Route7 | MA5051_LM | KDMC | - | Shree Ram Tulsi CHSL(Relocation of 4878_Pawan) | SHRI RAM TULSI HANUMAN NAGAR KALYAN EAST,THANE-421202,MUMBAI | ATC | Route LM | Co-Build | Feasible | Feb'26 | Ranjit Wadkar | #N/A | - | 10004531 | 2025-05-21 | 2026-05-21 | 20 | Old PO-10004521,revised PO received on 21-05-2025 | -2 | PO Released | - |  | FF_NW1920_25749 | CWIP-76558 | Received | PO Released | - |  | 0 | -20 | -
| 2026-12-31 | 377 | MU | Antop Hill |  | MA1934 | MU-MA1934 | 150 | 150 | 19.0196 | 72.8705 | Mumbai_Coverage_Route6 | MA1934_LM | MCGM | F/N | Gurav House Wadala | GANESH NAGAR SP ROAD WADALA MUMBAI MAHARASHTRA 37 | Rakshit | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-12-31 | 378 | MU | Antop Hill | 5995 | 5995 | MU-5995 | 99 | 99 | 19.0177 | 72.8684 | Mumbai_Coverage_Route6 | 5995_LM | MCGM | F/N | TAKDRNWSOF | Takdir Niwas,Wadala,Salt Pane Road,Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004550 | 2025-03-17 | 2026-03-17 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76550 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-12-31 | 379 | MU | Antop Hill | #N/A | MA3984 | MU-MA3984 | 22 | 22 | 19.0163 | 72.8663 | Mumbai_Coverage_Route6 | MA3984_LM | MCGM | F/N | Omkar jaiswal house | Omkar Jaiswal house,Jaiswal Communication House, Shop No. 45, Ambikawadi, Station Road, Opp Premji Haridasji Oil Mill, Korba Mithagar, Wadala (East), Mumbai 400 037 | Suyog | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004550 | 2025-03-17 | 2026-03-17 | 30 | Ok | 8 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76551 | Received | PO Released | - |  | 0 | -30 | -
| 2026-12-31 | 380 | MU | Antop Hill | 6180 | 6180 | MU-6180 | 66 | 66 | 19.0212 | 72.8728 | Mumbai_Coverage_Route6 | 6180_LM | MCGM | F/N | HARIOMMDOF | Shop No 9, Shanti Naga, S P Road, Wadala East, Mumbai-400037 | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004550 | 2025-03-17 | 2026-03-17 | 70 | Ok | 4 | PO Released | - |  | Not created | CWIP-76552 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-05-31 | 381 | MU | Parel | 4919 | 4919 | MU-4919 | 33 | 33 | 19.0106 | 72.8446 | Mumbai_Coverage_Route5 | 4919_LM | MCGM | F/S | KALSISDNOF | Kalsi Sadan,Jyotiba Phule Road,Naigaon,Mumbai-14 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004514 | 2025-03-13 | 2026-03-13 | 120 | PO length is greater than Feasibility Length | 87 | PO Released | - |  | Not created | CWIP-76119 | RFAI Awaited | PO Released | - |  | 0 | -120 | - |  |  | Site under Relocation
| 2026-05-31 | 382 | MU | Parel | 5181 | 5181 | MU-5181 | 33 | 33 | 19.0077 | 72.8449 | Mumbai_Coverage_Route5 | 5181_LM | MCGM | F/S | APNABZARONM1 | Apna Bazar Co-op,Govindji Kani Road,Naigaon,Mumbai 400014 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004514 | 2025-03-13 | 2026-03-13 | 50 | PO length is greater than Feasibility Length | 17 | PO Released | - |  | Not created | CWIP-76120 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-05-31 | 383 | MU | Parel | 3511 | 3511 | MU-3511 | 33 | 33 | 19.0058 | 72.8453 | Mumbai_Coverage_Route5 | 3511_LM | MCGM | F/S | Deep Residency | Jerbai Wadia Rd Bhoiwada, Parel Mumbai, Maharashtra 400014 | INDUS | Route LM | Co-Build | Not Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004514 | 2025-03-13 | 2026-03-13 | 30 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76121 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-12-31 | 384 | MU | Antop Hill | 5392 | 5392 | MU-5392 | 99 | 99 | 19.0276 | 72.8734 | Mumbai_Coverage_Route4 | 5392_LM | MCGM | F/N | KHANABDLOF | Khan Abdul Riyaz,Bhartiya Kamla Nagar,SM Road,Behind Budh Vihar,RN NoCEN 32/191,Wadala,Antopholl,Mumbai- 400037 | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004546 | 2025-03-17 | 2026-03-17 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76548 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-03-31 | 385 | MU | Matunga | MA4005 | MA4005 | MU-MA4005 | 195.328 | 195.328 | 19.0284 | 72.8597 | Mumbai_Coverage_Route38 | MA4005_LM | MCGM | F/N | Seva Mandal Education Society (B M shah college) | 338,R. A . KIDWAI ROAD, KINGS CIRCLE ,MATUNGA, MUMBAI- 19 | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004967 | 2025-04-15 | 2026-04-15 | 150 | PO length is less than Feasibility length | -45.328 | PO Released | - |  | Not created | CWIP-76539 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-03-31 | 386 | MU | Sion | MB1727 | MB1727 | MU-MB1727 | 26.4 | 26.4 | 19.0209 | 72.8589 | Mumbai_Coverage_Route38 | MB1727_LM | MCGM | F/N | S.I.W.S. college | Plot No:-337,N R Swamy College Of Commerce And Economics, Major R Parameswaran Rd, Wadla Village, Wadala, Mumbai, Maharashtra 400031. Post Office:-Wadala , Police Station:-Wadala | INDUS | Route LM | Co-Build | Feasible |  | Manoj Ligade | Yogesh Deshpande | - | 10004967 | 2025-04-15 | 2026-04-15 | 40 | PO length is greater than Feasibility Length | 13.6 | PO Released | - |  | Not created | CWIP-76540 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-03-31 | 387 | MU | Antop Hill | 6062 | 6062 | MU-6062 | 100 | 0 | 19.0257 | 72.8606 | Mumbai_Coverage_Route38 | 6062_LM | MCGM | F/N | SUMANGALO | Su Mangal chs,NR.AMULAKHA SCHOOL,KIDWAI ROAD,MATUNGA(W),Mumbai. | INDUS | Route LM | Co-Build | Data mismatch |  | Swapnil Salvi | Yogesh Deshpande | - | 10004967 | 2025-04-15 | 2026-04-15 | 80 | PO length is greater than Feasibility Length | 80 | PO Released | - |  | Not created | CWIP-76541 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2026-04-30 | 388 | MU | Sion | 4436 | 4436 | MU-4436 | 52.8 | 52.8 | 19.0306 | 72.8527 | Mumbai_Coverage_Route37 | 4436_LM | MCGM | F/N | Shree Krishna niwas | Shree Krishna Niwas, 550, Vacharaj Lane, Behind Ram Baug Lane, Matunga Central Railway,Mumbai- 400019 | INDUS | Route LM | Co-Build | Feasible |  | Manoj Ligade | Yogesh Deshpande | - | 10004574 | 2025-03-18 | 2026-03-18 | 60 | Ok | 7.2 | PO Released | - |  | Not created | CWIP-76535 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-04-30 | 389 | MU | Matunga | MA1265 | MA1265 | MU-MA1265 | 280.5 | 280.5 | 19.0287 | 72.8521 | Mumbai_Coverage_Route37 | MA1265_LM | MCGM | F/N | Shree Gyaneshwar Math Trust | Near railway satation matunga east . | ATC | Route LM | Co-Build | Feasible |  | Narayan Parab | #N/A | - | 10004574 | 2025-03-18 | 2026-03-18 | 40 | PO length is less than Feasibility length | -240.5 | PO Released | - |  | Not created | CWIP-76536 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-04-30 | 390 | MU | Matunga | #N/A | MA4376 | MU-MA4376 | 27.5 | 27.5 | 19.027 | 72.8527 | Mumbai_Coverage_Route37 | MA4376_LM | MCGM | F/N | BEST SITE Matunga | Kings Circle, Matunga, Mumbai, Maharashtra | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004574 | 2025-03-18 | 2026-03-18 | 100 | PO length is greater than Feasibility Length | 72.5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76537 | Received | PO Released | - |  | 0 | -100 | -
| 2026-02-28 | 391 | MU | Kandivali | MB1626 | MB1626 | MU-MB1626 | 33 | 33 | 19.2087 | 72.8481 | Mumbai_Coverage_Route36 | MB1626_LM | MCGM | R/S | Heritage Parody | Near Swami Vivekananda International School - Parekh Nagar- S. V. Road- Kandivali 400101 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004568 | 2025-03-18 | 2026-03-18 | 30 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76533 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-10-31 | 392 | MU | Borivali | 5741 | 5741 | MU-5741 | 99 | 99 | 19.2333 | 72.847 | Mumbai_Coverage_Route35 | 5741_LM | MCGM | R/C | ARMABLQQONM1 | Aroma, Koliwada Marg, Borivali (W), Mumbai-400091 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004583 | 2025-03-18 | 2026-03-18 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76527 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-10-31 | 393 | MU | Borivali | 6407 | 6407 | MU-6407 | 22 | 22 | 19.2299 | 72.8465 | Mumbai_Coverage_Route35 | 6407_LM | MCGM | R/C | Kent Residency | Chanrawarkar Rd, Ashok Nagar, Borivali West, Mumbai, Maharashtra | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004583 | 2025-03-18 | 2026-03-18 | 50 | PO length is greater than Feasibility Length | 28 | PO Released | - |  | Not created | CWIP-76528 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-10-31 | 394 | MU | Borivali | 1191 | 1191 | MU-1191 | 33 | 33 | 19.2354 | 72.8463 | Mumbai_Coverage_Route35 | 1191_LM | MCGM | R/C | ZGARDENQOF | Zed garden,C.T.S no 353 /1 ,EKSAR Rd, Off Eksar Rd , Yogi nagar , Borivali(w) , Mumbai-92 | ATC | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004583 | 2025-03-18 | 2026-03-18 | 60 | PO length is greater than Feasibility Length | 27 | PO Released | - |  | Not created | CWIP-76529 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-10-31 | 395 | MU | Borivali | 5761 | 5761 | MU-5761 | 88 | 88 | 19.2391 | 72.8499 | Mumbai_Coverage_Route35 | 5761_LM | MCGM | R/N | Shasi Apt | Shashi Apt, Devidas Lane, Borivali (W) Mum | ATC | Route LM | Co-Build | Not Feasible |  | Virendra | #N/A | - | 10004583 | 2025-03-18 | 2026-03-18 | 120 | PO length is greater than Feasibility Length | 32 | PO Released | - |  | Not created | CWIP-76530 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2026-10-31 | 396 | MU | Borivali | 1956 | 1956 | MU-1956 | 308 | 308 | 19.2421 | 72.8546 | Mumbai_Coverage_Route35 | 1956_LM | MCGM | R/N | HARSHIAPO | Near Bhagwati hospital, Borivali East, Mumbai-400103 | INDUS | Route LM | Co-Build | Not Feasible |  | Virendra | #N/A | - | 10004583 | 2025-03-18 | 2026-03-18 | 310 | Ok | 2 | PO Released | - |  | Not created | CWIP-76531 | RFAI Awaited | PO Released | - |  | 0 | -310 | -
| 2025-12-31 | 397 | MU | Bhayander East | MB4276 | MB4276 | MU-MB4276 | 11 | 11 | 19.316 | 72.8571 | Mumbai_Coverage_Route34 | MB4276_LM | MBMC | - | Jesal Manor | Bhayandar, Jesal Park, Bhayandar East, Mira Bhayandar, Maharashtra 401105 | INDUS | Route LM | Co-Build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | - | 10004968 | 2025-04-15 | 2026-04-15 | 100 | PO length is greater than Feasibility Length | 89 | PO Released | - |  | Not created | CWIP-76116 | Received | PO Released | - |  | 0 | -100 | -
| 2025-12-31 | 398 | MU | #N/A | MA2979 | MA2979 | MU-MA2979 | 601 | 601 | 19.3169 | 72.8548 | Mumbai_Coverage_Route34 | MA2979_LM | MBMC | - | SAI SHAKTI | Nr. Kapoor TowerJesal ParkBhayander EastDist. Thane | INDUS | Route LM | Co-Build | more than 500 mtr | March'26 | Sabhajeet Maurya | Satish Singh | - | 10004968 | 2025-04-15 | 2026-04-15 | 70 | PO length is less than Feasibility length | -531 | PO Released | - |  | Not created | CWIP-76117 | Received | PO Released | - |  | 0 | -70 | -
| 2026-02-28 | 399 | MU | Taloja | MA2463 | MA2463 | MU-MA2463 | 100 | 100 | 19.0783 | 73.109 | Mumbai_Coverage_Route33 | MA2463_LM | PMC | - | Shree Apartment | Shree Apartment, Ghotkamp Koyana Velhe, Taloja, Panvel, Navi Mumbai, Maharashtra- 410208 DOMBIVALI | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004572 | 2025-03-18 | 2026-03-18 | 100 | Ok | 0 | PO Released | - |  | Not created | CWIP-76523 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-02-28 | 400 | MU | Taloja | MA2028 | MA2028 | MU-MA2028 | 55 | 55 | 19.0837 | 73.112 | Mumbai_Coverage_Route33 | MA2028_LM | PMC | - | Patil Gala-GBM_Crack | GBT-PATIL GALA, GHOT RD, GHOTKAMP, TALOJA, NEW MUMBAI MAHARASHTRA | ATC | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004572 | 2025-03-18 | 2026-03-18 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76524 | Received | PO Released | - |  | 0 | -60 | -
| 2026-02-28 | 401 | MU | Taloja | MA2559 | MA2559 | MU-MA2559 | 132 | 132 | 19.0805 | 73.1095 | Mumbai_Coverage_Route33 | MA2559_LM | PMC | - | Gopinath seth niwas open plot | KOYANA VELHE,TALOJA ,RAIGAD, 410208 | ATC | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004572 | 2025-03-18 | 2026-03-18 | 100 | PO length is less than Feasibility length | -32 | PO Released | - |  | Not created | CWIP-76525 | Received | PO Released | - |  | 0 | -100 | -
| 2026-03-31 | 402 | MU | Dombivali | 686 | 686 | MU-686 | 22 | 22 | 19.2252 | 73.0759 | Mumbai_Coverage_Route32 | 686_LM | KDMC | - | Kalu Sadan | Reti Bunder Road,Motagaon Reti Bunder,Dombivali-421202 | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Subhodh | Praveen Nigam | - | 10004555 | 2025-03-17 | 2026-03-17 | 20 | PO Pending |  | PO Released | - |  | Not created | CWIP-76517 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-03-31 | 403 | MH | Kalyan | MB2153 | MB2153 | MU-MB2153 | 110 | 110 | 19.2185 | 73.0847 | Mumbai_Coverage_Route32 | MB2153_LM | KDMC | - | Sai Savli | Old Dombivli Rd, Shastri Nagar, Dombivli West, Maharashtra 421202 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Ranjit Wadkar | #N/A | - | 10004555 | 2025-03-17 | 2026-03-17 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76519 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-02-28 | 404 | MU | Dombivali | MA954 | MA954 | MU-MA954 | 220 | 220 | 19.2129 | 73.0985 | Mumbai_Coverage_Route31 | MA954_LM | KDMC | - | Savodaya Laxmi | Sarvoday Laxmi(Sagarli gaon), Samarth Vihar NX, Sagarli Gaon, Dombivli East, Dombivli, Maharashtra 421203 DOMBIVALI | ATC | Route LM | Co-Build | Feasible | March'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 100 | PO length is less than Feasibility length | -120 | PO Released | - |  | Not created | CWIP-76511 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-02-28 | 405 | MU | Dombivali | MB1581 | MB1581 | MU-MB1581 | 110 | 110 | 19.2061 | 73.0978 | Mumbai_Coverage_Route31 | MB1581_LM | KDMC | - | Harsachi Solution Pvt Ltd | Harsachi Solution Pvt. Ltd,Plot No:-W-250(A),Sudama Nagar,Near Police Quarter,MIDC Phase-2,Dombivli East,Dombivli,Maharashtra:-421201. Post Office:-Dombivli, Police Station:-Dombivli | INDUS | Route LM | Co-Build | Feasible | March'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 40 | PO length is less than Feasibility length | -70 | PO Released | - |  | Not created | CWIP-76512 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-02-28 | 406 | MU | Dombivali | 2452 | 2452 | MU-2452 | 5.5 | 5.5 | 19.2092 | 73.0969 | Mumbai_Coverage_Route31 | 2452_LM | KDMC | - | VIGNHAR CHSL | Ayodhya Nagari, Dombivali East-421201 | INDUS | Route LM | Co-Build | Feasible | March'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 30 | PO length is greater than Feasibility Length | 24.5 | PO Released | - |  | Not created | CWIP-76513 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-02-28 | 407 | MU | Dombivali | 4991 | 4991 | MU-4991 | 165 | 165 | 19.2131 | 73.0969 | Mumbai_Coverage_Route31 | 4991_LM | KDMC | - | Vinod Bhavan | VINOD BHAVAN , NEAR SAMARTH NURSING HOME, GOGRAS WADI, DOMBIVALI (E) Maharashtra 421201 | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 50 | PO length is less than Feasibility length | -115 | PO Released | - |  | Not created | CWIP-76514 | Received | PO Released | - |  | 0 | -50 | -
| 2026-02-28 | 408 | MU | Dombivali | #N/A | MA1400 | MU-MA1400 | 66 | 66 | 19.2122 | 73.0947 | Mumbai_Coverage_Route31 | MA1400_LM | KDMC | - | Chathurthi Arcade_Crack | NAMDEV CROSS PATH,ROCKEL DEPOT GALLI, OPP. KDMC GARDEN, GOGRASWADI, DOMBIVLI EAST, MUMBAI, MAHARASHTRA. 421201 | Netsol | Route LM | Co-Build | Feasible | Feb'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 180 | PO length is greater than Feasibility Length | 114 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76515 | RFAI Awaited | PO Released | - |  | 0 | -180 | -
| 2026-02-28 | 409 | MU | Dombivali | MA285 | MA285 | MU-MA285 | 55 | 55 | 19.2106 | 73.0961 | Mumbai_Coverage_Route31 | MA285_LM | KDMC | - | Sangam Niwas_Crack | Mr. S. Disuja- (9819104443), Sangan Niwas, Jijai Nagar Street, Ambika Nagar, Gograswadi, Ayodhya nagari, Dombivali East, Maharashtra- 421201 DOMBIVALI | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Sandeep randive | Yogesh Deshpande | - | 10004580 | 2025-03-18 | 2026-03-18 | 70 | PO length is greater than Feasibility Length | 15 | PO Released | - |  | Not created | CWIP-76516 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-11-30 | 410 | MU | Kandivali | MA138 | MA138 | MU-MA138 | 11 | 11 | 19.198 | 72.8436 | Mumbai_Coverage_Route30 | MA138_LM | MCGM | R/S | Rajani Gandha | Shankar Lane Balasinor Society, Kandivali West Mumbai, Maharashtra 400067 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004573 | 2025-03-18 | 2026-03-18 | 30 | PO length is greater than Feasibility Length | 19 | PO Released | - |  | Not created | CWIP-76507 | Received | PO Released | - |  | 0 | -30 | -
| 2026-11-30 | 411 | MU | Kandivali | 6179 | 6179 | MU-6179 | 5.5 | 5.5 | 19.1952 | 72.8437 | Mumbai_Coverage_Route30 | 6179_LM | MCGM | P/N | Shardha Apart | Sharda Apt,GORASWADI PARK ROAD,SV ROAD,KAILASH NAGAR,MALAD (W). | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004573 | 2025-03-18 | 2026-03-18 | 30 | PO length is greater than Feasibility Length | 24.5 | PO Released | - |  | Not created | CWIP-76508 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-11-30 | 412 | MU | Kandivali | 1041 | 1041 | MU-1041 | 159.5 | 159.5 | 19.1984 | 72.8458 | Mumbai_Coverage_Route30 | 1041_LM | MCGM | R/S | MANEKAP | 69, Shankar Lane, Kandivli (W) | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004573 | 2025-03-18 | 2026-03-18 | 160 | Ok | 0.5 | PO Released | - |  | Not created | CWIP-76509 | Received | PO Released | - |  | 0 | -160 | -
| 2026-04-30 | 413 | MU | Kandivali | MA818 | MA818 | MU-MA818 | 49.5 | 49.5 | 19.1886 | 72.8441 | Mumbai_Coverage_Route3 | MA818_LM | MCGM | P/N | Siddhachal Chs | SIDDHACHAL CHS, MAMLETDARWADI RD NUMBER 5,ADARSH NAGAR, MALAD WEST,MUMBAI, MAHARASHTRA 400064 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 50 | Ok | 0.5 | PO Released | - |  | Not created | CWIP-76498 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-04-30 | 414 | MU | Kandivali | 4558 | 4558 | MU-4558 | 11 | 11 | 19.1822 | 72.8385 | Mumbai_Coverage_Route3 | 4558_LM | MCGM | P/N | SAINATHAOMM1 | Link Road, Malad West,400064 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76499 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-04-30 | 415 | MU | Kandivali | MB1466 | MB1466 | MU-MB1466 | 11 | 11 | 19.1817 | 72.8365 | Mumbai_Coverage_Route3 | MB1466_LM | MCGM | P/N | Nestle | Nestle,Rajan Pada, Bhandarwada, Gaothan road (Linking Road), Malad West, Mumbai 400 064 | ATC | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76500 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-04-30 | 416 | MU | Malad | 4427 | 4427 | MU-4427 | 22 | 22 | 19.1851 | 72.8421 | Mumbai_Coverage_Route3 | 4427_LM | MCGM | P/N | Nitisha CHSL | Nitisha CHSL, 2nd Cross Rd,Liberty Garden,Malad W | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 20 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76501 | Received | PO Released | - |  | 0 | -20 | -
| 2026-04-30 | 417 | MU | Malad | MB1349 | MB1349 | MU-MB1349 | 11 | 11 | 19.1867 | 72.841 | Mumbai_Coverage_Route3 | MB1349_LM | MCGM | P/N | Chamundia Building | Malad, Navy Colony, Liberty Garden, Malad West, Post Office-Malad, Police Station-Malad, Mumbai, Maharashtra 400064 | ATC | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76502 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-04-30 | 418 | MU | Malad | MA4606 | MA4606 | MU-MA4606 | 5.5 | 5.5 | 19.1841 | 72.8409 | Mumbai_Coverage_Route3 | MA4606_LM | MCGM | P/N | SADGURU CHS. | C Wing, Bhandarwada, Opposite Jain Temple, Malad West, Mumbai-400064 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 10 | Ok | 4.5 | PO Released | - |  | Not created | CWIP-76503 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-04-30 | 419 | MU | Malad |  | MA6472 | MU-MA6472 | 11 | 11 | 19.1887 | 72.848 | Mumbai_Coverage_Route3 | MA6472_LM | MCGM | P/N | Jagruti | Near Malad Subway, Sainath Road, Malad West, Mumbai, 400064 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-04-30 | 420 | MU | Malad | 304 | 304 | MU-304 | 99 | 99 | 19.1873 | 72.8437 | Mumbai_Coverage_Route3 | 304_LM | MCGM | P/N | Trimurti enclave | Trimurti enclave, Mamlatdar Wadi Road, Opp: Gariba Hospital, malad West | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76504 | Received | PO Released | - |  | 0 | -100 | -
| 2026-04-30 | 421 | MU | Malad | 1955 | 1955 | MU-1955 | 165 | 165 | 19.1879 | 72.8459 | Mumbai_Coverage_Route3 | 1955_LM | MCGM | P/N | HETALARCOF | Opp Natraj Shopping Centre, Malad W | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004549 | 2025-03-17 | 2026-03-17 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76505 | Received | PO Released | - |  | 0 | -170 | -
| 2026-04-30 | 422 | MU | Santacruz | 3068 | 3068 | MU-3068 | 5.5 | 5.5 | 19.1737 | 72.8515 | Mumbai_Coverage_Route29 | 3068_LM | MCGM | P/S | Lucky Building CHSL | Lucky Building CHSL, Chinchowali Gate Rd, Chinchowali Colony, Malad East-400063 | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004523 | 2025-03-13 | 2026-03-13 | 10 | Ok | 4.5 | PO Released | - |  | Not created | CWIP-76095 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-04-30 | 423 | MU | Goregaon | 1831 | 1831 | MU-1831 | 201.6 | 201.6 | 19.1667 | 72.853 | Mumbai_Coverage_Route29 | 1831_LM | MCGM | P/S | ALOKJYOTO | Aarey Road, Goregaon(E) 400063 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004519 | 2025-03-13 | 2026-03-13 | 100 | PO length is less than Feasibility length | -101.6 | PO Released | - |  | Not created | CWIP-76493 | RFAI Awaited | PO Released | - |  | 0 | -100 | - |  |  | Site under Relocation
| 2026-04-30 | 424 | MU | Goregaon | 4509 | 4509 | MU-4509 | 187 | 187 | 19.1662 | 72.8506 | Mumbai_Coverage_Route29 | 4509_LM | MCGM | P/S | GULMOHR | Opposite Anupam Theatre, Station Road, Goregaon East, Mumbai-400063 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004519 | 2025-03-13 | 2026-03-13 | 190 | Ok | 3 | PO Released | - |  | Not created | CWIP-76494 | RFAI Awaited | PO Released | - |  | 0 | -190 | -
| 2026-04-30 | 425 | MU | Goregaon | 1742 | 1742 | MU-1742 | 33 | 33 | 19.1675 | 72.8502 | Mumbai_Coverage_Route29 | 1742_LM | MCGM | P/S | Akshata CHS | Akshata Apartment,Near Thomas High School, Gogtewadi, Goregaon East | ATC | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004519 | 2025-03-13 | 2026-03-13 | 30 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76495 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-04-30 | 426 | MU | Goregaon | MA6080 | MA6080 | MU-MA6080 | 297 | 297 | 19.1692 | 72.8516 | Mumbai_Coverage_Route29 | MA6080_LM | MCGM | P/S | Shankhala Industrial Estate | Gogate Wadi Rd, Ganesh Nagar Cooperative Housing Society, Churi Wadi, Goregaon, Mumbai, Maharashtra 400063 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004519 | 2025-03-13 | 2026-03-13 | 300 | Ok | 3 | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | -300 | -
| 2026-04-30 | 427 | MU | Goregaon | 1046 | 1046 | MU-1046 | 11 | 11 | 19.1706 | 72.8508 | Mumbai_Coverage_Route29 | 1046_LM | MCGM | P/S | OMKARPMROM | Plot No 51, Pandurang Wadi, Road No 2, Goregaon East, Mumbai-400063 | INDUS | Route LM | Co-Build | Not Feasible |  | Virendra | #N/A | - | 10004519 | 2025-03-13 | 2026-03-13 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76496 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-10-31 | 428 | MU | Jogeshwari | 4634 | 4634 | MU-4634 | 11 | 11 | 19.1298 | 72.8516 | Mumbai_Coverage_Route28 | 4634_LM | MCGM | K/E | SHRISMRTO | 52, Natwar Nagar, Road No 5, Jogeshwari East, Mumbai-400060 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004512 | 2025-03-12 | 2026-03-12 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76113 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-10-31 | 429 | MU | Jogeshwari |  | MA3718 | MU-MA3718 | 11 | 11 | 19.1267 | 72.8491 | Mumbai_Coverage_Route28 | MA3718_LM | MCGM | K/E | JAFAR HOUSE | Pardisandhpor, Mogra Pada, Natwar Nagar, Jogeshwari East, Mumbai, Maharashtra 400053 | Rakshit | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | PO Modification WIP | - |  | Not created | CWIP-76491 | - | PO Modification WIP | - |  | 0 | 0 | -
| 2026-10-31 | 430 | MU | Jogeshwari | 3019 | 3019 | MU-3019 | 60.5 | 60.5 | 19.1279 | 72.8483 | Mumbai_Coverage_Route28 | 3019_LM | MCGM | K/E | Anand Dham | Building No4, Opp: Amboli Level Crosssing, Andheri East-400053 | INDUS | Route LM | Co-Build | Not Feasible |  | Dudhnath Tiwari | #N/A | - | 10004512 | 2025-03-12 | 2026-03-12 | 60 | PO length is less than Feasibility length | -0.5 | PO Released | - |  | Not created | CWIP-76114 | RFAI Awaited | PO Released | - |  | 0 | -60 | - |  |  | Site under Relocation
| 2026-11-30 | 431 | MU | Kandivali | MA1260 | MA1260 | MU-MA1260 | 11 | 11 | 19.1916 | 72.8661 | Mumbai_Coverage_Route25 | MA1260_LM | MCGM | P/N | MAHENDRA SHARMA | SHIVAJI NAGAR RD, KURAR VILLAGE, MALAD EAST, MUMBAI, MAHARASHTRA 400097 | ATC | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004582 | 2025-03-18 | 2026-03-18 | 400 | PO length is greater than Feasibility Length | 389 | PO Modification WIP | - |  | Not created | CWIP-76486 | RFAI Awaited | PO Modification WIP | - |  | 0 | -400 | -
| 2026-11-30 | 432 | MU | Kandivali | #N/A | 3700 | MU-3700 | 11 | 11 | 19.199 | 72.8645 | Mumbai_Coverage_Route25 | 3700_LM | MCGM | R/S | Rani Recharge centre | RANI RECHARGE CENTER,Near Datta Mandir, Wadar Pada Road 2, Hanuman Nagar, Kandivli East | Suyog | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004582 | 2025-03-18 | 2026-03-18 | 300 | PO length is greater than Feasibility Length | 289 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76487 | RFAI Awaited | PO Released | - |  | 0 | -300 | - |  |  | Site under Relocation
| 2026-11-30 | 433 | MU | Kandivali | 2460 | 2460 | MU-2460 | 11 | 11 | 19.1975 | 72.8645 | Mumbai_Coverage_Route25 | 2460_LM | MCGM | R/S | Nisar House | Pathan Chal Hanuman Nager Akrli Road Kandiwali (E),Mumbai-400101 | ATC | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004582 | 2025-03-18 | 2026-03-18 | 300 | PO length is greater than Feasibility Length | 289 | PO Released | - |  | Not created | CWIP-76488 | RFAI Awaited | PO Released | - |  | 0 | -300 | -
| 2026-11-30 | 434 | MU | Kandivali |  | MA2221 | MU-MA2221 | 11 | 11 | 19.1961 | 72.8646 | Mumbai_Coverage_Route25 | MA2221_LM | MCGM | R/S | Vishwakarma Mandir_Crack | Pathan Chal Hanuman Nager Akrli Road Kandiwali (E),Mumbai-400101 | Rakshit | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-11-30 | 435 | MU | Kandivali | 5619 | 5619 | MU-5619 | 231 | 231 | 19.1936 | 72.8646 | Mumbai_Coverage_Route25 | 5619_LM | MCGM | R/S | Machhindra More House | Machindra House,kurar village Malad (e) | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004582 | 2025-03-18 | 2026-03-18 | 230 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76489 | RFAI Awaited | PO Released | - |  | 0 | -230 | -
| 2026-12-31 | 436 | MU | Dombivali | MA3332 | MA3332 | MU-MA3332 | 22 | 22 | 19.2223 | 73.0804 | Mumbai_Coverage_Route23 | MA3332_LM | KDMC | - | Sachin Mhatre building_Crack | SACHIN MHATRE BUILDING, THAKURWADI, DOMBIVLI WEST, DOMBIVLI, MUMBAI, MAHARASHTRA 421202 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Subhodh | Praveen Nigam | - | 10004556 | 2025-03-17 | 2026-03-17 | 50 | PO length is greater than Feasibility Length | 28 | PO Released | - |  | Not created | CWIP-76481 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-12-31 | 437 | MU | Dombivali | MA5231 | MA5231 | MU-MA5231 | 11 | 11 | 19.2192 | 73.0785 | Mumbai_Coverage_Route23 | MA5231_LM | KDMC | - | Rahul Bhavan/EMUMARCHANAQ | Opp : Hindu Kush Apts, Shastri Nagar, Old Dombivli West | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Subhodh | Praveen Nigam | - | 10004556 | 2025-03-17 | 2026-03-17 | 40 | PO length is greater than Feasibility Length | 29 | PO Released | - |  | Not created | CWIP-76482 | Received | PO Released | - |  | 0 | -40 | -
| 2026-12-31 | 438 | MU | Dombivali | 1508 | 1508 | MU-1508 | 11 | 11 | 19.2174 | 73.0774 | Mumbai_Coverage_Route23 | 1508_LM | KDMC | - | Vipul Niwas | Telkoswadi,Juni Dombivali,Dombivali(W),Thane,Maharashtra 421201 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Subhodh | Praveen Nigam | - | 10004556 | 2025-03-17 | 2026-03-17 | 40 | PO length is greater than Feasibility Length | 29 | PO Released | - |  | Not created | CWIP-76483 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-12-31 | 439 | MU | Dombivali | MB5951 | MB5951 | MU-MB5951 | 11 | 11 | 19.2202 | 73.08 | Mumbai_Coverage_Route23 | MB5951_LM | KDMC | - | JESTHA SADAN | JESTHA SADAN,RAM MANDIR, RD VIA DEVI CHOWK, NEAR RAM MANDIR (RIKSHAW) AUTO STAND, RETI BUNDER, SHASTRI NAGAR, DOMBIVLI WEST, DOMBIVLI, | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Subhodh | Praveen Nigam | - | 10004556 | 2025-03-17 | 2026-03-17 | 50 | PO length is greater than Feasibility Length | 39 | PO Released | - |  | Not created | CWIP-76484 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-10-31 | 440 | MU | Khadakpada | 1262 | 1262 | MU-1262 | 55 | 55 | 19.2315 | 73.0876 | Mumbai_Coverage_Route21 | 1262_LM | KDMC | - | Anusai Bhagat Niwas | ANUSAI BHAGAT NIWAS,Netaji Subhash Chandra Bose Road, Garibachapada, Kumbharkhan Pada, Dombivali West | ATC | Route LM | Co-Build | Feasible | Oct'25 | Vaijesh Patil | Prem Verma | - | 10004548 | 2025-03-17 | 2026-03-17 | 400 | PO length is greater than Feasibility Length | 345 | PO Released | - |  | Not created | CWIP-76475 | RFAI Awaited | PO Released | - |  | 0 | -400 | -
| 2026-10-31 | 441 | MU | Khadakpada | MB2213 | MB2213 | MU-MB2213 | 110 | 110 | 19.2323 | 73.0857 | Mumbai_Coverage_Route21 | MB2213_LM | KDMC | - | Chakrapani Phase 2A | Building No 2A,Chakrapani Apartment,Near model school,mahatma Phule Road, Garibachawada., Kumbharkhan Pada, Dombivli, Maharashtra 421202 | INDUS | Route LM | Co-Build | Feasible | Oct'25 | Vaijesh Patil | Prem Verma | - | 10004548 | 2025-03-17 | 2026-03-17 | 130 | PO length is greater than Feasibility Length | 20 | PO Released | - |  | Not created | CWIP-76476 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-10-31 | 442 | MU | Dombivali | MA5208 | MA5208 | MU-MA5208 | 110 | 110 | 19.2332 | 73.0831 | Mumbai_Coverage_Route21 | MA5208_LM | KDMC | - | ANCHOR_Devki Laxman | Gopinath Chowk, Devicha Pada, Dombivli West, Maharashtra 421202 | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Subhodh | Praveen Nigam | - | 10004548 | 2025-03-17 | 2026-03-17 | 120 | PO length is greater than Feasibility Length | 10 | PO Released | - |  | Not created | CWIP-76477 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2026-10-31 | 443 | MU | Dombivali | 6394 | 6394 | MU-6394 | 11 | 11 | 19.2312 | 73.0805 | Mumbai_Coverage_Route21 | 6394_LM | KDMC | - | SUMITRDEOF | Sumitradevi,Satyavan Chowk, Umesh nagar, Dombivali (W). | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Subhodh | Praveen Nigam | - | 10004548 | 2025-03-17 | 2026-03-17 | 30 | PO length is greater than Feasibility Length | 19 | PO Released | - |  | Not created | CWIP-76478 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-10-31 | 444 | MU | Dombivali | MB2836 | MB2836 | MU-MB2836 | 275 | 275 | 19.2313 | 73.0822 | Mumbai_Coverage_Route21 | MB2836_LM | KDMC | - | Mandar bhoir plot | Mandar Bhoir Plot | INDUS | Route LM | Co-Build | Feasible | Nov'25 | Subhodh | Praveen Nigam | - | 10004548 | 2025-03-17 | 2026-03-17 | 180 | PO length is less than Feasibility length | -95 | PO Released | - |  | Not created | CWIP-76479 | Received | PO Released | - |  | 0 | -180 | -
| 2025-10-31 | 445 | MU | Kashimira | MA1356 | MA1356 | MU-MA1356 | 11 | 11 | 19.2793 | 72.8837 | Mumbai_Coverage_Route2 | MA1356_LM | MBMC | - | Silver Sarita Complex | Kashimira, Mira Road East-401104. | INDUS | Route LM | Co-Build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | - | 10004557 | 2025-03-17 | 2026-03-17 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76473 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-05-31 | 446 | MU | Jogeshwari | MA1352 | MA1352 | MU-MA1352 | 11 | 11 | 19.1287 | 72.869 | Mumbai_Coverage_Route17 | MA1352_LM | MCGM | K/E | Hotel Jinger | Mahakali caves road, Bindra Complex, Andheri (E), Mumbai 400093. | ATC | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004547 | 2025-03-17 | 2026-03-17 | 40 | PO length is greater than Feasibility Length | 29 | PO Released | - |  | Not created | CWIP-76468 | Received | PO Released | - |  | 0 | -40 | -
| 2026-05-31 | 447 | MU | Jogeshwari | 2369 | 2369 | MU-2369 | 11 | 11 | 19.1269 | 72.8692 | Mumbai_Coverage_Route17 | 2369_LM | MCGM | K/E | KISNA9 | Hare Kirshna,Hare Krishna A-9 SRA Co-Op HSG Society Bindra Complex Mahakali Cave Road Andheri (E) | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004547 | 2025-03-17 | 2026-03-17 | 250 | PO length is greater than Feasibility Length | 239 | PO Released | - |  | Not created | CWIP-76469 | RFAI Awaited | PO Released | - |  | 0 | -250 | -
| 2026-05-31 | 448 | MU | Jogeshwari | MA5707 | MA5707 | MU-MA5707 | 220 | 220 | 19.131 | 72.8728 | Mumbai_Coverage_Route17 | MA5707_LM | MCGM | K/E | Mahakali Mandir | , MAHAKALI CAVES ROAD ANDHERI EAST, MUMBAI, MAHARASHTRA. | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004547 | 2025-03-17 | 2026-03-17 | 50 | PO length is less than Feasibility length | -170 | PO Released | - |  | Not created | CWIP-76470 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-05-31 | 449 | MU | Jogeshwari |  | 4525 | MU-4525 | 11 | 11 | 19.1276 | 72.8678 | Mumbai_Coverage_Route17 | 4525_LM | MCGM | K/E | ROSHANAPO | Roshan Appt,OppHoly Spirit Hospital,Mahakali Caves Rd,Andheri(E),Mumbai-400093 | INDUS | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-05-31 | 450 | MU | Jogeshwari | 3389 | 3389 | MU-3389 | 11 | 11 | 19.1297 | 72.8701 | Mumbai_Coverage_Route17 | 3389_LM | MCGM | K/E | New Bilqees App | Bilqees,Mahakali caves road, Andheri (E) | ATC | Route LM | Co-Build | Feasible |  | Dudhnath Tiwari | #N/A | - | 10004547 | 2025-03-17 | 2026-03-17 | 20 | Ok | 9 | PO Released | - |  | Not created | CWIP-76471 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-04-30 | 451 | MU | Belapur | 4871 | 4871 | MU-4871 | 11 | 11 | 19.0158 | 73.0321 | Mumbai_Coverage_Route15 | 4871_LM | PMC | - | Prathamesh (Plot No.275) | Belapur Gaon Sector 20, Belapur-400614 | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004562 | 2025-03-17 | 2026-03-17 | 20 | Ok | 9 | PO Released | - |  | Not created | CWIP-76465 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-04-30 | 452 | MU | Belapur | #N/A | MB6431 | MU-MB6431 | 193.032 | 0 | 19.0155 | 73.0352 | Mumbai_Coverage_Route15 | MB6431_LM | PMC | - | T K Apartment | House No, 0678, Shahdawali Shah Dargah Road, Shahbaz Village, Sector 19, CBD Belapur, Navi Mumbai, Maharashtra 400614 | Netsol | Route LM | Co-Build | Data mismatch |  | Abdul Quadir | #N/A | - | 10004562 | 2025-03-17 | 2026-03-17 | 170 | PO length is greater than Feasibility Length | 170 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76466 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-11-30 | 453 | MU | Khadakpada | MB1187 | MB1187 | MU-MB1187 | 88 | 88 | 19.2621 | 73.1445 | Mumbai_Coverage_Route13 | MB1187_LM | KDMC | - | Reveria Building | Godrej Hill, Khadakpada, Kalyan, Maharashtra 421301 | INDUS | Route LM | Co-Build | Feasible | Oct'25 | Vaijesh Patil | Prem Verma | - | 10004559 | 2025-03-17 | 2026-03-17 | 100 | PO length is greater than Feasibility Length | 12 | PO Released | - |  | Request Raised | CWIP-76458 | Received | PO Released | - |  | 0 | -100 | -
| 2026-11-30 | 454 | MU | Khadakpada | MA5523 | MA5523 | MU-MA5523 | 55 | 55 | 19.2598 | 73.1436 | Mumbai_Coverage_Route13 | MA5523_LM | KDMC | - | D-Mart_Kalyan_SCM | SHOP NO - 03,C,WADHWA HEIGHTS, GODREJ HILL RD, NEAR D-MART, KHADAKPADA, KHADAKPADA, CITY-KALYAN,THANE, MAHARASHTRA, PINCODE- 421301 | Airtel Own | Route LM | Co-Build | Feasible | Oct'25 | Vaijesh Patil | Prem Verma | - | 10004559 | 2025-03-17 | 2026-03-17 | 60 | Ok | 5 | PO Released | - |  | Request Raised | CWIP-76459 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-11-30 | 455 | MU | Khadakpada | 175 | 175 | MU-175 | 165 | 165 | 19.2575 | 73.1427 | Mumbai_Coverage_Route13 | 175_LM | KDMC | - | Mahakaleshwar chs | Barve Village, Khadakpada Chowk, Near Godrej Hill, Kalyan West, Dist Thane, 421301 | INDUS | Route LM | Co-Build | Feasible | May'25 | Vaijesh Patil | Prem Verma | - | 10004559 | 2025-03-17 | 2026-03-17 | 800 | PO length is greater than Feasibility Length | 635 | PO Modification WIP | - |  | Request Raised | CWIP-76460 | RFAI Awaited | PO Modification WIP | - |  | 0 | -800 | -
| 2026-11-30 | 456 | MU | Khadakpada | #N/A | MA599 | MU-MA599 | 330 | 330 | 19.2624 | 73.1415 | Mumbai_Coverage_Route13 | MA599_LM | KDMC | - | Shiv Valley Bldg No.3 | SHIV VALLEY BLDG NO.3, BARAVE RD, GODREJ HILL, KHADAKPADA, KALYAN, MUMBAI, MAHARASHTRA 421301 | Purple Soil | Route LM | Co-Build | Feasible | May'25 | Jayhind Yadav | Yogesh Deshpande | - | 10004559 | 2025-03-17 | 2026-03-17 | 450 | PO length is greater than Feasibility Length | 120 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76461 | RFAI Awaited | PO Released | - |  | 0 | -450 | -
| 2026-11-30 | 457 | MU | Khadakpada | MA5153 | MA5153 | MU-MA5153 | 276.1 | 276.1 | 19.2635 | 73.1369 | Mumbai_Coverage_Route13 | MA5153_LM | KDMC | - | Motiram Open Plot | KALYAN-SAPE RD, GANDHAR NAGAR, KHADAKPADA, KALYAN THANE,STATE-MAHARASHTRA PINCODE-421301 | INDUS | Route LM | Co-Build | Feasible | April'25 | Vaijesh Patil | Prem Verma | - | 10004559 | 2025-03-17 | 2026-03-17 | 280 | Ok | 3.9 | PO Released | - |  | Request Raised | CWIP-76462 | Received | PO Released | - |  | 0 | -280 | -
| 2026-11-30 | 458 | MU | Khadakpada | MA5138 | MA5138 | MU-MA5138 | 181.5 | 181.5 | 19.2626 | 73.147 | Mumbai_Coverage_Route13 | MA5138_LM | KDMC | - | Padmavati Builders Open Plot | GODREJ HILL, KHADAKPADA, KALYAN,THANE,421301 | ATC | Route LM | Co-Build | Feasible | April'25 | Vaijesh Patil | Prem Verma | - | 10004559 | 2025-03-17 | 2026-03-17 | 190 | Ok | 8.5 | PO Released | - |  | Request Raised | CWIP-76463 | RFAI Awaited | PO Released | - |  | 0 | -190 | -
| 2026-02-28 | 459 | MU | Palava City | 6194 | 6194 | MU-6194 | 63.8 | 63.8 | 19.1683 | 73.074 | Mumbai_Coverage_Route12 | 6194_LM | KDMC | - | Casa Bella Gold Sub station | Casa Bella Gold, Casa Bella,Dombivali(E),Thane, Maharashtra 421204 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Jayhind Yadav | Yogesh Deshpande | - | 10004561 | 2025-03-17 | 2026-03-17 | 60 | PO length is less than Feasibility length | -3.8 | PO Released | - |  | Not created | CWIP-76453 | Received | PO Released | - |  | 0 | -60 | -
| 2026-02-28 | 460 | MU | Palava City | MA4669 | MA4669 | MU-MA4669 | 6.6 | 6.6 | 19.1672 | 73.0726 | Mumbai_Coverage_Route12 | MA4669_LM | KDMC | - | Viento B wing | VIENTO B WING, LODHA,PALAVA,DOMBIVLI EAST, MUMBAI, MAHARASHTRA. | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | - | 10004561 | 2025-03-17 | 2026-03-17 | 40 | PO length is greater than Feasibility Length | 33.4 | PO Released | - |  | Not created | CWIP-76454 | Received | PO Released | - |  | 0 | -40 | -
| 2026-02-28 | 461 | MU | Palava City | MA3429 | MA3429 | MU-MA3429 | 35.2 | 35.2 | 19.1738 | 73.0717 | Mumbai_Coverage_Route12 | MA3429_LM | KDMC | - | Magnifica Open Plot | Magnifica Open plot, Casa Bella InternalCasa Bella Main Rd, Casa Bella, Usarghar, Maharashtra 421204 | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | - | 10004561 | 2025-03-17 | 2026-03-17 | 40 | Ok | 4.8 | PO Released | - |  | Not created | CWIP-76455 | Received | PO Released | - |  | 0 | -40 | -
| 2026-02-28 | 462 | MU | Palava City | 6164 | 6164 | MU-6164 | 11 | 11 | 19.1737 | 73.0691 | Mumbai_Coverage_Route12 | 6164_LM | KDMC | - | Pole Near Temple(Casa Bella) | LODHA HEAVEN CASA BELLA,PALAVA CITY, DOMBIWALI E | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Jayhind Yadav | Yogesh Deshpande | - | 10004561 | 2025-03-17 | 2026-03-17 | 30 | PO length is greater than Feasibility Length | 19 | PO Released | - |  | Not created | CWIP-76456 | Received | PO Released | - |  | 0 | -30 | -
| 2026-03-31 | 463 | MU | Thane | 4488 | 4488 | MU-4488 | 11 | 11 | 19.1868 | 72.9535 | Mumbai_Coverage_Route10 | 4488_LM | TMC | - | STLAWRENO | StLawrence High School,Road No - 3,Waghle Estate,Thane - 400604 | INDUS | Route LM | Co-Build | Feasible |  | Ranjit Wadkar | #N/A | - | 10004558 | 2025-03-17 | 2026-03-17 | 50 | PO length is greater than Feasibility Length | 39 | PO Released | - |  | Not created | CWIP-76449 | Received | PO Released | - |  | 0 | -50 | -
| 2026-03-31 | 464 | MU | Thane | 4004 | 4004 | MU-4004 | 11 | 11 | 19.1893 | 72.9522 | Mumbai_Coverage_Route10 | 4004_LM | TMC | - | GANESHQQOF | Ganesh, Road No 15, Kisan Nagar, Thane 400604 | INDUS | Route LM | Co-Build | Feasible |  | Ranjit Wadkar | #N/A | - | 10004558 | 2025-03-17 | 2026-03-17 | 50 | PO length is greater than Feasibility Length | 39 | PO Released | - |  | Not created | CWIP-76450 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-03-31 | 465 | MU | Thane | #N/A | MA5851 | MU-MA5851 | 187 | 187 | 19.1869 | 72.9515 | Mumbai_Coverage_Route10 | MA5851_LM | TMC | - | United House | UNITED HOUSE, PADWAL NAGAR, KISAN NAGAR,THANE(W) MUMBAI, MAHARASHTRA. 400604 | Rakshit | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004558 | 2025-03-17 | 2026-03-17 | 190 | Site Drop by Airtel but PO Received | 3 | PO Modification WIP | - |  | Not created | CWIP-76451 | - | PO Modification WIP | - |  | 0 | -190 | -
| 2026-03-31 | 466 | MU | Bhayander East | 2309 | 2309 | MU-2309 | 11 | 11 | 19.2927 | 72.8767 | Mumbai_Coverage_Route1 | 2309_LM | MBMC | - | Marigold Bldg No 5 | New Marigold Bldg No.5,New Marigold CHSL Bldg no.5, Kanakia Spaces, near Cinemax, Baverly Park, Mira Road East, Thane Dist 401 105 | INDUS | Route LM | Co-Build | Not Feasible | Oct'25 | Sabhajeet Maurya | Satish Singh | - | 10004966 | 2025-04-15 | 2026-04-15 | 150 | PO length is less than Feasibility length | 139 | PO Released | - |  | Not created | CWIP-76111 | Received | PO Released | - |  | 0 | -150 | -
| 2027-01-31 | 467 | MU | Mankhurd | #N/A | MA4640 | MU-MA4640 | 55 | 55 | 19.0497 | 72.9336 | MUM_Route_90 | MA4640_LM | MCGM | M/E | Tej Plastic Metal Mart (Alt of Shivneri Mitra Mandal) | Tej plastic, Sahyadri Chawl, Mahatma Phule nagar No 1 , Sion Panvel Highway, Mankhurd, Mum-400088 | Suyog | Route LM | Co-build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004960 | 2025-04-08 | 2026-04-08 | 70 | PO length is greater than Feasibility Length | 15 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76660 | Received | PO Released | - |  | 0 | -70 | -
| 2027-01-31 | 468 | MU | Sanpada | 1641 | 1641 | MU-1641 | 400 | 400 | 19.0689 | 73.0125 | MUM_Route_90 | 1641_LM | NMMC | - | BALAJIAPO | Behind Hotel Appetite, Sion Panvel Highway, Vashi, Navi Mumbai-400703 | INDUS | Route LM | Co-Build | Not Feasible | Nov'25 | Abdul Quadir | #N/A | - | 10004960 | 2025-04-08 | 2026-04-08 | 300 | PO Pending |  | PO Released | - |  | Request Raised | #N/A | RFAI Awaited | PO Released | - |  | 0 | -300 | -
| 2027-01-31 | 469 | MU | Shiravane | 3625 | 3625 | MU-3625 | 110 | 110 | 19.0484 | 73.0272 | MUM_Route_90 | 3625_LM | NMMC | - | DX-10 | DX-10, MIDC Industrial Area, Shiravane, Nerul, Navi Mumbai, Maharashtra 400706 | INDUS | Route LM | Co-Build | Feasible | Nov'25 | Abdul Quadir | #N/A | - | 10004960 | 2025-04-08 | 2026-04-08 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Request Raised | CWIP-76661 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2027-01-31 | 470 | MU | Vashi | 583 | 583 | MU-583 | 110 | 110 | 19.0691 | 72.9879 | MUM_Route_90 | 583_LM | NMMC | - | Vardh Vinayak | Varadh Vinayak,plot no -162, Sector 31, Vashi Gaon, Near Vashi Tol Naka, Vashi,Navi Mumbai | ATC | Route LM | Co-Build | Feasible | Dec'25 | Abdul Quadir | #N/A | - | 10004960 | 2025-04-08 | 2026-04-08 | 60 | PO length is less than Feasibility length | -50 | PO Released | - |  | Request Raised | CWIP-76662 | Received | PO Released | - |  | 0 | -60 | -
| 2027-01-31 | 471 | MU | Vashi | 5307 | 5307 | MU-5307 | 129.48 | 0 | 19.071 | 72.998 | MUM_Route_90 | 5307_LM | NMMC | - | ARENJAQQOF | Arenja Arcade Sec-17, Plot No-4, Vashi, New Mumbai-400703 | INDUS | Route LM | Co-Build | Data mismatch | Dec'25 | Narayan Parab | #N/A | - | 10004960 | 2025-04-08 | 2026-04-08 | 300 | Ok | 300 | PO Released | - |  | Request Raised | CWIP-76663 | RFAI Awaited | PO Released | - |  | 0 | -300 | -
| 2027-01-31 | 472 | MU | Vashi | 5814 | 5814 | MU-5814 | 220 | 0 | 19.0682 | 72.9898 | MUM_Route_90 | 5814_LM | NMMC | - | ANISHAHMOF | Anisha Homes,Plot No238,Sec -31,Vashi Village,Navi Mumbai-400703 | INDUS | Route LM | Co-Build | De-scope | Dec'25 | Abdul Quadir | #N/A | - | 10004960 | 2025-04-08 | 2026-04-08 | 180 | Ok | 180 | PO Released | - |  | Request Raised | CWIP-76664 | RFAI Awaited | PO Released | - |  | 0 | -180 | -
| 2026-02-28 | 473 | MU | Airoli | 1694 | 1694 | MU-1694 | 300 | 300 | 19.1751 | 72.997 | MUM_Route_68 | 1694_LM | NMMC | - | MATOSHRI APPT | Mr. Abhishek(9889205001), Matoshree Appt, Thane-Belapur Road, Sanjay Gandhi Nagar, Dighe, Navi Mumbai, Maharashtra 400708 NAVI MUMBAI | ATC | Route LM | Co-Build | Not Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 200 | PO length is less than Feasibility length | -100 | PO Released | - |  | Not created | CWIP-76755 | Received | PO Released | - |  | 0 | -200 | -
| 2026-02-28 | 474 | MU | Airoli |  | 1863 | MU-1863 | 605 | 605 | 19.1586 | 72.9983 | MUM_Route_68 | 1863_LM | NMMC | - | Shri Sainath Chsl | ambedkar rd, opp airoli station, airoli E | ATC | Route LM | Co-Build | Feasible | Feb'26 | Abdul Quadir | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2026-02-28 | 475 | MU | Airoli | MB2246 | MB2246 | MU-MB2246 | 605 | 605 | 19.1535 | 72.9989 | MUM_Route_68 | MB2246_LM | NMMC | - | Shree Radhe Krishna Chs | SHREE RADHE KRISHNA CHS,PLOT NO-11, ABOVE ABHINANDHAN HOTEL, SECTOR 4, AIROLI, NAVI MUMBAI,POST OFFICE:-AIROLI,POLICE STATION:-AIROLI | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 80 | PO length is less than Feasibility length | -525 | PO Released | - |  | Not created | CWIP-76756 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2026-02-28 | 476 | MU | Airoli | 5618 | 5618 | MU-5618 | 200 | 200 | 19.1731 | 72.9986 | MUM_Route_68 | 5618_LM | NMMC | - | SHAGIRAHOF | Shageer Ahmed House, Opp Thomson Press, Sanjay Gandhi Nagar, Digha-Belapur Road, Navi Mumbai-400708 | INDUS | Route LM | Co-Build | Not Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 50 | PO length is less than Feasibility length | -150 | PO Released | - |  | Not created | CWIP-76757 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-02-28 | 477 | MU | Airoli | 109 | 109 | MU-109 | 200 | 200 | 19.1553 | 72.999 | MUM_Route_68 | 109_LM | NMMC | - | Swagat | Sector 4, Airoli, Navi Mumbai, Maharashtra 400708 | INDUS | Route LM | Co-Build | Not Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004657 | 2025-03-24 | 2026-03-24 | 60 | PO length is less than Feasibility length | -140 | PO Released | - |  | Not created | CWIP-76758 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2025-12-31 | 478 | MU | Jogeshwari | 2161 | 2161 | MU-2161 | 110 | 110 | 19.1426 | 72.8541 | MUM_Route_62 | 2161_LM | MCGM | P/S | Raheja Titanium | Ram Nagar, Near Western Express Highway, Goregaon East | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004595 | 2025-03-19 | 2026-03-19 | 100 | PO length is less than Feasibility length | -10 | PO Released | - |  | Not created | CWIP-76438 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2026-01-31 | 479 | MU | JuiNagar | 4750 | 4750 | MU-4750 | 330 | 330 | 19.0563 | 73.0293 | MUM_Route_58 | 4750_LM | NMMC | - | Rizwan Ice Factory | Plot No. D/366, Near MIDC Ioc Terminal Road, MIDC, Turbhe. | ATC | Route LM | Co-Build | Feasible | Jan'26 | Narayan Parab | #N/A | - | 10004658 | 2025-03-24 | 2026-03-24 | 330 | Ok | 0 | PO Released | - |  | Not created | CWIP-76750 | Received | PO Released | - |  | 0 | -330 | -
| 2026-01-31 | 480 | MU | Turbhe |  | MA5877 | MU-MA5877 | 55 | 55 | 19.0738 | 73.0279 | MUM_Route_58 | MA5877_LM | NMMC | - | Super containers pvt ltd (Relocation of MA3575_Gaikwad House) | PLOT - C 425, MIDC INDUSTRIAL AREA, TTC TURBHE, MUMBAI, MAHARASHTRA. 400703 | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 481 | MU | Turbhe | MA3485 | MA3485 | MU-MA3485 | 132 | 132 | 19.0804 | 73.0277 | MUM_Route_57 | MA3485_LM | NMMC | - | Sejal plastic | Turbhe,TTC Industrial Area, Opposite Mayur cold storage, Navi Mumbai | INDUS | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004659 | 2025-03-24 | 2026-03-24 | 130 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76746 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-03-31 | 482 | MU | Turbhe | MB1718 | MB1718 | MU-MB1718 | 198 | 198 | 19.0766 | 73.0307 | MUM_Route_57 | MB1718_LM | NMMC | - | Chemox House | Plot No: D84, Indira Nagar, MIDC Industrial Area, Turbhe, Navi Mumbai, Maharashtra 400705 | ATC | Route LM | Co-Build | Feasible | Jan'26 | Abdul Quadir | #N/A | - | 10004659 | 2025-03-24 | 2026-03-24 | 160 | PO length is less than Feasibility length | -38 | PO Released | - |  | Not created | CWIP-76747 | Received | PO Released | - |  | 0 | -160 | -
| 2026-03-31 | 483 | MU | Turbhe | MB6371 | MB6371 | MU-MB6371 | 220 | 220 | 19.0692 | 73.0313 | MUM_Route_57 | MB6371_LM | NMMC | - | PERFECT PAKET MOVERS | Perfect Packet Movers,Turbhe Belapur Rd, MIDC Industrial Area, Sanpada, Navi Mumbai, Maharashtra 400706,Post office:-Turbhe,police station:Turbhe | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004659 | 2025-03-24 | 2026-03-24 | 100 | PO length is less than Feasibility length | -120 | PO Released | - |  | Not created | CWIP-76748 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2025-07-31 | 484 | MU | Rabale | MA2181 | MA2181 | MU-MA2181 | 543.252 | 0 | 19.1357 | 73.0189 | MUM_Route_50 | MA2181_LM | NMMC | - | Sai Prasad Building | MIDC IND AREA RABLE | INDUS | Route LM | Co-Build | Not Feasible | Feb'26 | Narayan Parab | #N/A | - | 10004765 | 2025-05-21 | 2026-05-21 | 400 | Old PO - 10004772 revised PO received 21-05-2025 | 400 | PO Released | Part of 99 |  | FF_NW2122_785499 | CWIP-76743 | RFAI Awaited | PO Released | 730473 |  | 375 | -25 | -
| 2025-07-31 | 485 | MU | Rabale | MB3667 | MB3667 | MU-MB3667 | 275 | 275 | 19.1136 | 73.0233 | MUM_Route_50 | MB3667_LM | NMMC | - | Plot No. 255 19.113555 73.023331 | Plot No-255.Mahape Midc Rd. Midc Industrial Area. Mahape.Post Office:-Mahape. | INDUS | Route LM | Co-Build | Feasible | Feb'26 | Abdul Quadir | #N/A | - | 10004765 | 2025-05-21 | 2026-05-21 | 280 | Old PO - 10004772 revised PO received 21-05-2025 | 5 | PO Released | Part of 99 |  | FF_NW2122_785500 | CWIP-76744 | RFAI Awaited | PO Released | 450717 |  | 130 | -150 | -
| 2026-03-31 | 486 | MU | Mahape | #N/A | MB2282 | MU-MB2282 | 55 | 55 | 19.0933 | 73.0214 | MUM_Route_49 | MB2282_LM | NMMC | - | Team Design Architect | A-145/6, Pawane Village Midc Rd, T.T.C. Industrial Area, MIDC Industrial Area, Pawne, Navi Mumbai, Maharashtra 400710 | Netsol | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004665 | 2025-03-24 | 2026-03-24 | 60 | Ok | 5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76741 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-12-31 | 487 | MU | Dahisar | 297 | 297 | MU-297 | 165 | 165 | 19.2565 | 72.867 | MUM_Route_4 | 297_LM | MCGM | R/N | Rajmudra A & B Wing | Parag Nagar, Ketki Pada, Dahisar East,Mumbai- 400068 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76100 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-12-31 | 488 | MU | Miraroad | MA2938 | MA2938 | MU-MA2938 | 165 | 165 | 19.2657 | 72.8746 | MUM_Route_4 | MA2938_LM | MBMC | - | Ajit Ind Estate | AJIT IND ESTATE , LIJAT PAPAD COMPANY NR AJIT PALACE HOTEL MIRA BHAYANDER RD, DAHISER EAST, MUMBAI, MAHARASHTRA. | INDUS | Route LM | Co-Build | Feasible | March'26 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76101 | Received | PO Released | - |  | 0 | -170 | -
| 2026-12-31 | 489 | MU | Miraroad | MA2915 | MA2915 | MU-MA2915 | 110 | 110 | 19.2731 | 72.886 | MUM_Route_4 | MA2915_LM | MBMC | - | BHATIA OPEN PLOT | Plot Mo. 19. Neel Kamal Naka, R K Building, Laxmi Baug, Kashigaon, Mira Road, Mira Bhayandar, Maharashtra 401107 | ATC | Route LM | Co-Build | Feasible | Feb'26 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76102 | Received | PO Released | - |  | 0 | -110 | -
| 2026-12-31 | 490 | MU | Miraroad | 4779 | 4779 | MU-4779 | 110 | 110 | 19.2802 | 72.8902 | MUM_Route_4 | 4779_LM | MBMC | - | SSCLUTCHO | S.S Clutch(RTT),S.S.Clutch Mfg. Co Pvt ltd., 462 SVP road, Mumbai-04 | INDUS | Route LM | Co-Build | Feasible | March'26 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 110 | PO Pending |  | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-12-31 | 491 | MU | Miraroad | #N/A | MB6450 | MU-MB6450 | 55 | 55 | 19.2816 | 72.8897 | MUM_Route_4 | MB6450_LM | MBMC | - | Vaity Open Plot | HARIBHAKTI INDUATRIAL ESTATE, GHBUNDER ROAD, OPP. MICROVAC ENGINEERS, MIRA BHAYANDAR, POST OFFICE-MIRA BHAYANDAR, POLICE STATION-MI 401104 | Rakshit | Route LM | Co-Build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 60 | Site Drop by Airtel but PO Received | 5 | PO Modification WIP | - |  | Not created | CWIP-76103 | - | PO Modification WIP | - |  | 0 | -60 | -
| 2026-12-31 | 492 | MU | Miraroad | #N/A | MA2917 | MU-MA2917 | 242 | 242 | 19.2886 | 72.8958 | MUM_Route_4 | MA2917_LM | MBMC | - | Rajesh Kamble House | Ghodbunder Gaon, Versave, Thane - 401 104 | Suyog | Route LM | Co-Build | Feasible | March'26 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 240 | PO length is less than Feasibility length | -2 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76104 | Received | PO Released | - |  | 0 | -240 | -
| 2026-12-31 | 493 | MU | Miraroad | 5274 | 5274 | MU-5274 | 55 | 55 | 19.2852 | 72.899 | MUM_Route_4 | 5274_LM | MBMC | - | Hill Top | Hill Top Hotel, Near Mumbai-Ahmedabad highway, Versova village, Versova, Mira Bhayandar, Maharashtra 401107 | INDUS | Route LM | Co-Build | Feasible | May'25 | Sabhajeet Maurya | Satish Singh | - | 10004541 | 2025-03-13 | 2026-03-13 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76105 | Received | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 494 | MU | Andheri | MA609 | MA609 | MU-MA609 | 110 | 110 | 19.1351 | 72.8174 | MUM_Route_37 | MA609_LM | MCGM | K/W | Padmaja CHSL | Padmaja Apartment, Fisheries University Rd, Versova, Andheri West, Mumbai, Maharashtra 400061,post office:-Andheri,police station:-Andheri | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004525 | 2025-03-13 | 2026-03-13 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76098 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-04-30 | 495 | MU | Goregaon | #N/A | MA5287 | MU-MA5287 | 154 | 154 | 19.1692 | 72.8368 | MUM_Route_36 | MA5287_LM | MCGM | P/S | Babu Khan | Babu Khan , Prem Nagar Road,Goregaon (W),Mumbai-400104 | Suyog | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004962 | 2025-04-08 | 2026-04-08 | 150 | Ok | -4 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76707 | Received | PO Released | - |  | 0 | -150 | -
| 2026-04-30 | 496 | MU | Goregaon | #N/A | MA4035 | MU-MA4035 | 88 | 88 | 19.1692 | 72.8417 | MUM_Route_36 | MA4035_LM | MCGM | P/S | AJIZ SHEIKH HOUSE | Unnat Nagar Rd Number 2, Prem Nagar Slums, Prem Nagar, Goregaon W | Netsol | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004962 | 2025-04-08 | 2026-04-08 | 90 | Ok | 2 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76708 | RFAI Awaited | PO Released | - |  | 0 | -90 | -
| 2026-04-30 | 497 | MU | Goregaon |  | 6033 | MU-6033 | 396 | 396 | 19.1662 | 72.8428 | MUM_Route_36 | 6033_LM | MCGM | P/S | DIVYANGTOF | Md. Hasan Mendihasan Khan 9930140859, 6/23, Yashwant Nagar Rd No 2, Goregaon West, Mumbai, Maharashtra 400104 MUMBAI | INDUS | Route LM | Co-Build | Not Feasible |  | Virendra | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2026-04-30 | 498 | MU | Goregaon |  | MA3631 | MU-MA3631 | 264 | 264 | 19.1598 | 72.8477 | MUM_Route_36 | MA3631_LM | MCGM | P/S | CHANDRA DARSHAN | JAWAHAR NAGAR, ROAD NO.9, GOREGAON W. | INDUS | Route LM | Co-Build | Not Feasible |  | Virendra | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2026-11-30 | 499 | MU | Oshiwara | 278 | 278 | MU-278 | 66 | 66 | 19.1472 | 72.836 | MUM_Route_35 | 278_LM | MCGM | K/W | TECH WEB CENTRE | TECH WEB CENTRE, LINK ROAD BEHRAM BAUG JOGESHWARI W | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004671 | 2025-03-24 | 2026-03-24 | 70 | Ok | 4 | PO Released | - |  | Not created | CWIP-76705 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-04-30 | 500 | MU | Goregaon | MA6341 | MA6341 | MU-MA6341 | 22 | 22 | 19.174 | 72.8461 | MUM_Route_33 | MA6341_LM | MCGM | P/S | AK Tower | 1001, LILIYA NAGAR, NEAR MTNL TELEPHONE EXCANGE S.V ROAD, , MALAD WEST,PINCODE- 400064 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004523 | 2025-03-13 | 2026-03-13 | 20 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76096 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-04-30 | 501 | MU | Malad | MA1484 | MA1484 | MU-MA1484 | 143 | 143 | 19.1803 | 72.8383 | MUM_Route_33 | MA1484_LM | MCGM | P/N | MA1484-Kaveri Bldg No. 13 | Chincholi Bunder Rd, Malad, Chincholi Bunder, Malad West, Mumbai, Maharashtra 400064 | ATC | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004523 | 2025-03-13 | 2026-03-13 | 140 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76092 | RFAI Awaited | PO Released | - |  | 0 | -140 | -
| 2026-04-30 | 502 | MU | Goregaon | 5768 | 5768 | MU-5768 | 297 | 297 | 19.1739 | 72.8535 | MUM_Route_33 | 5768_LM | MCGM | P/S | ABROLW | Abrol Apartments,Vasant Valley, Near Oberoi Mall, Goregaon East | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004523 | 2025-03-13 | 2026-03-13 | 300 | Ok | 3 | PO Released | - |  | Not created | CWIP-76093 | RFAI Awaited | PO Released | - |  | 0 | -300 | -
| 2026-04-30 | 503 | MU | Malad | 5579 | 5579 | MU-5579 | 99 | 99 | 19.1743 | 72.8485 | MUM_Route_33 | 5579_LM | MCGM | P/S | HAKIMBLDOF | Hakimi CHS,13,udyog nagar,liliya ngr,sv rd,goregaon(w) | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004523 | 2025-03-13 | 2026-03-13 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76094 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2025-12-31 | 504 | MU | Malad | MA1878 | MA1878 | MU-MUM_Route_30 | 55 | 0 | 19.1776 | 72.8363 | MUM_Route_30 | MA1878_LM | MCGM | P/S | 0 | Nirman Industrial Estate, Near Chincholi Fire Station, New Link Rd, Ram Nagar, Malad West, Mumbai, Maharashtra 400064 | INDUS | Route LM | Co-Build | 0 |  | #N/A | #N/A | - | 10004669 | 2025-03-24 | 2026-03-24 | 60 | PO length is greater than Feasibility Length | 60 | PO Released | - |  | Not created | CWIP-76701 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2025-12-31 | 505 | MU | Malad | 6502 | 6502 | MU-6502 | 264 | 264 | 19.1728 | 72.8357 | MUM_Route_30 | 6502_LM | MCGM | P/S | INORBTMLOF | Link Road, Malad West, Mumbai-400064 | Airtel Own | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004669 | 2025-03-24 | 2026-03-24 | 260 | PO length is less than Feasibility length | -4 | PO Released | - |  | Not created | CWIP-76702 | RFAI Awaited | PO Released | - |  | 0 | -260 | -
| 2026-01-31 | 506 | MU | Versova | 139 | 139 | MU-139 | 209 | 209 | 19.1239 | 72.8218 | MUM_Route_27 | 139_LM | MCGM | K/W | Harsh Vardhan | jhhu varsova link road bharat nager 4 banglow Andheri west,400058 | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 210 | Ok | 1 | PO Released | - |  | Not created | CWIP-76421 | RFAI Awaited | PO Released | - |  | 0 | -210 | -
| 2026-01-31 | 507 | MU | Andheri | 2283 | 2283 | MU-2283 | 104.5 | 104.5 | 19.1216 | 72.8248 | MUM_Route_27 | 2283_LM | MCGM | K/W | VIGNHRTA | Plot No 35, Nav Bharata Rd, Varsova Link Rd, Andheri(W) | ATC | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 150 | PO length is greater than Feasibility Length | 45.5 | PO Released | - |  | Not created | CWIP-76422 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-01-31 | 508 | MU | Andheri | MB3372 | MB3372 | MU-MB3372 | 88 | 88 | 19.1078 | 72.8408 | MUM_Route_27 | MB3372_LM | MCGM | K/W | KLS Memorial Hospital | KLS MEMORIAL HOSPITAL,TANAJI MALUSARE RD, NAVPADA, IRLA, VILE PARLE WEST,POST OFFICE:-VILE PARLE,POLICE STATION:-VILE PARLE | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 90 | Ok | 2 | PO Released | - |  | Not created | CWIP-76423 | RFAI Awaited | PO Released | - |  | 0 | -90 | -
| 2026-01-31 | 509 | MU | Vile Parle | 1148 | 1148 | MU-1148 | 475 | 475 | 19.1046 | 72.8406 | MUM_Route_27 | 1148_LM | MCGM | K/W | KSHEMKALO | Sanyas Ashram Compound, Vithalbhai Road, Vile Parle West, Mumbai-400056 | INDUS | Route LM | Co-Build | Not Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 480 | Ok | 5 | PO Released | - |  | Not created | CWIP-76424 | RFAI Awaited | PO Released | - |  | 0 | -480 | -
| 2026-01-31 | 510 | MU | Vile Parle | MB6434 | MB6434 | MU-MB6434 | 5.5 | 5.5 | 19.105 | 72.8392 | MUM_Route_27 | MB6434_LM | MCGM | K/W | Chandan Apt | Chandan Apartments, G - 3, Swami Vivekananda Rd, Indira Nagar, Vile Parle West, Mumbai, Maharashtra 400056 | ATC | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 60 | PO length is greater than Feasibility Length | 54.5 | PO Released | - |  | Not created | CWIP-76425 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 511 | MU | Vile Parle | MB2875 | MB2875 | MU-MB2875 | 5.5 | 5.5 | 19.0902 | 72.8363 | MUM_Route_27 | MB2875_LM | MCGM | K/W | Pioneer Heritage Residency | A-21 Sane Guruji Road BEST Colony Santacruz West Mumbai Maharashtra- 400054 MUMBAI | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 60 | PO length is greater than Feasibility Length | 54.5 | PO Released | - |  | Not created | CWIP-76426 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 512 | MU | Vile Parle | MB1250 | MB1250 | MU-MB1250 | 121 | 121 | 19.0903 | 72.8331 | MUM_Route_27 | MB1250_LM | MCGM | K/W | Nutan Alka | Nutan Alka Cooperative Housing Society,Plot No:-67,Daulat Nagar,STY Relief Rd,Santacruz West,Mumbai,Maharashtra 400049 | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 200 | PO length is greater than Feasibility Length | 79 | PO Released | - |  | Not created | CWIP-76427 | RFAI Awaited | PO Released | - |  | 0 | -200 | -
| 2026-01-31 | 513 | MU | Vile Parle | #N/A | MA4901 | MU-MA4901 | 99 | 99 | 19.0876 | 72.8349 | MUM_Route_27 | MA4901_LM | MCGM | K/W | Shastri Nagar Bus Depot | SHASTRI NAGAR, SANTACRUZ WEST, MUMBAI, MAHARASHTRA 400054 | Suyog | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004594 | 2025-03-19 | 2026-03-19 | 250 | PO length is greater than Feasibility Length | 151 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76428 | RFAI Awaited | PO Released | - |  | 0 | -250 | -
| 2026-04-30 | 514 | MU | Mahape | 1777 | 1777 | MU-1777 | 110 | 110 | 19.1146 | 73.0165 | MUM_Route_160 | 1777_LM | NMMC | - | TECHNOCITY X5/3 | TECHNOCITY X5/3, RELIANCE CORPORATE PARK, MIDC INDUSTRIAL AREA,GHANSOLI,400701 | Airtel Own | Route LM | Co-Build | Feasible | May'25 | Abdul Quadir | #N/A | - | 10004654 | 2025-03-24 | 2026-03-24 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76693 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2025-11-30 | 515 | MU | Kurla | MA1669 | MA1669 | MU-MA1669 | 220 | 220 | 19.0732 | 72.8769 | MUM_Route_16 | MA1669_LM | MCGM | L | Rizvi Bldg | Rizvi Bldg, LBS road , Ambedkar nagar , Kurla west, Mumbai, Maharashtra 400070 | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004588 | 2025-03-19 | 2026-03-19 | 220 | PO Pending |  | PO Released | - |  | Not created | CWIP-76402 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-05-31 | 516 | MU | Kandivali | 2257 | 2257 | MU-MUM_Route_142 | 67.2 | 0 | 19.2089 | 72.8734 | MUM_Route_142 | 2257_LM | MCGM | R/S | 0 | D-Mart, opp thakur mall, Thakur village, kandivali (e) | Airtel Own | Route LM | Co-Build | 0 |  | #N/A | #N/A | - | 10004528 | 2025-03-13 | 2026-03-13 | 70 | PO length is greater than Feasibility Length | 70 | PO Released | - |  | Not created | CWIP-76089 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-11-30 | 517 | MU | Vile Parle | 2895 | 2895 | MU-2895 | 132 | 132 | 19.0895 | 72.8403 | MUM_Route_13 | 2895_LM | MCGM | H/W | Classic Power Residency B wing | Classic Power Residency B wing,Near Big Bazar,Milan subway signal,Villeparle W | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004600 | 2025-03-19 | 2026-03-19 | 130 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76394 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-11-30 | 518 | MU | Santacruz |  | MB2250 | MU-MB2250 | 5.5 | 5.5 | 19.0866 | 72.845 | MUM_Route_13 | MB2250_LM | MCGM | H/E | Agripada Subway | Flyover No:-01,AMSP-36,Western Express Hwy, Agripada, Santacruz East, Mumbai, Maharashtra 400055 | OSR | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 519 | MU | Kandivali | MA3616 | MA3616 | MU-MA3616 | 275 | 275 | 19.2212 | 72.8461 | MUM_Route_115 | MA3616_LM | MCGM | R/C | Royal Krissh_ relo of Sony Tower | Haridas Nagar, Borivali West,Mumbai, Maharashtra 400092 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004538 | 2025-03-13 | 2026-03-13 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76073 | Received | PO Released | - |  | 0 | -280 | -
| 2026-03-31 | 520 | MU | Kandivali | MA1806 | MA1806 | MU-MA1806 | 165 | 165 | 19.2188 | 72.8471 | MUM_Route_115 | MA1806_LM | MCGM | R/C | Jai Ram_ATC | Jay Ram apartment,Saibaba Mandir Marg, Saibaba Nagar, Borivali West,Mumbai, Maharashtra 400092 | ATC | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004538 | 2025-03-13 | 2026-03-13 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76074 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-03-31 | 521 | MU | Kandivali | MA118 | MA118 | MU-MA118 | 22 | 22 | 19.2206 | 72.848 | MUM_Route_115 | MA118_LM | MCGM | R/C | Chimy Bldg 1 | Kalpana Chowk, Haridas Nagar, Borivali West, Mumbai, Maharashtra | ATC | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004538 | 2025-03-13 | 2026-03-13 | 20 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76075 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-03-31 | 522 | MU | Kandivali | 1455 | 1455 | MU-1455 | 11 | 11 | 19.2173 | 72.8483 | MUM_Route_115 | 1455_LM | MCGM | R/C | SUDARAM | SUNDARAM SOCIETY,7/65,c special bldg,geetanjali nagar,saibaba mandir road,borivali west | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004538 | 2025-03-13 | 2026-03-13 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76076 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-03-31 | 523 | MU | Kandivali | 2946 | 2946 | MU-2946 | 253 | 253 | 19.2217 | 72.8549 | MUM_Route_115 | 2946_LM | MCGM | R/C | Kavita Apartment | NATAKWALA LANE, MEGHDOOT, HARI OM NAGAR, BORIVALI, MUMBAI, MAHARASHTRA 400092 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004538 | 2025-03-13 | 2026-03-13 | 250 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76077 | RFAI Awaited | PO Released | - |  | 0 | -250 | -
| 2026-03-31 | 524 | MU | Goregaon | #N/A | MB1435 | MU-MB1435 | 110 | 110 | 19.2205 | 72.8629 | MUM_Route_115 | MB1435_LM | MCGM | R/C | Apex Multispeciality Hospitals | Plot No 262, Sector-1, Dr Babasaheb Ambedkar Rd, near Mangalmurti Hospital, Charkop Gaon, Kandivali West, Mumbai, Maharashtra 400067 | Netsol | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004538 | 2025-03-13 | 2026-03-13 | 110 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76078 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-05-31 | 525 | MU | Goregaon | 5294 | 5294 | MU-5294 | 33 | 33 | 19.1744 | 72.8613 | MUM_Route_114 | 5294_LM | MCGM | P/S | PADMAVATOMM1 | Padmavati, Gen A.K. Vaidya Road (Filmcity Road), Dindoshi, Goregaon (E), Mumbai 400063 | INDUS | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004516 | 2025-03-13 | 2026-03-13 | 30 | Site Drop by Airtel but PO Received | -3 | PO Modification WIP | - |  | Not created | CWIP-76069 | RFAI Awaited | PO Modification WIP | - |  | 0 | -30 | -
| 2026-05-31 | 526 | MU | Goregaon | MB1703 | MB1703 | MU-MB1703 | 5.5 | 5.5 | 19.1733 | 72.8677 | MUM_Route_114 | MB1703_LM | MCGM | P/S | Shivam B19 CHSL | Shivam CHSl,Sai Rd,Building No:- B-19,Near Gokuldham High School & Jr. College,Gokuldham Colony,Goregaon,Mumbai,Maharashtra:-400063. Post Office:Goregaon,Police Station:Goregaon | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004516 | 2025-03-13 | 2026-03-13 | 10 | Ok | 4.5 | PO Released | - |  | Not created | CWIP-76070 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-05-31 | 527 | MU | Goregaon | 5665 | 5665 | MU-5665 | 66 | 66 | 19.171 | 72.8712 | MUM_Route_114 | 5665_LM | MCGM | P/S | Panchashil Gokuldham CHS (Film city) | Panchsheel CHS, Behind RBI Quarters, Gokuldham, Goregaon (E), Mumbai-400063 | ATC | Route LM | Co-Build | Feasible |  | Virendra | #N/A | - | 10004516 | 2025-03-13 | 2026-03-13 | 70 | Ok | 4 | PO Released | - |  | Not created | CWIP-76071 | RFAI Awaited | PO Released | - |  | 0 | -70 | - |  |  | Site under Relocation
| 2026-12-31 | 528 | MU | Andheri | MA6116 | MA6116 | MU-MA6116 | 154 | 154 | 19.1146 | 72.8605 | MUM_Route_113 | MA61116_LM | MCGM | K/E | P-193_WE Highway to Chakala | WM-P-193_WE HIGHWAY TO CHAKALA, ANDHERI KURLA ROAD, ANDHERI EAST, MUMBAI, MAHARASHTRA.400059 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004598 | 2025-03-19 | 2026-03-19 | 150 | PO length is less than Feasibility length | -4 | PO Released | - |  | Not created | CWIP-76386 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-12-31 | 529 | MU | Andheri | MB3864 | MB3864 | MU-MB3864 | 264 | 264 | 19.1131 | 72.8624 | MUM_Route_113 | MB3864_LM | MCGM | K/E | Saroton Height | 204, Dr. Charatsingh Colony, Chakala, J B Nagar, Andheri East, Mumbai, Maharashtra 400093,post office:-Chakala,police station:-Chakala | ATC | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004598 | 2025-03-19 | 2026-03-19 | 260 | PO length is less than Feasibility length | -4 | PO Released | - |  | Not created | CWIP-76387 | RFAI Awaited | PO Released | - |  | 0 | -260 | -
| 2026-12-31 | 530 | MU | Andheri | MA6036 | MA6036 | MU-MA6036 | 154 | 154 | 19.1115 | 72.8688 | MUM_Route_113 | MA6036_LM | MCGM | K/E | P-282_Marol Naka | Andheri - Kurla Rd MIDC Industrial Estate, Bhim Nagar, Andheri East Mumbai, Maharashtra 400053 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004598 | 2025-03-19 | 2026-03-19 | 150 | PO length is less than Feasibility length | -4 | PO Released | - |  | Not created | CWIP-76388 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2025-11-30 | 531 | MU | Andheri | 5339 | 5339 | MU-5339 | 143 | 143 | 19.1424 | 72.8246 | MUM_Route_112 | 5339_LM | MCGM | K/W | SUNSWPTQOMM1 | Sun Swept, Lokhandwal Complex, Andheri (W), Mumbai, Maharashtra 400102 | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004539 | 2025-03-13 | 2026-03-13 | 140 | PO length is less than Feasibility length | -3 | PO Released | - |  | Not created | CWIP-76066 | RFAI Awaited | PO Released | - |  | 0 | -140 | -
| 2025-11-30 | 532 | MU | Andheri | 1949 | 1949 | MU-1949 | 88 | 88 | 19.1458 | 72.8236 | MUM_Route_112 | 1949_LM | MCGM | K/W | CROSSGATO | Cross gate,LOKHANDWALA COMPLEX, ANDHERI (w) | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004539 | 2025-03-13 | 2026-03-13 | 90 | Site Drop by Airtel but PO Received | 2 | PO Modification WIP | - |  | Not created | CWIP-76067 | RFAI Awaited | PO Modification WIP | - |  | 0 | -90 | -
| 2026-11-30 | 533 | MU | Santacruz | 2359 | 2359 | MU-2359 | 132 | 132 | 19.0746 | 72.8666 | MUM_Route_109 | 2359_LM | MCGM | H/E | Osia Sugandh | Osia Sugandh, Dawood Bagh Road, Near Air India Colony, Santacruz Mumbai 400098 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004597 | 2025-03-19 | 2026-03-19 | 130 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76372 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-11-30 | 534 | MU | Kalina | MB4811 | MB4811 | MU-MB4811 | 110 | 110 | 19.0743 | 72.8698 | MUM_Route_109 | MB4811_LM | MCGM | H/E | Lemon Tree | Kolivery Village, Kunchi Kurve Nagar, Kalina, Santacruz East, Mumbai, Maharashtra 400098,post office:-Kalina,police station:-Kalina | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004597 | 2025-03-19 | 2026-03-19 | 30 | PO length is less than Feasibility length | -80 | PO Released | - |  | Not created | CWIP-76373 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2026-11-30 | 535 | MU | Kalina | #N/A | MB5402 | MU-MB5402 | 220 | 220 | 19.0771 | 72.8607 | MUM_Route_109 | MB5402_LM | MCGM | H/E | Gurudwara | Gurudwara Guru Nanak Satsang Kalina (Regd.),Lotus Lane,Sunder Nagar,Kalina,Santacruz East,opp. Bombay College of Pharmacy India,Mumbai, Maharashtra 400098 | Netsol | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004597 | 2025-03-19 | 2026-03-19 | 220 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76374 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-11-30 | 536 | MU | Bandra | 5827 | 5827 | MU-5827 | 77 | 77 | 19.0703 | 72.8715 | MUM_Route_109 | 5827_LM | MCGM | H/E | MTNL_BKC | BKC MTNL, Junction of Bandra kurla road , Kurla | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004597 | 2025-03-19 | 2026-03-19 | 140 | PO length is greater than Feasibility Length | 63 | PO Released | - |  | Not created | CWIP-76375 | RFAI Awaited | PO Released | - |  | 0 | -140 | -
| 2026-05-31 | 537 | MU | Bandra | MB2378 | MB2378 | MU-MB2378 | 264 | 264 | 19.0547 | 72.8475 | MUM_Route_108 | MB2378_LM | MMRDA | - | MHADA Head Office | Madhusudan Kalelkar Rd, Gandhi Nagar, Bandra East, Mumbai, Maharashtra 400051 | Airtel Own | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004634 | 2025-03-22 | 2026-03-22 | 250 | PO length is less than Feasibility length | -14 | PO Released | - |  | Not created | CWIP-76593 | RFAI Awaited | PO Released | - |  | 0 | -250 | -
| 2026-11-30 | 538 | MU | Bhandup | MA3597 | MA3597 | MU-MA3597 | 110 | 110 | 19.1387 | 72.93 | MUM_Route_23 | MA3597_LM | MCGM | S | RIDDHI SIDDHI | (B-WING)RIDDHI-SIDDHI CHS,NEAR JANTA MARKET BUS STOP,L.B.S. ROAD,BHANDUP(W) | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76608 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-11-30 | 539 | MU | Thane |  | MB2245 | MU-MB2245 | 110 | 110 | 19.2101 | 72.9745 | MUM_Route_23 | MB2245_LM | TMC | - | Goldendyes Flyover | Goldendyes Flyover, Owner Name-Mr.Sanjay, Amsp-29, Mumbai-Agra National Highway, Majiwada Thane(W),Maharashatra 400601 | OSR | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-11-30 | 540 | MU | Chandivali |  | MB2238 | MU-MB2238 | 110 | 110 | 19.1246 | 72.8954 | MUM_Route_23 | MB2238_LM | MCGM | L | JVLR Flyover | JVLR Flyover,Pole No:-AMSP-24,Jogeshwari-Vikhroli Link Rd, IIT Area,Powai,Mumbai,Maharashtra:-400072 | OSR | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-11-30 | 541 | MU | Thane | 6056 | 6056 | MU-6056 | 110 | 110 | 19.1957 | 72.9619 | MUM_Route_23 | 6056_LM | TMC | - | Mantra Hotel | Anand Savli Residency,Behind Landmark Society, Eastern Express Hwy, kajuwadi, Thane, Maharashtra 400604 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 80 | PO length is less than Feasibility length | -30 | PO Released | - |  | Not created | CWIP-76609 | Received | PO Released | - |  | 0 | -80 | -
| 2026-11-30 | 542 | MU | Thane | MB1348 | MB1348 | MU-MB1348 | 110 | 110 | 19.2001 | 72.9629 | MUM_Route_23 | MB1348_LM | TMC | - | Silver Plaza Chsl | silver plaza,above ranka banquet, Nirmaladevi Dighe Marg, near nitin signal,wagle estate post office,wagle estate police station, Thane West, Maharashtra 400601 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-03-22 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76610 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-11-30 | 543 | MU | Thane | 2351 | 2351 | MU-2351 | 165 | 165 | 19.1859 | 72.9564 | MUM_Route_23 | 2351_LM | TMC | - | Prabhakar Bldg | Near St Lawrence School, Thane West-400604 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 50 | PO length is less than Feasibility length | -115 | PO Released | - |  | Not created | CWIP-76611 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-11-30 | 544 | MU | Mulund | 5235 | 5235 | MU-5235 | 88 | 88 | 19.1833 | 72.948 | MUM_Route_23 | 5235_LM | MCGM | T | EKTAAPTQOMM1 | Ekta Apartment - B Wing, LBS Marg, Mulund ((w), Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 50 | PO length is less than Feasibility length | -38 | PO Released | - |  | Not created | CWIP-76612 | Received | PO Released | - |  | 0 | -50 | -
| 2026-11-30 | 545 | MU | Gandhinagar | 1562 | 1562 | MU-1562 | 110 | 110 | 19.1248 | 72.9245 | MUM_Route_23 | 1562_LM | MCGM | S | MTNL Powai | MTNL Exchange,MTNL Exchange, Kanjur Marg Rd, Gandhi Nagar | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Not created | CWIP-76613 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-11-30 | 546 | MU | Bhandup | MB1179 | MB1179 | MU-MB1179 | 110 | 110 | 19.146 | 72.9357 | MUM_Route_23 | MB1179_LM | MCGM | S | Kailash Complex (Rel of 2681 Dreams Mall) | Kailas Complex, Bhandup, Valmik Nagar,Bhandup west post office,Bhandup west police station., Bhandup West, Mumbai, Maharashtra 400078 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Not created | CWIP-76614 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2026-11-30 | 547 | MU | Powai | 3023 | 3023 | MU-3023 | 110 | 110 | 19.1196 | 72.901 | MUM_Route_23 | 3023_LM | MCGM | S | JHEEL DARSHAN | Powai Vihar, Opposite Powai Lake, Powai, Mumbai-400076 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76615 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-11-30 | 548 | MU | Thane | MB3249 | MB3249 | MU-MB3249 | 69.3 | 69.3 | 19.1845 | 72.9553 | MUM_Route_23 | MB3249_LM | TMC | - | Kateelashwar Arcade | Building No:-1,Kateeleshwari Arcade,Near Mulund Tool Naka, Lal Bahadur Shastri Rd, Mulund West, Mumbai, Maharashtra 400080. Post Office:-Mulund, Police Station:- Mulund | INDUS | Route LM | Co-Build | Feasible |  | Ranjit Wadkar | #N/A | - | 10004959 | 2025-04-05 | 2026-04-05 | 90 | PO length is greater than Feasibility Length | 20.7 | PO Released | - |  | Not created | CWIP-76616 | Received | PO Released | - |  | 0 | -90 | -
| 2026-11-30 | 549 | MU | Thane | MA6156 | MA6156 | MU-MA6156 | 11 | 11 | 19.1864 | 72.9573 | MUM_Route_23 | MA6156_LM | TMC | - | Gutenberg House_ATC | MIDC FLATTED FACTORY, MIDC COLONY, RAHEJA GARDENS,WAGLE ESTATE , THANE WEST, 400082 | ATC | Route LM | Co-Build | Feasible |  | Ranjit Wadkar | #N/A | - | 10004959 | 2025-04-05 | 2026-04-05 | 80 | PO length is greater than Feasibility Length | 69 | PO Released | - |  | Not created | CWIP-76617 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2026-11-30 | 550 | MU | Gandhinagar | #N/A | 141 | MU-141 | 33 | 33 | 19.1241 | 72.91 | MUM_Route_23 | 141_LM | MCGM | S | Panchkutir FOB | Pizza Hut FOB, FOB Near Suvarna Temple, Adi Shankaracharya Road, Powai, Mumbai | Suyog | Route LM | Co-Build | Feasible |  | Manoj Ligade | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 80 | PO length is greater than Feasibility Length | 47 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76618 | Received | PO Released | - |  | 0 | -80 | -
| 2025-12-31 | 551 | MU | Ghatkoper |  | MB2230 | MU-MB2230 | 66 | 66 | 19.0845 | 72.9211 | MUM_Route_97 | MB2230_LM | MCGM | N | Ghatkopar Flyover | Flyover No:-01, AMSP-18, Mumbai-Agra National Hwy, Godrej Mangroves Area, Eastern Express Hwy, Ghatkopar East, Mumbai, Maharashtra 400075 | OSR | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2025-12-31 | 552 | MU | Ghatkoper | MA5673 | MA5673 | MU-MA5673 | 44 | 44 | 19.0883 | 72.908 | MUM_Route_97 | MA5673_LM | MCGM | N | Pillor no-434_Ghatkoper Metro | WM-PILLOR NO-434_GHATKOPER METRO, GHATKOPER RAILWAY. STATION GHATKOPER ( W), | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004672 | 2025-03-24 | 2026-03-24 | 40 | PO length is less than Feasibility length | -4 | PO Released | - |  | Not created | CWIP-76441 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2025-12-31 | 553 | MU | Bhandup | #N/A | 1536 | MU-1536 | 66 | 66 | 19.1449 | 72.9505 | MUM_Route_97 | 1536_LM | MCGM | S | BHANDUP TALAV | Bhandup FOB,Eastern express highway, Bhandup east | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 70 | Ok | 4 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76442 | RFAI Awaited | PO Released | - |  | 0 | -70 | - |  |  | Site under Relocation
| 2025-12-31 | 554 | MU | Ghatkoper | #N/A | MA4315 | MU-MA4315 | 66 | 66 | 19.0868 | 72.9188 | MUM_Route_97 | MA4315_LM | MCGM | N | BEST SITE Ghatkopar | Ghatkopar Depot, Best Colony, Ghatkopar East. Mumbai- 400075 | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 100 | PO length is greater than Feasibility Length | 34 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76443 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2025-12-31 | 555 | MU | Vikroli | #N/A | 1532 | MU-1532 | 66 | 66 | 19.1306 | 72.9418 | MUM_Route_97 | 1532_LM | MCGM | S | KNJFOB | kanjur marg FOB, KANJURGMARG FOOTOVER BRIDGE ON EASTERN EXPRESS HIGHWAY. | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 70 | Ok | 4 | PO Released-Hold by Airtel | Part of 99 |  | FF_NW1920_15543 | CWIP-76444 | RFAI Awaited | PO Released | - |  | 0 | -70 | Pending |  |  | Site under Relocation
| 2025-12-31 | 556 | MU | Vikroli |  | MB2233 | MU-MB2233 | 66 | 66 | 19.1245 | 72.9386 | MUM_Route_97 | MB2233_LM | MCGM | S | JVLR(Mid) Flyover | Flyover No:-01,AMSP-20,Mumbai - Agra National Hwy, Kannamwar Nagar II,Vikhroli, Mumbai, Maharashtra 400083 | OSR | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2025-12-31 | 557 | MU | Bhandup |  | MB2239 | MU-MB2239 | 66 | 66 | 19.1522 | 72.9552 | MUM_Route_97 | MB2239_LM | MCGM | S | GMLR Flyover | GMLR Flyover, AMSP-25,Mumbai - Agra National Hwy, Bhandup East, Mumbai, Maharashtra 400080 | OSR | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2025-12-31 | 558 | MU | Vikroli | #N/A | 2730 | MU-2730 | 66 | 66 | 19.0928 | 72.9255 | MUM_Route_97 | 2730_LM | MCGM | N | Godrej Shop FOB | Mr. Anil Kale (9869601327), Godrej Sops Vikhroli, SEP-2, B- 3,Eastern Express Hwy,Mumbai, Maharashtra 400079 MUMBAI | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 70 | Ok | 4 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76445 | RFAI Awaited | PO Released | - |  | 0 | -70 | - |  |  | Site under Relocation
| 2025-12-31 | 559 | MU | Vikroli | #N/A | MB2649 | MU-MB2649 | 220 | 220 | 19.1039 | 72.9286 | MUM_Route_97 | MB2649_LM | MCGM | N | Rajoot House | Jai Ambe Tea Shop, Vikhroli Gaothan Rd, Vikhroli Village, Pirojshanagar, Vikhroli, Mumbai, Maharashtra 400079 | Purple Soil | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 220 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76446 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2025-12-31 | 560 | MU | Ghatkoper | #N/A | MA2578 | MU-MA2578 | 11 | 11 | 19.0913 | 72.9111 | MUM_Route_97 | MA2578_LM | MCGM | N | Hasan Shaikh House Plot_Crack | SHOP NO.-12, NITYANAD NAGAR,NEAR FISH MARKET, CHIRAG NAGAR, GHATKOPAR WEST, MUMBAI,400086 | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004672 | 2025-03-24 | 2026-03-24 | 40 | PO length is greater than Feasibility Length | 29 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76447 | RFAI Awaited | PO Released | - |  | 0 | -40 | -
| 2026-02-28 | 561 | MU | Vikroli | #N/A | MA5223 | MU-MA5223 | 275 | 275 | 19.1016 | 72.919 | MUM_Route_25 | MA5223_LM | MCGM | N | Vikhroli | BMC Colony Lal Bahadur Shastri Marg Park Site Road Near Vikhroli Bus Depot Vikhroli West Mumbai Maharashtra- 400079 MUMBAI | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004656 | 2025-03-24 | 2026-03-24 | 200 | PO length is less than Feasibility length | -75 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76399 | RFAI Awaited | PO Released | - |  | 0 | -200 | -
| 2026-02-28 | 562 | MU | Vikroli | #N/A | MB2236 | MU-MB2236 | 77 | 77 | 19.1092 | 72.9324 | MUM_Route_25 | MB2236_LM | MCGM | S | Vikhroli Flyover | Vikhroli Flyover, Owner Name-Mr.Sanjay, Pole No.Amsp-22, Near Godrej Creekside Colony, Vikhroli, Mumbai, Maharashtra 400083 | OSR | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004651 | 2025-03-24 | 2026-03-24 | 80 | Site Drop by Airtel but PO Received | 3 | PO Modification WIP | - |  | Not created | - | - | PO Modification WIP | - |  | 0 | -80 | -
| 2026-02-28 | 563 | MU | Powai | MA2131 | MA2131 | MU-MA2131 | 55 | 55 | 19.114 | 72.9063 | MUM_Route_25 | MA2131_LM | MCGM | S | Richmond | RICHMOND, CLIFF AVE RD,HIRANANDANI GARDENS, POWAI,MUMBAI, MAHARASHTRA 400076 | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004651 | 2025-03-24 | 2026-03-24 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76417 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-02-28 | 564 | MU | Vikroli | 5769 | 5769 | MU-5769 | 280 | 0 | 19.1083 | 72.928238° | MUM_Route_25 | 5769_LM | MCGM | N | GODREJ BLDG NO.X-44 | GODREJ BLDG NOX-44, VIKHROLI(E) | Airtel Own | Route LM | Co-Build | De-scope |  | Swapnil Salvi | Yogesh Deshpande | - | 10004651 | 2025-03-24 | 2026-03-24 | 280 | PO length is greater than Feasibility Length | 280 | PO Released | - |  | Not created | CWIP-76418 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-02-28 | 565 | MU | Vikroli | 2263 | 2263 | MU-2263 | 165 | 165 | 19.1142 | 72.9178 | MUM_Route_25 | 2263_LM | MCGM | N | CHOICSOLIFI1 | Choice Solutions, F-137, Vikhroli (w) | Airtel Own | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004651 | 2025-03-24 | 2026-03-24 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76419 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-02-28 | 566 | MU | Vikroli | 999 | 999 | MU-999 | 121 | 121 | 19.1195 | 72.9247 | MUM_Route_117 | 999_LM | MCGM | S | Vardhaman Complex | Vardhman complex,Opp. 247 park,LBS Road, Vikhroli W. | INDUS | Route LM | Co-Build | Feasible |  | Hari Yadav | Satish Singh | - | 10004590 | 2025-03-19 | 2026-03-19 | 120 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76391 | RFAI Awaited | PO Released | - |  | 0 | -120 | - |  |  | Site under Relocation
| 2026-10-31 | 567 | MU | Chandivali | #N/A | MA4248 | MU-MA4248 | 264 | 264 | 19.1076 | 72.8949 | MUM_Route_38 | MA4248_LM | MCGM | L | chaudhari plot | GBT-CHAUDHARI PLOT , GILBERT COMPOUND, IMAM AHMAD RAZA MARG, KHERANI ROAD, CHANDIVALI POWAI, MUMBAI, MAHARASHTRA-400072 | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004674 | 2025-03-24 | 2026-03-24 | 250 | PO length is less than Feasibility length | -14 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76432 | RFAI Awaited | PO Released | - |  | 0 | -250 | -
| 2026-10-31 | 568 | MU | Chandivali | 3075 | 3075 | MU-3075 | 187 | 187 | 19.1062 | 72.892 | MUM_Route_38 | 3075_LM | MCGM | L | Gurudwara Open Plot | Kharani road Jose nagar Kherani Rd, Asalpha Mumbai, Maharashtra 400072 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004674 | 2025-03-24 | 2026-03-24 | 260 | PO length is greater than Feasibility Length | 73 | PO Released | - |  | Not created | CWIP-76433 | RFAI Awaited | PO Released | - |  | 0 | -260 | -
| 2026-10-31 | 569 | MU | Chandivali | MA5557 | MA5557 | MU-MA5557 | 176 | 176 | 19.1048 | 72.8858 | MUM_Route_38 | MA5557_LM | MCGM | L | p 306 | P 306, NEAR SAKI NAKA ANDHERI MUMBAI, MAHARASHTRA. 400072 | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004674 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -26 | PO Released | - |  | Not created | CWIP-76434 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-10-31 | 570 | MU | Chandivali | #N/A | MA4846 | MU-MA4846 | 121 | 121 | 19.1043 | 72.8948 | MUM_Route_38 | MA4846_LM | MCGM | L | Altaf Khan Gala_Suyog | PEREIRA WADI, ASALPHA,POST OFFICE- SAKI VIHAR ROAD, POLICE STATION- SAKINAKA, CITY-GHATKOPAR, DISTRICT- MUMBAI, STATE-MAHARASHTRA, | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004674 | 2025-03-24 | 2026-03-24 | 120 | PO length is less than Feasibility length | -1 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76435 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2026-10-31 | 571 | MU | Chandivali | MB1103 | MB1103 | MU-MB1103 | 154 | 154 | 19.1092 | 72.9025 | MUM_Route_38 | MB1103_LM | MCGM | L | Surya Kiran CHSL | Bldg No:-26,Sangrsh Nagar,Chandivali,Near lord shiva tepmle,Andheri East,Mumbai,Maharashtra 400072, Police Station:Chandivali | ATC | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004674 | 2025-03-24 | 2026-03-24 | 70 | PO length is less than Feasibility length | -84 | PO Released | - |  | Not created | CWIP-76436 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-10-31 | 572 | MU | Ghatkoper | MB1882 | MB1882 | MU-MB1882 | 55 | 55 | 19.0871 | 72.9082 | MUM_Route_19 | MB1882_LM | MCGM | N | Lakshmi Arcade | Lakshmi Arcade, Owner Name-Mr.Dhaval Patel, Building No.01, New Laxmi Shopping Centre, Hd Road, Ghatkopar, Post Office-Ghatkopar, Police Station-Ghatkopar,Mumbai | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76405 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-10-31 | 573 | MU | Ghatkoper | MA1165 | MA1165 | MU-MA1165 | 286.72 | 0 | 19.0774 | 72.901 | MUM_Route_19 | MA1165_LM | MCGM | N | Karm Sankalp | OPPOSITE SOMAIYA COLLEGE, , 7TH RAJAWADI ROAD, RAJAWADI COLONY, VIDYAVIHAR,GHATKOPAR EAST,MUMBAI 400077 | INDUS | Route LM | Co-Build | De-scope |  | Ranjit Wadkar | #N/A | - | 10004663 | 2025-03-24 | 2026-03-24 | 290 | PO length is greater than Feasibility Length | 290 | PO Released | - |  | Not created | CWIP-76406 | RFAI Awaited | PO Released | - |  | 0 | -290 | -
| 2026-10-31 | 574 | MU | Ghatkoper | MA2586 | MA2586 | MU-MA2586 | 110 | 110 | 19.0687 | 72.8999 | MUM_Route_19 | MA2586_LM | MCGM | M/W | Krushal Commercial Complex/Riddhi Siddhi | ROAD NUMBER 13, PATELWADI, TILAK NAGAR, CHEMBUR WEST,MUMBAI,MAHARASHTRA PINCODE-400089 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76407 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-10-31 | 575 | MU | Ghatkoper | MA3996 | MA3996 | MU-MA3996 | 275 | 275 | 19.0807 | 72.9026 | MUM_Route_19 | MA3996_LM | MCGM | M/W | Haveli Apt_ATC | Haveli Apartment,Kailash regency, Rajawadi colony, Ghatkopar East,Mumbai,Maharastra 400077,Police Station: Ghatkopar Police Station, Post office: Ghatkopar Post Offife, Tel: Kurla, Dist: Mumbai MUMBAI | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76408 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-10-31 | 576 | MU | Ghatkoper | #N/A | 2731 | MU-2731 | 220 | 220 | 19.0648 | 72.9 | MUM_Route_19 | 2731_LM | MCGM | M/W | Gulshan Baug | Gulshan masjid p lokhande marg chembur west | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 220 | Ok | 0 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76409 | RFAI Awaited | PO Released | - |  | 0 | -220 | - |  |  | Site under Relocation
| 2026-10-31 | 577 | MU | Ghatkoper | #N/A | MB2224 | MU-MB2224 | 55 | 55 | 19.0611 | 72.8976 | MUM_Route_19 | MB2224_LM | MCGM | M/W | Chembur Monorail | Metro Station Chembur, Chembur, Mumbai, Maharashtra 400071 post and police station-chembur | Suyog | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 60 | Ok | 5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76410 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-10-31 | 578 | MU | Ghatkoper | MB2462 | MB2462 | MU-MB2462 | 77 | 77 | 19.0732 | 72.903 | MUM_Route_19 | MB2462_LM | MCGM | M/W | Waman CHS | SITE ID-MB2462,SITE NAME-WAMAN CHS,TOCO ID-(IN-3257520)CHEMBUR | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 80 | Ok | 3 | PO Released | - |  | Not created | CWIP-76411 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2026-10-31 | 579 | MU | Ghatkoper | 6359 | 6359 | MU-6359 | 132 | 132 | 19.0591 | 72.8973 | MUM_Route_19 | 6359_LM | MCGM | M/W | Jagdish Bldg | Jagdish BldgPlot No 185, 15th road, Opp Nirmal Harbai hair clinic Clse to R C Marg, Chembur,Mumbai,Maharashtra 400071 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 130 | PO length is less than Feasibility length | -2 | PO Released | - |  | Not created | CWIP-76412 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-10-31 | 580 | MU | Ghatkoper | #N/A | MB1595 | MU-MB1595 | 132 | 132 | 19.0626 | 72.8991 | MUM_Route_19 | MB1595_LM | MCGM | M/W | Natraj Cinema | Natraj Cinema Building, 1st Rd, Chembur West, Chembur Gaothan, Chembur, Mumbai, Maharashtra 400071 | Netsol | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 130 | PO length is less than Feasibility length | -2 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76413 | RFAI Awaited | PO Released | - |  | 0 | -130 | -
| 2026-10-31 | 581 | MU | Ghatkoper | 4213 | 4213 | MU-4213 | 198 | 198 | 19.0571 | 72.896 | MUM_Route_19 | 4213_LM | MCGM | M/W | ARIHANNTO | ARIHANT ,Road No. 10, R C Marg, Nr. Joy Hospital, Chembur, Mumbai-400071 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 150 | PO length is less than Feasibility length | -48 | PO Released | - |  | Not created | CWIP-76414 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-10-31 | 582 | MU | Ghatkoper | 4506 | 4506 | MU-4506 | 77 | 77 | 19.0854 | 72.9067 | MUM_Route_19 | 4506_LM | MCGM | N | JEEVANQ | Jeevan Jyot Hospital,Ghatkopar(W), Mumbai--400072 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004663 | 2025-03-24 | 2026-03-24 | 80 | Ok | 3 | PO Released | - |  | Not created | CWIP-76415 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2026-05-31 | 583 | MU | Kurla | 3170 | 3170 | MU-3170 | 220 | 220 | 19.0727 | 72.8804 | MUM_Route_110 | 3170_LM | MCGM | L | White House Bld. No. 3 | Buddh Colony, S.G.Barve Marg, Kurla (W.), Mumbai - 400 070 | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 220 | Ok | 0 | PO Released | - |  | Not created | CWIP-76377 | Received | PO Released | - |  | 0 | -220 | -
| 2026-05-31 | 584 | MU | Kurla | 4670 | 4670 | MU-4670 | 165 | 165 | 19.0721 | 72.8834 | MUM_Route_110 | 4670_LM | MCGM | L | MIGCLONYO | MIG Colony,Sangam Co-op Hsg Soc Ltd,Vinobabhave Nagar,Kurla(W),Mumbai-400070 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 150 | PO length is less than Feasibility length | -15 | PO Released | - |  | Not created | CWIP-76378 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-05-31 | 585 | MU | Kurla |  | 6518 | MU-6518 | 253 | 253 | 19.0583 | 72.8887 | MUM_Route_110 | 6518_LM | MCGM | M/W | NALANDA | Nalanda Kurla,Kurla Signal,Chembur(W)Mumbai 400071 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-05-31 | 586 | MU | Chembur | MA2281 | MA2281 | MU-MA2281 | 165 | 165 | 19.0558 | 72.8894 | MUM_Route_110 | MA2281_LM | MCGM | M/W | sumati Gujar Hall | PLOT NO 1213, SWASTIK PARK, NEAR MANGAL ANAND HOSPITAL, OPP SWASTIK CHEMBERS CHEMBUR(E) | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76379 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-05-31 | 587 | MU | Kurla | 4070 | 4070 | MU-4070 | 220 | 220 | 19.0702 | 72.8842 | MUM_Route_110 | 4070_LM | MCGM | L | MUBARAKQOF | Mubarak Complex,VINOBHA BHAVE NAGAR, NEXT TO LIG COLONY, KURLA(W) | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 220 | Ok | 0 | PO Released | - |  | Not created | CWIP-76380 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-05-31 | 588 | MU | Kurla | MA5500 | MA5500 | MU-MA5500 | 165 | 165 | 19.0739 | 72.882 | MUM_Route_110 | MA5500_LM | MCGM | L | Anjuman Khairul Momineen Masjid | , NEAR SIDHPURA INDUSTRIAL ESTATE, SCLR, KURLA WEST, KURLA, MUMBAI, MAHARASHTRA 400070 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76381 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-05-31 | 589 | MU | Kurla | MA3417 | MA3417 | MU-MA3417 | 110 | 110 | 19.0698 | 72.8775 | MUM_Route_110 | MA3417_LM | MCGM | L | Haji Najar Ali Imam bargah | 497 NEXT TO MANSI APARTMENTS, NEW, SWADESHI MILLS RD,KURLA WEST,400070 | Airtel Own | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004593 | 2025-03-19 | 2026-03-19 | 140 | PO length is greater than Feasibility Length | 30 | PO Released | - |  | Not created | CWIP-76382 | RFAI Awaited | PO Released | - |  | 0 | -140 | -
| 2026-03-31 | 590 | MU | Lalbaug |  | 1029 | MU-1029 | 161.7 | 161.7 | 18.9909 | 72.8364 | MUM_Route_10 | 1029_LM | MCGM | F/S | LALBAUGRO | Shri Ganesh Nagar, Lalbaug | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 591 | MU | Lalbaug | MA6540 | MA6540 | MU-MA6540 | 16.5 | 16.5 | 18.9876 | 72.8354 | MUM_Route_10 | MA6540_LM | MCGM | E | Phanse Building(Akolawala Building) | VISHNU GANESH PINGLE MARG, CHINCHPOKLI, MUMBAI, MAHARASHTRA 400011 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 270 | PO length is greater than Feasibility Length | 253.5 | PO Released | Part of 99 |  | FF_NW2122_785501 | CWIP-76568 | RFAI Awaited | PO Released | - | Shrikant Chavan | 304 | 34 | Pending
| 2026-03-31 | 592 | MU | Fort | 3054 | 3054 | MU-3054 | 144.1 | 144.1 | 18.937 | 72.8378 | MUM_Route_10 | 3054_LM | MCGM | A | KRISHNA NIWAS | Krishna Niwas,Shahid Bhagat Singh Rd,Fort,Mumbai-400001 | ATC | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 30 | PO length is less than Feasibility length | -114.1 | PO Released | Part of 99 | Received | FF_NW1920_15468 | CWIP-76569 | RFAI Awaited | PO Released | 960574 | Shrikant Chavan | 20 | -10 | -
| 2026-03-31 | 593 | MU | Lalbaug | 5256 | 5256 | MU-5256 | 33 | 33 | 18.9926 | 72.8372 | MUM_Route_10 | 5256_LM | MCGM | F/S | Hilla Tower | DRSS Rao Road,Bharat Rice Mills Compound, Lal Baug, Parel 400012 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 150 | PO length is greater than Feasibility Length | 117 | PO Released | Part of 99 |  | FF_NW1920_15031 | CWIP-76570 | RFAI Awaited | PO Released | - |  | 229 | 79 | Pending
| 2026-03-31 | 594 | MU | Masjid Bundar | 5055 | 5055 | MU-5055 | 5.5 | 5.5 | 18.9502 | 72.8348 | MUM_Route_10 | 5055_LM | MCGM | B | MOMIRWLAOMM1 | Mahatma Jotiba Phule Mandi, Mohammedali Rd, Masjid Bunder, Mumbai-400003 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 10 | Ok | 4.5 | PO Released | Part of 99 |  | FF_NW1920_14448 | CWIP-76571 | RFAI Awaited | PO Released | - |  | 69 | 59 | LA Considered
| 2026-03-31 | 595 | MU | Masjid Bundar |  | 5606 | MU-5606 | 44 | 44 | 18.9528 | 72.8342 | MUM_Route_10 | 5606_LM | MCGM | B | Commercial Chamber | Commercial Chamber Yusuf Meher Ali Rd, Masjid Bandar West, Masjid Bandar Mumbai, Maharashtra 400003 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 596 | MU | Masjid Bundar | MA1059 | MA1059 | MU-MA1059 | 77 | 77 | 18.9568 | 72.8323 | MUM_Route_10 | MA1059_LM | MCGM | B | Ibrahim rehmantula | FAJANDAR BUILDING, MOHAMMED ALI RD, AJMER, BHENDI BAZAAR, BHULESHWAR, MUMBAI, MAHARASHTRA 400003 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 80 | Ok | 3 | PO Released | Part of 99 |  | FF_NW2122_785502 | CWIP-76572 | RFAI Awaited | PO Released | - |  | 51 | -29 | -
| 2026-03-31 | 597 | MU | Masjid Bundar | 5029 | 5029 | MU-5029 | 66 | 66 | 18.9552 | 72.8323 | MUM_Route_10 | 5029_LM | MCGM | B | SAIFEESCOF | Saifee High School Mandvi, Mumbai-4000003 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 70 | Ok | 4 | PO Released | Part of 99 |  | FF_NW1920_14443 | CWIP-76573 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-03-31 | 598 | MU | Fort | MB3135 | MB3135 | MU-MB3135 | 134.2 | 134.2 | 18.9391 | 72.8384 | MUM_Route_10 | MB3135_LM | MCGM | A | Friends Union | Lexcorp Towers, Frere Rd, Indira Docks, Mumbai Port Trust, CST, Mumbai, Maharashtra 400001,post office:-Mazgaon,police station:-Mazgaon | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 130 | PO length is less than Feasibility length | -4.2 | PO Released | Part of 99 |  | FF_NW2122_785503 | CWIP-76574 | RFAI Awaited | PO Released | - | Shrikant Chavan | 28 | -102 | -
| 2026-03-31 | 599 | MU | Mumbai Central | 5451 | 5451 | MU-5451 | 110 | 110 | 18.9685 | 72.8316 | MUM_Route_10 | 5451_LM | MCGM | E | Rehnabad CHSL | Spence Road, Near Saboo Siddiquei College, Byculla (W.), Mumbai | ATC | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 120 | PO length is greater than Feasibility Length | 10 | PO Released | Part of 99 |  | FF_NW2122_785504 | CWIP-76575 | RFAI Awaited | PO Released | - |  | 83 | -37 | - |  |  | Site under Relocation
| 2026-03-31 | 600 | MU | Nagpada | 2763 | 2763 | MU-2763 | 88 | 88 | 18.9711 | 72.8322 | MUM_Route_10 | 2763_LM | MCGM | E | BYCULLA HOUSE | Byculla House,Byculla House CHSL, Mastana Shopping Centre, Byculla Bridge, Mumbai - 400008 | ATC | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 50 | PO length is less than Feasibility length | -38 | PO Released | Part of 99 |  | FF_NW1920_14940 | CWIP-76576 | RFAI Awaited | PO Released | - |  | 56 | 6 | LA Considered
| 2026-03-31 | 601 | MU | Masjid Bundar | 4847 | 4847 | MU-4847 | 5.5 | 5.5 | 18.9595 | 72.832 | MUM_Route_10 | 4847_LM | MCGM | B | MAMAJIHSOF | Mamaji House,Above Hakimi Pharmacy,Bhendi Bazar,E R Road,Mumbai-400003 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 10 | Ok | 4.5 | PO Released | Part of 99 |  | FF_NW1920_14425 | CWIP-76577 | RFAI Awaited | PO Released | - |  | 0 | -10 | Pending
| 2026-03-31 | 602 | MU | Nagpada |  | MB2225 | MU-MB2225 | 49.5 | 49.5 | 18.9619 | 72.8319 | MUM_Route_10 | MB2225_LM | MCGM | E | J.J. Hospital Flyover | J.J.Flyover,Pole No:-AMSP-13,Sir J.J.Flyover, J.J. Junction,Near J.J. Hospital,Nagpada,Mumbai,Maharashtra 400008 | OSR | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-03-31 | 603 | MU | Fort | MA6295 | MA6295 | MU-MA6295 | 22 | 22 | 18.9357 | 72.8368 | MUM_Route_10 | MA6295_LM | MCGM | A | Hotel Popular palace | 100, MINT RD, BORABAZAR PRECINCT, BALLARD ESTATE, FORT, DISTRICT-MUMBAI, STATE- MAHARASHTRA, PINCODE- 400001 | ATC | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 30 | Ok | 8 | PO Released | Part of 99 | Received | FF_NW2122_784629 | CWIP-76578 | RFAI Awaited | PO Released | 760495 | Shrikant Chavan | 20 | -10 | -
| 2026-03-31 | 604 | MU | Fort | MA4226 | MA4226 | MU-MA4226 | 22 | 22 | 18.9379 | 72.8374 | MUM_Route_10 | MA4226_LM | MCGM | A | Hira Building, | HIRA BUILDING, , BALLARD ESTATE, FORT | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 20 | PO length is less than Feasibility length | -2 | PO Released | Part of 99 | Received | FF_NW1920_15271 | CWIP-76579 | RFAI Awaited | PO Released | 956303 | Shrikant Chavan | 8 | -12 | -
| 2026-03-31 | 605 | MU | Byculla | MA1885 | MA1885 | MU-MA1885 | 44 | 44 | 18.9755 | 72.8317 | MUM_Route_10 | MA1885_LM | MCGM | E | GULMOHAR _ Rel Porbunderwala House | GULMOHAR near Porbandarwala house, opposite of rly. Station Byculla(W), Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 40 | PO length is less than Feasibility length | -4 | PO Released | Part of 99 |  | FF_NW2122_785505 | CWIP-76580 | RFAI Awaited | PO Released | 208251 | Shrikant Chavan | 3 | -37 | -
| 2026-03-31 | 606 | MU | Masjid Bundar | 4859 | 4859 | MU-4859 | 132 | 132 | 18.9515 | 72.8335 | MUM_Route_10 | 4859_LM | MCGM | B | PLOTN155OF | PLOT NO 155,NARAYAN DHURI STREET,MUMBAI-400003 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004641 | 2025-03-22 | 2026-03-22 | 50 | PO length is less than Feasibility length | -82 | PO Released-Not Feasible | Part of 99 |  | FF_NW1920_15661 | CWIP-76581 | RFAI Awaited | PO Released | - |  | 127 | 77 | -
| 2026-03-31 | 607 | MU | Mazgaon |  | MB3948 | MU-MB3948 | 104.5 | 104.5 | 18.9494 | 72.84 | MUM_Route_10 | MB3948_LM | MCGM | B | Tata Power Company Carnac | The Tata Power Company Block-3, Sant Tukaram Rd, Masjid Bandar East, Masjid Bandar, Mumbai, Maharashtra 400009 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2025-12-31 | 608 | MU | Fort | 3090 | 3090 | MU-3090 | 11 | 11 | 18.9315 | 72.8311 | MUM_Route_99 | 3090_LM | MCGM | A | HSBCQQQQIMI1 | HSBC Main Bldg, Fort, Churchgate-400032 | Airtel Own | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 10 | PO length is less than Feasibility length | -1 | PO Released | - |  | Not created | CWIP-76670 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2025-12-31 | 609 | MU | Fort | MB6015 | MB6015 | MU-MB6015 | 66 | 66 | 18.9305 | 72.8265 | MUM_Route_99 | MB6015_LM | MCGM | A | Prem Court | Prem Court, Jamshedji Tata Road, Churchgate, Mumbai, Maharashtra 400020 | Indus | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 30 | PO length is less than Feasibility length | -36 | PO Released | - |  | Not created | CWIP-76671 | RFAI Awaited | PO Released | - |  | 0 | -30 | -
| 2025-12-31 | 610 | MU | Fort | #N/A | MB6017 | MU-MB6017 | 22 | 22 | 18.9297 | 72.8262 | MUM_Route_99 | MB6017_LM | MCGM | A | Ramon House (HDFC) | Churchgate, Mumbai, Maharashtra 400020 | Crest Digitel | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 70 | PO length is greater than Feasibility Length | 48 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76672 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2025-12-31 | 611 | MU | Churchgate | 907 | 907 | MU-907 | 99 | 99 | 18.9288 | 72.8276 | MUM_Route_99 | 907_LM | MCGM | A | HDFC - H.L House | Backbay Reclamation Road, Churchgate-400001 | Airtel Own | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 100 | Ok | 1 | PO Released | - |  | Not created | CWIP-76673 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2025-12-31 | 612 | MU | Churchgate | 3310 | 3310 | MU-3310 | 16.5 | 16.5 | 18.9332 | 72.8308 | MUM_Route_99 | 3310_LM | MCGM | A | MTNL FOUNTAIN | MTNL Fountain,near VSNL , hutatma chauk, fort,Mumbai. | ATC | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004624 | 2025-03-22 | 2026-03-22 | 120 | PO length is greater than Feasibility Length | 103.5 | PO Released | - |  | Not created | CWIP-76674 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2025-12-31 | 613 | MU | Churchgate |  | MB1504 | MU-MB1504 | 179.2 | 179.2 | 18.9311 | 72.8232 | MUM_Route_99 | MB1504_LM | MCGM | A | Hotel Marine Plaza | Hotel Marine, N S C Bose Road, Nr Brabourne Stadium, Nariman Point, Mumbai | Airtel Own | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | PO Pending |  | PR In Process | - |  | Not created | - | RFAI Awaited | PR In Process | - |  | 0 | 0 | -
| 2026-01-31 | 614 | MU | Dadar | 6239 | 6239 | MU-6239 | 55 | 55 | 19.0149 | 72.8274 | MUM_Route_8 | 6239_LM | MCGM | G/S | Prithvi Emperor | Prithvi Appt,PRITHVI EMPEROR situated at New Prabhadevi Road, Prabhadevi, Mumbai – 400 025 | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76641 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 615 | MU | Worli | MA5269 | MA5269 | MU-MA5269 | 165 | 165 | 19.0083 | 72.8212 | MUM_Route_8 | MA5269_LM | MCGM | G/S | TV Industrial Estate (Rel of National Cycle) | T. V. Industrial Estate , Plot No.-112, Hind Cycle Marg, Hanuman Nagar, City-Worli, Worli Post Office, Worli Police Station, Tehsil-Andheri, Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76642 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-01-31 | 616 | MU | Cumballa Hill | 810 | 810 | MU-810 | 232.96 | 0 | 18.9688 | 72.8076 | MUM_Route_8 | 810_LM | MCGM | D | Avantika bldg no. 1 | Peddar Road, Mumbai | INDUS | Route LM | Co-Build | De-scope |  | Vaijesh Patil | Prem Verma | - | 10004619 | 2025-03-22 | 2026-03-22 | 230 | PO length is greater than Feasibility Length | 230 | PO Released | - |  | Not created | CWIP-76643 | RFAI Awaited | PO Released | - |  | 0 | -230 | -
| 2026-01-31 | 617 | MU | Mahalaxmi | 3058 | 3058 | MU-3058 | 110 | 110 | 18.9848 | 72.8157 | MUM_Route_8 | 3058_LM | MCGM | G/S | NSCIQQQQIMI1 | Nehru Science Centre, Nr Mahalaxmi Race Course, Lala Lajpath Marg, Worli- | Airtel Own | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 70 | PO Pending |  | PO Released | - |  | Not created | #N/A | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-01-31 | 618 | MU | Mahalaxmi | MA742 | MA742 | MU-MA742 | 275 | 275 | 18.9768 | 72.8082 | MUM_Route_8 | MA742_LM | MCGM | D | Swaminarayan Mandir | MANINAGAR SHRI SWAMINARAYAN GADI SANSTHAN, SHRI MUKTJEEVAN SWAMIBAPA DHARMSHALA, BHULABHAI DESAI ROAD, MAHALAXMI MUMBAI, MAHARASHTRA-400026. | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76644 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-01-31 | 619 | MU | Grant Rd | MA256 | MA256 | MU-MA256 | 110 | 110 | 18.9648 | 72.8092 | MUM_Route_8 | MA256_LM | MCGM | D | Pushpak Apt(Indrasan CHSL) | ALTAMOUNT ROAD GOWALIA TANK, TARDEO, MUMBAI, MAHARASHTRA 400026 | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76645 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-01-31 | 620 | MU | Grant Rd | 4545 | 4545 | MU-4545 | 275 | 275 | 18.9573 | 72.8143 | MUM_Route_8 | 4545_LM | MCGM | D | RAJDHAN | Rajdhani Bldg,Raghuwadi Frenesh Bridge,Mumbai- 400007 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76646 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-01-31 | 621 | MU | Grant Rd | MB5997 | MB5997 | MU-MB5997 | 55 | 55 | 18.9419 | 72.8266 | MUM_Route_8 | MB5997_LM | MCGM | A | QUEENS CHAMBERS | QUEENS CHAMBERS, MAHARSHI KARVE RD, DHOBI TALAO, NEW MARINE LINES, MARINE LINES, MUMBAI,POST OFFICE:-MARINE LINES,POLICE STATION:-MARINE LINES | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76647 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 622 | MU | Grant Rd | 6102 | 6102 | MU-6102 | 110 | 110 | 18.9549 | 72.8146 | MUM_Route_8 | 6102_LM | MCGM | D | PRAKDEV | Prakash dev CHS Opp Birla Sports Center, Opp Chowpaty , above_café Coffe day Charni Road ( W), Mumbai, Maharashtra 400007 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76648 | RFAI Awaited | PO Released | - |  | 0 | -110 | -
| 2026-01-31 | 623 | MU | Worli | MA3668 | MA3668 | MU-MA3668 | 110 | 110 | 18.999 | 72.817 | MUM_Route_8 | MA3668_LM | MCGM | G/S | TULSI VIHAR CHS | WORLI NAKA,PREM NAGAR,A.B. ROAD,WORLI,MUMBAI | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 50 | PO length is less than Feasibility length | -60 | PO Released | - |  | Not created | CWIP-76649 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2025-08-31 | 624 | MU | Dharavi | 5604 | 5604 | MU-5604 | 220 | 220 | 19.0497 | 72.8567 | MUM_Route_55 | 5604_LM | MCGM | G/N | SHPNO114OF | shop no.114,shop no.114-Dharavi-14371 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 70 | PO length is less than Feasibility length | -150 | PO Released | - |  | Not created | CWIP-76628 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2025-08-31 | 625 | MU | Sion | 4913 | 4913 | MU-4913 | 275 | 275 | 19.0524 | 72.8658 | MUM_Route_55 | 4913_LM | MCGM | L | ASHAPURAOF | Ashapura General Stores,Gmn 79/85,Near Shiv Mandir,Prem Nagar,Lbs Road,Sion(W),Mumbai-400017 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 50 | PO length is less than Feasibility length | -225 | PO Released | - |  | Not created | CWIP-76629 | RFAI Awaited | PO Released | - |  | 0 | -50 | -
| 2025-08-31 | 626 | MU | Dharavi | MA4466 | MA4466 | MU-MA4466 | 55 | 55 | 19.0459 | 72.8507 | MUM_Route_55 | MA4466_LM | MCGM | G/N | Nehru Nagar | Nehru Nagar CHS,Dharavi T juction, Mahim E | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76630 | Received | PO Released | - |  | 0 | -60 | -
| 2025-08-31 | 627 | MU | Lower Parel | 4932 | 4932 | MU-4932 | 11 | 11 | 19.0016 | 72.8301 | MUM_Route_55 | 4932_LM | MCGM | G/S | Vishwa Kamal | Kashinath Dhuru Compound,Senapati Bapat Marg,Lower ParelMumbai-400013 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004628 | 2025-03-22 | 2026-03-22 | 120 | PO length is greater than Feasibility Length | 109 | PO Released | - |  | Not created | CWIP-76631 | RFAI Awaited | PO Released | - |  | 0 | -120 | -
| 2025-08-31 | 628 | MU | Lower Parel | #N/A | MA728 | MU-MA728 | 176 | 176 | 19.0033 | 72.8304 | MUM_Route_55 | MA728_LM | MCGM | G/S | Saksham CHSL | SENAPATI BAPAT MARG, OPPSITE KAMLA MILLS COMPOUND, JOSHI MARG ,LOWER PAREL,MUMBAI,400013 | Netsol | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004628 | 2025-03-22 | 2026-03-22 | 100 | PO length is less than Feasibility length | -76 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76632 | RFAI Awaited | PO Released | - |  | 0 | -100 | -
| 2025-08-31 | 629 | MU | Dadar |  | 4929 | MU-4929 | 110 | 110 | 19.0208 | 72.8423 | MUM_Route_55 | 4929_LM | MCGM | G/N | Datey Bhavan | DATEY BHAVAN, DADAR WEST, DADAR, MUMBAI, MAHARASHTRA 400028 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2025-08-31 | 630 | MU | Dadar | 358 | 358 | MU-358 | 33 | 33 | 19.0242 | 72.8436 | MUM_Route_55 | 358_LM | MCGM | G/N | INDRAYANI COMPLEX | Indrayani Complex CHS, Plot No.24, J.K. Sawant Marg, Dadar(W) Mumbai-400028 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 160 | PO length is greater than Feasibility Length | 127 | PO Released | - |  | Not created | CWIP-76633 | RFAI Awaited | PO Released | - |  | 0 | -160 | -
| 2025-08-31 | 631 | MU | Dadar | 3120 | 3120 | MU-3120 | 110 | 110 | 19.0271 | 72.8429 | MUM_Route_55 | 3120_LM | MCGM | G/N | Yashwant natya shala | Yashwant Natya Shala,Manmala Tank Road, Matunga - Mahim, Mumbai- 400016 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 110 | Ok | 0 | PO Released | - |  | Not created | CWIP-76634 | RFAI Awaited | PO Released | - |  | 0 | -110 | - |  |  | Site under Relocation
| 2025-08-31 | 632 | MU | Mahim | 3258 | 3258 | MU-3258 | 26.4 | 26.4 | 19.0415 | 72.845 | MUM_Route_55 | 3258_LM | MCGM | G/N | OLV&PS CHSL | Near Mahim Sation,Mahim West,Mumbai, Maharashtra 400016 | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004628 | 2025-03-22 | 2026-03-22 | 160 | PO length is greater than Feasibility Length | 133.6 | PO Released | - |  | Not created | CWIP-76635 | RFAI Awaited | PO Released | - |  | 0 | -160 | -
| 2025-08-31 | 633 | MU | Mahim | 3177 | 3177 | MU-3177 | 11 | 11 | 19.0449 | 72.8453 | MUM_Route_55 | 3177_LM | MCGM | G/N | KUMEL AHMED HOUSE | Kumel Ahmad ,Mahim Sion link Road,Mahim(E).Mum 17. | ATC | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 20 | Ok | 9 | PO Released | - |  | Not created | CWIP-76636 | Received | PO Released | - |  | 0 | -20 | -
| 2025-08-31 | 634 | MU | Mahim | #N/A | MA2383 | MU-MA2383 | 165 | 165 | 19.0447 | 72.8471 | MUM_Route_55 | MA2383_LM | MCGM | G/N | Jalil Compound | DIAMOND PACKAGING, UNIT 2, MAHIM SION LINK RD JALIL, ASHOK MILL COMPOUND RD, KALA QILA, DHARAVI, MUMBAI, STATE-MAHARASHTRA, PINCODE- 400017 | Suyog | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004628 | 2025-03-22 | 2026-03-22 | 170 | Ok | 5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76637 | Received | PO Released | - |  | 0 | -170 | -
| 2026-05-31 | 635 | MU | Lower Parel | MA25 | MA25 | MU-MA25 | 60.5 | 60.5 | 18.9979 | 72.8252 | MUM_Route_105 | MUM_Route_105 | MCGM | G/S | Athashree CHSL (Sanskruti B-Wing) | Ganapatrao Kadam Marg,Lower Parel,Mumbai, Maharashtra 400013 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004638 | 2025-03-22 | 2026-03-22 | 60 | PO length is less than Feasibility length | -0.5 | PO Released | - |  | Not created | CWIP-76585 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-04-30 | 636 | MU | Dadar | 5372 | 5372 | MU-5372 | 55 | 55 | 19.0203 | 72.8331 | MUM_Route_106 | 5372_LM | MCGM | G/N | MIRAMRCHONM1 | Miramar Chsl,Near Prabhadevi Tel Exchange,Vir Savarkar Marg,Dadar(W),Mumbai-400028 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004621 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | Part of 99 |  | FF_NW1920_14493 | CWIP-76586 | RFAI Awaited | PO Released | - |  | 120 | 60 | LA Considered
| 2026-04-30 | 637 | MU | Dadar | 4324 | 4324 | MU-4324 | 77 | 77 | 19.0223 | 72.8368 | MUM_Route_106 | 4324_LM | MCGM | G/N | WHITELILO | White Lily, Veer Savarkar Marg, Dadar, Mumbai, 400028 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004621 | 2025-03-22 | 2026-03-22 | 80 | Ok | 3 | Dropped | Part of 99 |  | FF_NW2122_785506 | CWIP-76588 | RFAI Awaited | PO Released | - |  | 214 | 134 | -
| 2025-12-31 | 638 | MU | Mahim | 5342 | 5342 | MU-5342 | 16.5 | 16.5 | 19.0379 | 72.8419 | MUM_Route_107 | 5342_LM | MCGM | G/N | MAHMUDIDOF | Mohammed Idu Manjil, LJ Road, Mahim Mumbai-400016 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004626 | 2025-03-22 | 2026-03-22 | 20 | Ok | 3.5 | PO Released | - |  | Not created | CWIP-76591 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2025-12-31 | 639 | MU | Bandra |  | MB5740 | MU-MB5740 | 11 | 11 | 19.0497 | 72.8383 | MUM_Route_107 | MB5740_LM | MCGM | H/W | Bandra Reclamation Flyover | BANDRA RECLAMATION FLYOVER,WESTERN EXPRESS HWY, SANTOSH NAGAR, BANDRA WEST, MUMBAI, MAHARASHTRA | OSR | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | Site Drop by Airtel |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-02-28 | 640 | MU | Kalamboli | 1303 | 1303 | MU-1303 | 165 | 165 | 19.0289 | 73.1029 | MUM_Route_123 | 1303_LM | PMC | - | Kothari House | Shop No-24,Plot no-15, Sector-4E, Janta Market,Sector 4E, Kalamboli, Panvel, Navi Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004664 | 2025-03-24 | 2026-03-24 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-78095 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-02-28 | 641 | MU | Kalamboli | 4941 | 4941 | MU-4941 | 150 | 150 | 19.0309 | 73.1015 | MUM_Route_123 | 4941_LM | PMC | - | ANGELARCO | Angel Arc,Plot No - 23,Sce - 8,Near Church,Kalamboli,Mumbai | INDUS | Route LM | Co-Build | Not Feasible |  | Abdul Quadir | #N/A | - | 10004664 | 2025-03-24 | 2026-03-24 | 150 | Ok | 0 | PO Released | - |  | Not created | CWIP-78096 | RFAI Awaited | PO Released | - |  | 0 | -150 | -
| 2026-04-30 | 642 | MU | Lower Parel | 1135 | 1135 | MU-1135 | 55 | 55 | 19.0015 | 72.8252 | MUM_Route_54 | 1135_LM | MCGM | G/S | LAXMIINDO | Shankarrao Naram Path, Off Ferguson Road, Lower Parel | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004637 | 2025-05-21 | 2026-05-21 | 60 | Old PO-10004620 revised PO received 21-05-2025 | 5 | PO Released | Part of 99 |  | FF_NW1920_15603 | CWIP-76620 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2026-04-30 | 643 | MU | Lower Parel | MA1542 | MA1542 | MU-MA1542 | 220 | 220 | 19.0103 | 72.8299 | MUM_Route_54 | MA1542_LM | MCGM | G/S | Sadguru Darshan | SADGURU DARSHAN, NEAR PAREL ST DEPOT, PAREL WEST, MUMBAI - 400013 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004637 | 2025-05-21 | 2026-05-21 | 220 | Old PO-10004620 revised PO received 21-05-2025 | 0 | PO Released | - |  | Not created | CWIP-76621 | RFAI Awaited | PO Released | - |  | 0 | -220 | -
| 2026-04-30 | 644 | MU | Dadar | 1456 | 1456 | MU-1456 | 231 | 231 | 19.015 | 72.8331 | MUM_Route_54 | 1456_LM | MCGM | G/N | Sidhhivinayak Ashray | Appesaheb Marathe Marg, Khed Gali, Dadar West-400025 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004637 | 2025-05-21 | 2026-05-21 | 230 | Old PO-10004620 revised PO received 21-05-2025 | -1 | PO Released | Part of 99 |  | FF_NW1920_14930 | CWIP-76622 | RFAI Awaited | PO Released | - | Not Mapped | 160 | -70 | -
| 2026-04-30 | 645 | MU | Dadar | MA4021 | MA4021 | MU-MA4021 | 66 | 66 | 19.019 | 72.8333 | MUM_Route_54 | MA4021_LM | MCGM | G/N | ChitraKoot | Opp.Sahakari Bhandar,Kashinath Dhuru Marg,Dadar West,Mumbai,Maharastra-400025 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004637 | 2025-05-21 | 2026-05-21 | 70 | Old PO-10004620 revised PO received 21-05-2025 | 4 | PO Released | Part of 99 |  | FF_NW1920_15438 | CWIP-76623 | RFAI Awaited | PO Released | - |  | 19 | -51 | -
| 2026-05-31 | 646 | MU | Kharghar | MB6122 | MB6122 | MU-MB6122 | 275 | 275 | 19.0339 | 73.0666 | MUM_Route_122 | MB6122_LM | PMC | - | The Landmark | The Landmark, Plot No. 26/A, Sector 7, Kharghar, Navi Mumbai, Maharashtra 410210 | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76080 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-05-31 | 647 | MU | Kharghar | 2825 | 2825 | MU-2825 | 165 | 165 | 19.033 | 73.0659 | MUM_Route_122 | 2825_LM | PMC | - | 3STARQQQOF | Three Star Hotel, Crystal plaza, sector 7, kharghar, navi Mumbai | Airtel Own | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 170 | Ok | 5 | PO Released | - |  | Not created | CWIP-76081 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-05-31 | 648 | MU | Kharghar | 879 | 879 | MU-879 | 55 | 55 | 19.0398 | 73.0639 | MUM_Route_122 | 879_LM | PMC | - | Prime Mall | Prime mall,Near utsav chowk,sec 12 kharghar,Navi mumbai | ATC | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76082 | Received | PO Released | - |  | 0 | -60 | -
| 2026-05-31 | 649 | MU | Kharghar | 2074 | 2074 | MU-2074 | 66 | 66 | 19.044 | 73.0722 | MUM_Route_122 | 2074_LM | PMC | - | Zam Zam Appt | Neelam Heights, plot no 139,Opp Raghunath Vihar,Block G, Sector 13, Kharghar,Navi Mumbai | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 70 | Ok | 4 | PO Released | - |  | Not created | CWIP-76086 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-05-31 | 650 | MU | Kharghar | MA4382 | MA4382 | MU-MA4382 | 220 | 220 | 19.0456 | 73.0656 | MUM_Route_122 | MA4382_LM | PMC | - | Chamunda Krupa MU/MU/LO/11512 | Shree Dutt Mandir Rd, Sector 12, Kharghar,Navi Mumbai, Maharashtra 410210 | ATC | Route LM | Co-Build | Feasible |  | Narayan Parab | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 220 | Ok | 0 | PO Released | - |  | Not created | CWIP-76083 | Received | PO Released | - |  | 0 | -220 | -
| 2026-05-31 | 651 | MU | Kharghar | 5154 | 5154 | MU-5154 | 170.242 | 0 | 19.0472 | 73.0652 | MUM_Route_122 | 5154_LM | PMC | - | Nav Vihar | Nav Vihar,Plot No 31,Sec 12 Kharghar,Navi Mumbai | INDUS | Route LM | Co-Build | Data mismatch |  | Narayan Parab | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 170 | PO length is greater than Feasibility Length | 170 | PO Released | - |  | Not created | CWIP-76084 | RFAI Awaited | PO Released | - |  | 0 | -170 | -
| 2026-05-31 | 652 | MU | Kharghar | MB6428 | MB6428 | MU-MB6428 | 275 | 275 | 19.0344 | 73.0635 | MUM_Route_122 | MB6428_LM | PMC | - | Anant Chs | Anant CHS, CLUSTER_PANVEL-39, Plot No. 31, Sector 4, Kharghar, Navi Mumbai, Maharashtra 410210 | INDUS | Route LM | Co-Build | Feasible |  | Abdul Quadir | #N/A | - | 10004534 | 2025-03-13 | 2026-03-13 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76085 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2025-08-31 | 653 | MU | Sion |  | MA4570 | MU-MA4570 | 132 | 132 | 19.0486 | 72.8633 | MUM_Route_55 | MA4570_LM | MCGM | G/N | Idris Bhai House_Netsol | LBS RD, NAIK NAGAR,OPP SION RAILWAY STATION,SION DHARAVI, MUMBAI, MAHARASHTRA 400017 | Netsol | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | - | - | - | 0 | PO Pending |  | PR In Process | - |  | Not created | - | RFAI Awaited | PR In Process | - |  | 0 | 0 | -
| 2026-01-31 | 654 | MU | Worli | 4207 | 4207 | MU-4207 | 275 | 275 | 19.0125 | 72.8203 | MUM_Route_8 | 4207_LM | MCGM | G/S | GMTINIWAO | Near Sasmira, Dr Annie Beaseant Road, Prabhadevi, Mumbai-400031 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76650 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2025-08-31 | 655 | MU | Dharavi | 4986 | 4986 | MU-4986 | 55 | 55 | 19.0459 | 72.8493 | MUM_Route_55 | 4986_LM | MCGM | G/N | THEVARQ | Mahim - Sion Link Road, Dharavi Mumbai-400017 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10004628 | 2025-03-22 | 2026-03-22 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76638 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| #N/A | 656 | MU | Thane | MB1714 | MB1714 | MU-MB1714 | 165 | 165 | 19.1888 | 72.9626 | MUM_Route_152 | MB1714_LM | TMC | - | Shivanand Chsl | Shivanand Society, Owner-Rakshe Gupta, Landmark-M.S.Road, Louis Wadi, City-Thane West, Thane, Post Office:-Thane, Police Station:-Thane,Thane | ATC | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004959 | 2025-04-05 | 2026-04-05 | 60 | PO length is less than Feasibility length | -105 | PO Released | - |  | Not created | CWIP-76598 | RFAI Awaited | PO Released | - |  | 0 | -60 | -
| 2025-08-31 | 657 | MU | Dharavi | MA1119 | MA1119 | MU-MA1119 | 110 | 110 | 19.0474 | 72.8585 | MUM_Route_55 | MA1119_LM | MCGM | G/N | KALAPATARU CHS | DHARAVI KALAPATARU CHS, Way to Khamdev Nagar, Dharavi, Mumbai, Maharashtra 400017 | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10005007 | 2025-05-07 | 2026-05-07 | 350 | Received on dated 7th May |  | PO Released | - |  | Not created | - | RFAI Awaited | PR In Process | - |  | 0 | -350 | -
| 2026-01-31 | 658 | MU | Mahalaxmi | 3879 | 3879 | MU-3879 | 275 | 275 | 18.9862 | 72.8161 | MUM_Route_8 | 3879_LM | MCGM | G/S | NSCI INDOOR STADIUM. | Near Nehru center, Worli, Mumbai, | Airtel Own | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 180 | PO length is less than Feasibility length | -95 | PO Released | - |  | Not created | CWIP-76651 | RFAI Awaited | PO Released | - |  | 0 | -180 | -
| 2026-03-31 | 659 | MU | Nagpada | 4981 | 4981 | MU-4981 | 297 | 297 | 18.9629 | 72.8308 | MUM_Route_10 | 4981_LM | MCGM | E | Yasin Palace | Yashmin Plaza,Huzaria Streets,Barkatali Marg,Mumbai-400008 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004641 | 2025-03-22 | 2026-03-22 | 30 | PO length is less than Feasibility length | -267 | PO Released | Part of 99 |  | FF_NW2122_785507 | CWIP-76582 | RFAI Awaited | PO Released | - |  | 209 | 179 | LA Considered |  |  | Site under Relocation
| 2026-05-31 | 660 | MU | Bandra |  | MA13 | MU-MA13 | 220 | 220 | 19.0539 | 72.8474 | MUM_Route_108 | MA13_LM | MMRDA | - | Dallas | Plot # 1Kalanagar CHSLBandra East,Mumbai-400051 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | - | - | - | 0 | PO Pending |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2027-01-31 | 661 | MU | Mankhurd | #N/A | 2475 | MU-2475 | 55 | 55 | 19.0439 | 72.9234 | MUM_Route_90 | 2475_LM | MCGM | M/E | Sanjay Rathore Singh | Sanjay Rathore, Mankhurd Gaon, Mankhurd, | Suyog | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10004960 | 2025-04-08 | 2026-04-08 | 60 | Ok | 5 | PO Released-Hold by Airtel | - |  | Not created | CWIP-76665 | Received | PO Released | - |  | 0 | -60 | -
| 2026-01-31 | 662 | MU | Grant Rd | 6463 | 6463 | MU-6463 | 275 | 275 | 18.9463 | 72.8231 | MUM_Route_8 | 6463_LM | MCGM | C | ISLAMGYMOF | Islam Gymkhana,Marine Lines Station(W)Marine Drive,Mumbai-400002 | INDUS | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | 10004619 | 2025-03-22 | 2026-03-22 | 280 | Ok | 5 | PO Released | - |  | Not created | CWIP-76652 | RFAI Awaited | PO Released | - |  | 0 | -280 | -
| 2026-03-31 | 663 | MU | Byculla | 5959 | 5959 | MU-5959 | 99 | 99 | 18.9776 | 72.8333 | MUM_Route_10 | 5959_LM | MCGM | E | Mehrali chsl | AMBEDKAR RD, BYCULLA (e),Maharashtra-400011 | INDUS | Route LM | Co-Build | Feasible |  | Prem Verma | Prem Verma | - | 10005003 | 2025-05-07 | 2026-05-07 | 100 | PO Received on dated 7 May 25 |  | PO Released | - |  | Not created | - | RFAI Awaited | PR in Process | - |  | 0 | -100 | -
| 2026-01-31 | 664 | MU | Grant Rd |  | MA2903 | MU-MA2903 | 275 | 275 | 18.9517 | 72.8193 | MUM_Route_8 | MA2903_LM | MCGM | E | Bandekar 29 mansion | 27-33, Maharshi Karve Rd, Charni Road East,Charni road post office,Charni road police station, Girgaon, Mumbai, Maharashtra 400004 | Netsol | Route LM | Co-Build | Feasible |  | Jayhind Yadav | Yogesh Deshpande | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2026-04-30 | 665 | MU | Dadar | MB3940 | MB3940 | MU-MB3940 | 165 | 165 | 19.0221 | 72.8419 | MUM_Route_106 | MB3940_LM | MCGM | G/N | Gurukrupa Co.Op.Housing Society Ltd | GURUKRUPA CO OP HOUSING SOCIETY,C-01, N C. KELKAR MARG, KELKAR WADI, DADAR,POLICA STATION:- DADAR, POST OFFICE:-DADAR | INDUS | Route LM | Co-Build | Feasible |  | Swapnil Salvi | Yogesh Deshpande | - | 10005007 | 2025-05-07 | 2026-05-07 | 350 | Revised Rec On 7th May | 185 | PO Released | Part of 99 |  | FF_NW2122_785508 | CWIP-76587 | RFAI Awaited | PR In Process | - |  | 21 | -329 | -
| 2026-12-31 | 666 | MU | Dombivali |  | MB1450 | MU-MB1450 | 280 | 280 | 19.201 | 73.1129 | Mumbai_Coverage_Route39 | MB1450_LM | KDMC | - | Samarth Complex | Samarth Complex Dawadi Gaon, Sonar Pada, Dombivli East, Dombivli, Maharashtra 421203 | Netsol | Route LM | Co-Build | Feasible | Nov'25 | Jayhind Yadav | Yogesh Deshpande | - | - | - | - | 0 | PO Pending |  | Dropped | - |  | Not created | - | - | Dropped | - |  | 0 | 0 | -
| 2026-05-31 | 667 | MU | - | 5856 | 5856 | MU-MM5856 | 11.2 | 11.2 | 0 | 0 | MUM_Route_142 | 5856_LM | 0 | - | 0 | Mahadev Apt,near NG sun city . Thakur village kandivali east | INDUS | Route LM | Co-Build | Feasible |  | Sabhajeet Maurya | Satish Singh | - | 10004528 | 2025-03-13 | 2026-03-13 | 10 | PO length is less than Feasibility length | -1.2 | PO Released | - |  | Not created | CWIP-76090 | RFAI Awaited | PO Released | - |  | 0 | -10 | -
| 2026-01-31 | 668 | MU | Mahalaxmi | 5385 | 5385 | MU-5385 | 66 | 66 | 18.985 | 72.8162 | MUM_Route_8 | 5385_LM | MCGM | G/S | NSCI Admin (Outdoor) | National Sports Club of India, Lala Lajpat Rai Marg, Warli | Airtel Own | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004619 | 2025-03-22 | 2026-03-22 | 70 | Ok | 4 | Dropped | - |  | Not created | CWIP-76653 | - | Dropped | - |  | 0 | -70 | -
| 2025-11-30 | 669 | MU | Ghatkoper | MA4620 | MA4620 | MU-MA4620 | 66 | 66 | 19.0949 | 72.9142 | MUM_Route_157 | MA4620_LM | MCGM | N | SHIV SHAKTI INDUSTRIAL ESTATE | MR. PRASHANT SHIBE- 9004713335, Shiv Shakti Industrial Estate, Lal Bahadur Shastri Road, Near Shreyas Talkies, Nityanand Nagar, Ghatkopar West, Mumbai, Maharashtra- 400086 MUMBAI | INDUS | Route LM | Co-Build | Feasible |  | Manoj Ligade | Yogesh Deshpande | - | 10004656 | 2025-03-24 | 2026-03-24 | 70 | PO Pending |  | PO Released | - |  | Not created | CWIP-76397 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-01-31 | 670 | MU | Airoli | MA2014 | MA2014 | MU-MA2014 | 517 | 517 | 19.152 | 72.9874 | MUM_Route_80 | MA2014_LM | NMMC | - | Bhumi Colossa-2 chs | SECTOR 14,AIROLI NAVI MUMBAI, | ATC | Route LM | Co-Build | Feasible | Dec'25 | Abdul Quadir | #N/A | - | 10004627 | 2025-03-22 | 2026-03-22 | 520 | Ok | 3 | PO Released | - |  | Not created | CWIP-76656 | RFAI Awaited | PO Released | - |  | 0 | -520 | -
| 2026-03-31 | 671 | MU | Byculla |  | MA3548 | MU-MA3548 | 495 | 495 | 18.9714 | 72.8338 | MUM_Route_10 | MA3548_LM | MCGM | E | Bridge View | Bridge View, Hansraj Lane No-16, Byculla(E), Mumbai- 400010. | INDUS | Route LM | Co-Build | Feasible |  | Narayan Parab | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2025-12-31 | 672 | MU | Fort | 1144 | 1144 | MU-1144 | 126.5 | 126.5 | 18.9306 | 72.8333 | MUM_Route_99 | 1144_LM | MCGM | A | RAJABAHAOF | 24 Bd Raja Bahadur Compound, Ambalal Doshi Marg, (Hamam Street) 400001 | INDUS | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004622 | 2025-03-22 | 2026-03-22 | 70 | PO Pending |  | PO Released | - |  | Not created | CWIP-76675 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-12-31 | 673 | MU | Dombivali | MB1917 | MB1917 | MU-MB1917 | 55 | 55 | 19.1988 | 73.1081 | Mumbai_Coverage_Route39 | MB1917_LM | KDMC | - | Mhatre plot | Plot No.G2H,Shankara Nagar Rd,Bagalya Darshan,Shankara Nagar, Sonar Pada, Dombivli East, Dombivli, Maharashtra 421203. Post Office:-Dombivli,Police Station:-Dombivli | INDUS | Route LM | Co-Build | Feasible | April'26 | Sandeep randive | Yogesh Deshpande | - | 10004571 | 2025-03-18 | 2026-03-18 | 60 | Ok | 5 | PO Released | - |  | Not created | CWIP-76543 | Received | PO Released | - |  | 0 | -60 | -
| 2026-12-31 | 674 | MU | Dombivali | 859 | 859 | MU-859 | 66 | 66 | 19.2035 | 73.1113 | Mumbai_Coverage_Route39 | 859_LM | KDMC | - | SHREE GANESH KRUPA | Shree Ganesh Krupa,Regency Estate Rd,Sonar Pada,Dombivali E | INDUS | Route LM | Co-Build | Feasible | April'26 | Sandeep randive | Yogesh Deshpande | - | 10004571 | 2025-03-18 | 2026-03-18 | 70 | Ok | 4 | PO Released | - |  | Not created | CWIP-76544 | RFAI Awaited | PO Released | - |  | 0 | -70 | -
| 2026-12-31 | 675 | MU | Dombivali | MB6174 | MB6174 | MU-MB6174 | 88 | 88 | 19.2002 | 73.1051 | Mumbai_Coverage_Route39 | MB6174_LM | KDMC | - | Vrindavan Chs | Shankara Nagar Rd, Sonar Pada, Dombivli East, Dombivli, Maharashtra 421203 | INDUS | Route LM | Co-Build | Feasible | April'26 | Sandeep randive | Yogesh Deshpande | - | 10004571 | 2025-03-18 | 2026-03-18 | 90 | Ok | 2 | PO Released | - |  | Not created | CWIP-76545 | RFAI Awaited | PO Released | - |  | 0 | -90 | -
| 2025-12-31 | 676 | MU | Fort | 5032 | 5032 | MU-5032 | 77 | 77 | 18.931 | 72.8317 | MUM_Route_99 | 5032_LM | MCGM | A | ORIENTALOF | Opp HSBC Bldg,Flora Fountain,Mumbai, 400001 | Airtel Own | Route LM | Co-Build | Feasible |  | Vaijesh Patil | Prem Verma | - | 10004622 | 2025-03-22 | 2026-03-22 | 80 | PO Pending |  | PO Released | - |  | Not created | CWIP-76676 | RFAI Awaited | PO Released | - |  | 0 | -80 | -
| 2025-11-30 | 677 | MU | Vikroli | MA4450 | MA4450 | MU-MA4450 | 16.5 | 16.5 | 19.0987 | 72.9174 | MUM_Route_157 | MA4450_LM | MCGM | N | Presedential plaza | LBS ROAD,OPP VIKHROLI BUS DEPOT,GHATKOPAR (W) MUMBAI - 86 | ATC | Route LM | Co-Build | Feasible |  | Manoj Ligade | Yogesh Deshpande | - | 10004656 | 2025-03-24 | 2026-03-24 | 20 | Ok | 3.5 | PO Released | - |  | Not created | CWIP-76398 | RFAI Awaited | PO Released | - |  | 0 | -20 | -
| 2026-12-31 | 678 | MU | Ghansoli | 2234 | 2234 | MU-2234 | 605 | 605 | 19.1156 | 73.0019 | MUM_Route_81 | 2234_LM | NMMC | - | MATOSHREE NIWAS | Plot-381,Sec-4,Ghansoli,Navi Mumbai-400701 | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Narayan Parab | #N/A | - | 10004680 | 2025-03-24 | 2026-03-24 | 610 | Ok | 5 | PO Released | - |  | Not created | CWIP-76774 | RFAI Awaited | PO Released | - |  | 0 | -610 | -
| 2026-12-31 | 679 | MU | Kalyan | MA2726 | MA2726 | MU-MA2726 | 660 | 660 | 19.2013 | 73.1163 | Mumbai_Coverage_Route39 | MA2726_LM | KDMC | - | Vasudev Bhoir Open Plot | SONAR PADA, MIDC, MANPADA ,DOMBIVLI EAST, THANE,STATE-MAHARASHTRA, PINCODE-421302 | INDUS | Route LM | Co-Build | Feasible | Dec'25 | Ranjit Wadkar | #N/A | - | 10004571 | 2025-03-18 | 2026-03-18 | 660 | Ok | 0 | PO Released | - |  | Not created | CWIP-76546 | RFAI Awaited | PO Released | - |  | 0 | -660 | -
| 2026-02-28 | 680 | MU | Airoli |  | 5987 | MU-5987 | 715 | 715 | 19.1572 | 72.9981 | MUM_Route_68 | 5987_LM | NMMC | - | COORG ASSOCIATION | COORG ASSOCIATION,SEC-3,NEAR RAILWAY STATION,AIROLI,NAVI MUMBAI | INDUS | Route LM | Co-Build | more than 500 mtr | Dec'25 | Abdul Quadir | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | - | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2027-01-31 | 681 | MU | Vashi |  | 1277 | MU-1277 | 750 | 0 | 19.0727 | 72.9865 | MUM_Route_90 | 1277_LM | NMMC | - | Nadkarni House | Nadkarni House, Varshav Bungalow, plor no 26, Sector 7, Vashi Navi Mumbai | INDUS | Route LM | Co-Build | Newly add | Feb'26 | Abdul Quadir | #N/A | - | - | - | - | 0 | PO Pending |  | Under validation | - |  | Not created | CWIP-76666 | RFAI Awaited | Under validation | - |  | 0 | 0 | -
| 2025-07-31 | 682 | MU | Koparkhairane |  | MA3407 | MU-MA3407 | 950 | 0 | 19.0956 | 73.0306 | MUM_Route_48 | MA3407_LM | NMMC | - | Sand Taxtiles | Near Pawane MIDC Road Number 7, Koparkharne 400703 | INDUS | Route LM | Co-Build | Newly add | Dec'25 | Abdul Quadir | #N/A | - | - | - | - | 0 | PO Pending |  | Hold | - |  | Not created | CWIP-76736 | - | Under validation | - |  | 0 | 0 | -
| 2026-05-31 | 683 | MU | Sion | 5568 | 5568 | MU-5568 | 60 | 0 | 19.0337 | 72.8636 | Tamil Sangham to Guru Teg Bahadur Nagar Station | 5568_LM | MCGM | F/N | Gurukripa Chs (B Wing) | Gurukripa Chs,J K Bhasin Marg,Near Gurunanak School,Sion Koliwada,MumbaiSion 400037 | INDUS | Route LM | Co-Build | Additional Scope |  | Prem Verma | Prem Verma | - | 10004971 | 2025-04-17 | 2026-04-16 | 60 | Ok |  | PO Released | - |  |  | CWIP-78684 |  |  | - |  | 0 | -60 | -
| 2026-05-31 | 684 | MU | Sion | MB3514 | MB3514 | MU-MB3514 | 250 | 0 | 19.0319 | 72.8631 | Tamil Sangham to Guru Teg Bahadur Nagar Station | MB3514_LM | MCGM | F/N | Raj Heights | RAJ HEIGHTS,C.G.S. COLONY, CGS COLONY, SECTOR 3, KANE NAGAR, ANTOP HILL,POST OFFICE:-ANTOP HILL,POLICE STATION:-ANTOP HILL | INDUS | Route LM | Co-Build | Additional Scope |  | Prem Verma | Prem Verma | - | 10004971 | 2025-04-17 | 2026-04-16 | 250 | Ok |  | PO Released | - |  |  | CWIP-78683 |  |  | - |  | 0 | -250 | -
| 2026-05-31 | 685 | MU | Sion | 6027 | 6027 | MU-6027 | 100 | 0 | 19.0309 | 72.8602 | Tamil Sangham to Guru Teg Bahadur Nagar Station | 6027_LM | MCGM | F/N | SHANMUK | Shanmukunanda Hall, Nr Sion Stn, Sion (E),Mumbai, Maharashtra 400022 | INDUS | Route LM | Co-Build | Additional Scope |  | Prem Verma | Prem Verma | - | 10004971 | 2025-04-17 | 2026-04-16 | 100 | Ok |  | PO Released |  |  |  | CWIP-78682 |  |  | - |  | 0 | -100 | -
| 2026-04-30 | 686 | MU | Dadar | MA3655 | MA3655 | MU-MA3655 | 0 | 0 | 19.0203 | 72.8409 | MUM_Route_106 | MA3655_LM | MCGM | G/N | Kohinoor Apt (C&D Wing) | KOHINOOR APT C&D WING,NEXT TO RAM NIWAS HOTEL,DADAR WEST,, MUMBAI, MAHARASHTRA. | INDUS | Route LM | Co-Build | Additional Scope |  | Prem Verma | Prem Verma | - | 10004997 | 2025-05-04 | 2026-05-04 | 50 | New PO Added on dated 7 May-25 | - | PO Released | - |  | - | - | - |  | - |  | 0 | -50 | -
| 2026-04-30 | 687 | MU | Dadar |  | 4324 | MU-5196 | 0 | 0 | 19.0194 | 72.841 | MUM_Route_106 | 5196_LM | MCGM | G/N | BAGDADI | Dadar Dargah,Near Kabutar Khana, N.C.Kelkar Marg, Dadar, Mumbai | INDUS | Route LM | Co-Build | alternate of 4324 |  | Prem Verma | Prem Verma | - | - | - | - | 0 | - | - | PR In Process | - |  | - | - | - |  | - |  | 0 | 0 | - | Yes
| 2026-02-28 | 688 | MU | Kalamboli |  | 4952 | MU-4952 | 0 | 0 | 19.0268 | 73.1064 | MUM_Route_123 | 4952_LM | PMC | - | - | - | INDUS | Route LM | Co-Build | Additional Scope |  | Abdul Quadir | #N/A | - | - | - | - | 0 |  |  | PR In Process |  |  | Not created | - | RFAI Awaited |  | - |  | 0 | 0 | -
|  | 689 | MU | Shimpoli | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 100 | 100 | 19.2234 | 72.8409 | Shimpoli Metro Station | MU-Metro Rail LM | MCGM | R/C | Shimpoli Metro Station | Shimpoli Metro Station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004981 | 2025-04-18 | 2026-04-18 | 100 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -100 | -
|  | 690 | MU | Dindoshi | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 120 | 120 | 19.1789 | 72.8581 | Dindoshi Metro station | MU-Metro Rail LM | MCGM | P/N | Dindoshi Metro station | Dindoshi Metro station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004980 | 2025-04-18 | 2026-04-18 | 120 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -120 | -
|  | 691 | MU | Goregaon | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 90 | 90 | 19.1634 | 72.8348 | Bangur Nagar Metro Station | MU-Metro Rail LM | MCGM | P/S | Bangur Nagar Metro Station | Bangur Nagar Metro Station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004979 | 2025-04-18 | 2026-04-18 | 90 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -90 | -
|  | 692 | MU | Dahisar | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 290 | 290 | 19.2572 | 72.8656 | CS Road- Near BMC Market, Anand Nagar Metro Station | MU-Metro Rail LM | MCGM | R/N | CS Road- Near BMC Market, Anand Nagar Metro Station | CS Road- Near BMC Market, Anand Nagar Metro Station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004978 | 2025-04-18 | 2026-04-18 | 290 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -290 | -
|  | 693 | MU | Malad | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 160 | 160 | 19.1962 | 72.8338 | Malad Marve Road, Valnai Meeth Chowky Metro Station | MU-Metro Rail LM | MCGM | P/N | Malad Marve Road, Valnai Meeth Chowky Metro Station | Malad Marve Road, Valnai Meeth Chowky Metro Station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004976 | 2025-04-18 | 2026-04-18 | 160 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -160 | -
|  | 694 | MU | Kandivali | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 100 | 100 | 19.2068 | 72.8349 | Model Near Leela Park Dhanukar wadi Metro Station | MU-Metro Rail LM | MCGM | R/S | Model Near Leela Park Dhanukar wadi Metro Station | Model Near Leela Park Dhanukar wadi Metro Station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004975 | 2025-04-18 | 2026-04-18 | 100 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -100 | -
|  | 695 | MU | Oshiwara | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 200 | 200 | 19.146 | 72.8332 | Oshiwara Metro Station to Oshiwara CLS | MU-Metro Rail LM | MCGM | K/W | Oshiwara Metro Station to Oshiwara CLS | Oshiwara Metro Station to Oshiwara CLS | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004977 | 2025-04-18 | 2026-04-18 | 200 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -200 | -
|  | 696 | MU | Andheri | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 200 | 200 | 19.1286 | 72.8312 | Blue Line to 2A Line Connectivity | MU-Metro Rail LM | MCGM | K/W | Blue Line to 2A Line Connectivity | Blue Line to 2A Line Connectivity | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004983 | 2025-04-20 | 2026-04-20 | 200 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -200 | -
|  | 697 | MU | Oshiwara | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 110 | 110 | 19.141 | 72.8316 | Lower Oshiwara Metro station Opp Infinity Mall | MU-Metro Rail LM | MCGM | K/W | Lower Oshiwara Metro station Opp Infinity Mall | Lower Oshiwara Metro station Opp Infinity Mall | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004982 | 2025-04-20 | 2026-04-20 | 110 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -110 | -
|  | 698 | MU | Andheri | MU-Metro Rail LM | MU-Metro Rail LM | MU-Metro Rail LM | 120 | 120 | 19.1286 | 72.8312 | D N Nagar to Andheri West metro station | MU-Metro Rail LM | MCGM | K/W | D N Nagar to Andheri West metro station | D N Nagar to Andheri West metro station | Metro | Metro_LM | Co-Build | METRO |  | Hari Yadav | Satish Singh | - | 10004984 | 2025-04-20 | 2026-04-20 | 120 | Ok |  | PO Released |  |  |  | #N/A |  |  | - |  | 0 | -120 | -
Formulas:
PO End Date = [PO Date]+365

## PO Details_new
[7 empty] | 457021 | 457.021 |  | 6224447580
S.No | Modality | Category | PO No | PO Date | Route / Site Id | PO Description | Length (Mtrs) | Length(Kms) | Rate | Base Amount | PO Validation Remark (Ops/Sales Team) | Type | Remark
1 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004510 | 2025-03-11 | 2309 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2309 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
2 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004511 | 2025-03-11 | Mumbai/Coverage/Route28 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route28 | 1860 | 1.86 | 16000 | 29760000 | Ok | Route
3 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004512 | 2025-03-12 | 4634 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4634 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
3 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004512 | 2025-03-12 | 3019 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3019 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
4 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004513 | 2025-03-13 | MUM/Route/141 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/141 Interface Malad | 2280 | 2.28 | 16000 | 36480000 | Ok | Route
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 4919 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4919 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 5181 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5181 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 3511 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3511 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
6 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004515 | 2025-03-13 | MUM/Route/111 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/111 MUM/LOK/916 | 841 | 0.841 | 16000 | 13456000 | Ok | Route
6 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004515 | 2025-03-13 | MUM/Route/112 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/112 MUM/LOK/916 | 1020 | 1.02 | 16000 | 16320000 | Ok | Route
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | MB1703 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1703 | 10 | 0.01 | 16490 | 164900 | Ok | POP
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | 5665 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5665 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | AGG GOE 908 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GOE 908 | 50 | 0.05 | 16490 | 824500 |  | Additional Scop
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | 5294 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5294 | 30 | 0.03 | 16490 | 494700 | Site Drop by Airtel but PO Received | POP
8 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004517 | 2025-03-13 | MUM/Route/142 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/142 | 2760 | 2.76 | 16000 | 44160000 | Ok | Route
9 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004518 | 2025-03-13 | Mumbai/Coverage/Route1 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route1 | 0 | 0 | 0 | 0 | PO Cancelled | Route | Cancelled PO
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1046 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1046 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1831 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1831 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 4509 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4509 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | MA6080 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6080 | 300 | 0.3 | 16490 | 4947000 | Ok | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1742 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1742 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
11 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004520 | 2025-03-13 | MA2979 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2979 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
11 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004520 | 2025-03-13 | MB4276 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4276 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MB1589 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1589 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA2218 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2218 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA5051 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5051 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MB1259 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1259 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA5147 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5147 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
13 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004522 | 2025-03-13 | MUM/Route/4 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/4 | 6820 | 6.82 | 12500 | 85250000 | Ok | Route
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | MA1484 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1484 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 5579 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5579 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | MA6341 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6341 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 3068 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3068 | 10 | 0.01 | 16490 | 164900 | Ok | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 5768 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5768 | 300 | 0.3 | 16490 | 4947000 | Ok | POP
15 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004524 | 2025-03-13 | MUM/Route/33 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/33 Spectrum Tower | 4230 | 4.23 | 12500 | 52875000 | Ok | Route
16 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004525 | 2025-03-13 | MA609 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA609 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
17 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004526 | 2025-03-13 | MUM/Route/114 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/114 | 3720 | 3.72 | 16000 | 59520000 | Ok | Route
18 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004527 | 2025-03-13 | Mumbai_Coverage_Route10 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route10 | 1430 | 1.43 | 16000 | 22880000 | Ok | Route
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | 2257 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2257 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | 5856 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5856 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | AGG/TVL/903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG/TVL/903 | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
20 | Co-Built | - | BAL-TNG-NLD--Maharashtra/PUR/10004529 | 2025-03-13 | - | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity | 1900 | 1.9 | 16000 | 30400000 |  | Additional Scop
21 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004530 | 2025-03-13 | MUM/Route/122 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/122 MUM/LSK/901 | 2670 | 2.67 | 16000 | 42720000 | Ok | Route
21 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004530 | 2025-03-13 | MUM/Route/121 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/121 MUM/LSK/901 | 2080 | 2.08 | 16000 | 33280000 | Ok | Route
22 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004531 | 2025-03-13 | Mumbai_Coverage_Route7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route7 | 2590 | 2.59 | 16000 | 41440000 | Ok | Route
23 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004532 | 2025-03-13 | Mumbai_Coverage_Route9 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route9 | 3770 | 3.77 | 16000 | 60320000 | Ok | Route
24 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004533 | 2025-03-13 | MUM/Route/115 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/115 | 4550 | 4.55 | 16000 | 72800000 | Ok | Route
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 879 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 879 | 60 | 0.06 | 16490 | 989400 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MB6122 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6122 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MA4382 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4382 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MB6428 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6428 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 2074 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2074 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 2825 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2825 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 5154 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5154 | 170 | 0.17 | 16490 | 2803300 | PO length is greater than Feasibility Length | POP
26 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004535 | 2025-03-13 | MUM/Route/37 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/37 Versova | 2620 | 2.62 | 12500 | 32750000 | Route extended. | Route
27 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004536 | 2025-03-13 | Mumbai_Coverage_Route34 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route34 | 0 | 0 | 0 | 0 | PO Cancelled | Route | Cancelled PO
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | MB3309 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3309 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | 4794 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4794 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | 4553 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4553 | 60 | 0.06 | 16490 | 989400 | Ok | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | MB2965 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2965 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA118 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA118 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MB1435 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1435 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | AGG BSN 903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG BSN 903 | 125 | 0.125 | 16490 | 2061250 |  | Additional Scop
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA3616 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3616 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA1806 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1806 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | 1455 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1455 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | 2946 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2946 | 250 | 0.25 | 16490 | 4122500 | PO length is less than Feasibility length | POP
30 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004539 | 2025-03-13 | 5339 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5339 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
30 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004539 | 2025-03-13 | 1949 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1949 | 0 | 0 | 16490 | 0 | Site Drop by Airtel but PO Received | POP
31 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004540 | 2025-03-13 | Mumbai/Coverage/Route29 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route29 | 2400 | 2.4 | 16000 | 38400000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | 297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 297 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2938 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2938 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2915 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2915 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG GSK 901 MUM/Route/144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GSK 901 MUM/Route/144 | 100 | 0.1 | 16490 | 1649000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MB6450 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6450 | 60 | 0.06 | 16490 | 989400 | Site Drop by Airtel but PO Received | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | 5274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5274 | 60 | 0.06 | 16490 | 989400 | Ok | POP
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG GSK 901 MUM/Route/143 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GSK 901 MUM/Route/143 | 110 | 0.11 | 16490 | 1813900 | Ok | Route
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG DAH 901 MUM/Route/146 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG DAH 901 MUM/Route/146 | 500 | 0.5 | 16490 | 8245000 | Ok | Route
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG DAH 901 MUM/Route/145 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG DAH 901 MUM/Route/145 | 200 | 0.2 | 16490 | 3298000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2917 | 240 | 0.24 | 16490 | 3957600 | PO length is less than Feasibility length | POP
33 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004542 | 2025-03-17 | Mumbai/Coverage/Route12 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route12 | 4400 | 4.4 | 16000 | 70400000 | Ok | Route
34 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004543 | 2025-03-17 | Mumbai/Coverage/Route32 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route32 | 6750 | 6.75 | 16000 | 108000000 | Ok | Route
35 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004544 | 2025-03-17 | Mumbai/Coverage/Route3 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route3 | 2200 | 2.2 | 16000 | 35200000 | Ok | Route
36 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004545 | 2025-03-17 | Mumbai/Coverage/Route13 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route13 | 3030 | 3.03 | 16000 | 48480000 | Ok | Route
37 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004546 | 2025-03-17 | 5392 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5392 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | MA5707 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5707 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | MA1352 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1352 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | 2369 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2369 | 250 | 0.25 | 16490 | 4122500 | PO length is greater than Feasibility Length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | 3389 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3389 | 20 | 0.02 | 16490 | 329800 | Ok | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | 1262 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1262 | 400 | 0.4 | 16490 | 6596000 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | 6394 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6394 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MB2213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2213 | 130 | 0.13 | 16490 | 2143700 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MA5208 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5208 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MB2836 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2836 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MB1466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1466 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 304 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 304 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 4427 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4427 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 4558 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4558 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 1955 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1955 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MA818 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA818 | 50 | 0.05 | 16490 | 824500 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MA4606 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4606 | 10 | 0.01 | 16490 | 164900 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MB1349 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1349 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | MA3984 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3984 | 30 | 0.03 | 16490 | 494700 | Ok | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | 5995 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5995 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | 6180 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6180 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
42 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004551 | 2025-03-17 | Mumbai/Coverage/Route15 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route15 | 1580 | 1.58 | 16000 | 25280000 | Ok | Route
43 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004552 | 2025-03-17 | Mumbai/Coverage/Route17 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route17 | 1320 | 1.32 | 16000 | 21120000 | Ok | Route
44 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004553 | 2025-03-17 | Mumbai/Coverage/Route2 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route2 | 910 | 0.91 | 16000 | 14560000 | Ok | Route
45 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004554 | 2025-03-17 | Mumbai/Coverage/Route23 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route23 | 1760 | 1.76 | 16000 | 28160000 | Ok | Route
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | MB2153 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2153 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | Gopi Cinema AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Gopi Cinema AGG | 380 | 0.38 | 16490 | 6266200 |  | Additional Scop
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | Gopi Cinema AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Gopi Cinema AGG | 20 | 0.02 | 16490 | 329800 | Ok | POP
46 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | BHW6458 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites BHW6458 | 200 | 0.2 | 16490 | 3298000 |  | Additional Scop
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MB5951 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5951 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | 1508 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1508 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MA5231 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5231 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MA3332 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3332 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
48 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004557 | 2025-03-17 | MA1356 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1356 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | MA5851 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5851 | 190 | 0.19 | 16490 | 3133100 | Site Drop by Airtel but PO Received | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | 4488 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4488 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | 4004 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4004 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | 175 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 175 | 800 | 0.8 | 16490 | 13192000 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5153 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5153 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5138 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MB1187 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1187 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5523 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5523 | 60 | 0.06 | 16490 | 989400 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA599 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA599 | 450 | 0.45 | 16490 | 7420500 | PO length is greater than Feasibility Length | POP
51 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004560 | 2025-03-17 | Mumbai/Coverag/Route4 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverag/Route4 | 1500 | 1.5 | 16000 | 24000000 | Ok | Route
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | MA3429 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3429 LM | 40 | 0.04 | 16490 | 659600 | Ok | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | 6164 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6164 LM | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | 6194 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6194 LM | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | MA4669 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4669 LM | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
53 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004562 | 2025-03-17 | 4871 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4871 LM | 20 | 0.02 | 16490 | 329800 | Ok | POP
53 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004562 | 2025-03-17 | MB6431 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6431 LM | 170 | 0.17 | 16490 | 2803300 | PO length is greater than Feasibility Length | POP
54 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004563 | 2025-03-17 | Mumbai/Coverage/Route6 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route6 | 1980 | 1.98 | 16000 | 31680000 | Ok | Route
55 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004564 | 2025-03-17 | Mumbai/Coverage/Route21 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route21 | 2000 | 2 | 16000 | 32000000 | Ok | Route
56 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004565 | 2025-03-18 | Mumbai/Coverage/Route33 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route33 | 4860 | 4.86 | 16000 | 77760000 | Ok | Route
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2463 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2028 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2028 | 60 | 0.06 | 16490 | 989400 | Ok | POP
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2559 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2559 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
58 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004578 | 2025-03-18 | Mumbai/Coverage/Route31 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route31 | 2200 | 2.2 | 16000 | 35200000 | Ok | Route
59 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004577 | 2025-03-18 | MUM_Route_127 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM_Route_127 DC NSE Mumbai | 1190 | 1.19 | 16000 | 19040000 | Ok | Route
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | MA4376 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4376 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | MA1265 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1265 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | 4436 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4436 | 60 | 0.06 | 16490 | 989400 | Ok | POP
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | 6062 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6062 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | MB1727 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1727 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | MA4005 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4005 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 660 | 0.66 | 16490 | 10883400 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | 859 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 859 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MB6174 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6174 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MB1917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1917 | 60 | 0.06 | 16490 | 989400 | Ok | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | 6179 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6179 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | 1041 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1041 | 160 | 0.16 | 16490 | 2638400 | Ok | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | MA138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA138 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 6407 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6407 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 5741 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5741 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 5761 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5761 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 1191 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1191 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 1956 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1956 | 310 | 0.31 | 16490 | 5111900 | Ok | POP
65 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004579 | 2025-03-18 | MUM_Route_116 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM_Route_116 MUM/FTB/915 AGG | 940 | 0.94 | 16000 | 15040000 | Ok | Route
66 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004567 | 2025-03-18 | Mumbai/Coverage/Route38 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route38 | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
67 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004569 | 2025-03-18 | Mumbai/Coverage/Route25 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route25 | 1650 | 1.65 | 16000 | 26400000 | Ok | Route
68 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004566 | 2025-03-18 | Mumbai/Coverage/Route30 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route30 | 2050 | 2.05 | 16000 | 32800000 | Ok | Route
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | MA1260 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1260 | 400 | 0.4 | 16490 | 6596000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 3700 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax Sites 3700 | 300 | 0.3 | 16490 | 4947000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 2460 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2460 | 300 | 0.3 | 16490 | 4947000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 5619 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5619 | 230 | 0.23 | 16490 | 3792700 | PO length is less than Feasibility length | POP
70 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004568 | 2025-03-18 | MB1626 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1626 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
71 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004576 | 2025-03-18 | Mumbai/Coverage/Route35 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route35 | 0 | 0 | 16000 | 0 | Orignal route length of 4070 mtr but po received 3500 mts | Route | Cancelled PO
72 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004575 | 2025-03-18 | Mumbai/Coverage/Route37 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route37 | 1900 | 1.9 | 16000 | 30400000 | Ok | Route
73 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004584 | 2025-03-18 | Mumbai/Coverage/Route36 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route36 | 870 | 0.87 | 16000 | 13920000 | Ok | Route
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | 4991 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax Sites 4991 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | 2452 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2452 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA285 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA285 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA954 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA954 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MB1581 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1581 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA1400 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1400 | 180 | 0.18 | 16490 | 2968200 | PO length is greater than Feasibility Length | POP
75 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004570 | 2025-03-18 | Mumbai/Coverage/Route39 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route39 | 2310 | 2.31 | 16000 | 36960000 | Ok | Route
76 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004585 | 2025-03-19 | MUM/Route/109 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/109 | 2900 | 2.9 | 16000 | 46400000 | Ok | Route
77 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004586 | 2025-03-19 | MUM/Route/13 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/13 | 3030 | 3.03 | 12500 | 37875000 | Ok | Route
78 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004587 | 2025-03-19 | MUM/Route/27 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/27 | 9230 | 9.23 | 12500 | 115375000 | Ok | Route
79 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004588 | 2025-03-19 | 2895 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2895 | 220 | 0.22 | 16490 | 3627800 | Duplicate PO | Duplicate PO/ POP
80 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004589 | 2025-03-19 | MUM/Route/110 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/110 | 6220 | 6.22 | 16000 | 99520000 | Ok | Route
81 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004590 | 2025-03-19 | 999 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 999 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP
81 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004590 | 2025-03-19 | MUM/LBS/906 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/LBS/906 AGG | 120 | 0.12 | 16490 | 1978800 |  | Additional Scop
82 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004591 | 2025-03-19 | MUM/Route/117 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/117 | 1760 | 1.76 | 16000 | 28160000 | Ok | Route
83 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004592 | 2025-03-19 | MUM/Route/16 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/16 | 1830 | 1.83 | 12500 | 22875000 | Ok | Route
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA5500 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5500 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA3417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3417 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 3170 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3170 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA2281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2281 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 4070 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4070 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 4670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4670 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 2283 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2283 | 150 | 0.15 | 16490 | 2473500 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB3372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3372 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MA4901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4901 | 250 | 0.25 | 16490 | 4122500 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 139 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 139 | 210 | 0.21 | 16490 | 3462900 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 1148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1148 | 480 | 0.48 | 16490 | 7915200 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB6434 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6434 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB1250 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1250 | 200 | 0.2 | 16490 | 3298000 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MUM/VRL/901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/VRL/901 | 200 | 0.2 | 16490 | 3298000 | Ok | Route
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB2875 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2875 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
86 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004595 | 2025-03-19 | 2161 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2161 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/135 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/135 AGG AND/905 | 440 | 0.44 | 16000 | 7040000 | Ok | Route
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/113 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/113 | 1890 | 1.89 | 16000 | 30240000 | Ok | Route
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/136 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/136 AGG AND/905 | 140 | 0.14 | 16000 | 2240000 | Ok | Route
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | 2359 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2359 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MUM/KAI/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/KAI/901 AGG | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MB4811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4811 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MB5402 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5402 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | 5827 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5827 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MA6116 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6116 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MUM/AND/933 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/AND/933 | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MB3864 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3864 | 260 | 0.26 | 16490 | 4287400 | PO length is less than Feasibility length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MA6036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6036 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
90 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004599 | 2025-03-19 | MUM/Route/62 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/62 AGG SMP/901 | 900 | 0.9 | 12500 | 11250000 | Ok | Route
91 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004600 | 2025-03-19 | 2895 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2895 | 130 | 0.13 | 16490 | 2143700 | PO length is greater than Feasibility Length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA256 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA256 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6102 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6102 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 4207 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4207 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6463 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MUM/Route/8 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/8 Cobuilt | 2424 | 2.424 | 12500 | 30300000 | Ok | Route
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 4545 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4545 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 5385 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5385 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6239 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6239 | 60 | 0.06 | 16490 | 989400 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA3668 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3668 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 3879 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3879 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA5269 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5269 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA742 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA742 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MB5997 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5997 | 60 | 0.06 | 16490 | 989400 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 810 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 810 | 230 | 0.23 | 16490 | 3792700 | PO length is greater than Feasibility Length | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | MA1542 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1542 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | 1135 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1135 | 60 | 0.06 | 16490 | 989400 | Ok | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | 1456 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1456 | 230 | 0.23 | 16490 | 3792700 | PO length is less than Feasibility length | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | MA4021 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4021 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | 5372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5372 | 60 | 0.06 | 16490 | 989400 | Ok | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | MB3940 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3940 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | 4324 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4324 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
94 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | MUM/Route/106 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/106 Cobuilt | 200 | 0.2 | 16000 | 3200000 | Ok | Route
95 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004622 | 2025-03-22 | MUM_Route_99 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM_Route_99 IP1 | 1970 | 1.97 | 8900 | 17533000 | Ok | Route
96 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004623 | 2025-03-22 | MUM/Route/107 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/107 IP1 | 650 | 0.65 | 8900 | 5785000 | Ok | Route
96 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004623 | 2025-03-22 | Route55 to Route 107 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity Route55 to Route 107 Connectivity | 600 | 0.6 | 8900 | 5340000 | New Added and CE existing network Present. | Route
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MB6015 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6015 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 907 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 907 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 80 | 0.08 | 16490 | 1319200 | Duplicate PO | Duplicate PO/ POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 3310 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3310 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | BSE Iindia DC | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites BSE Iindia DC | 1000 | 1 | 16490 | 16490000 |  | Additional Scop
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 6369 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6369 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 70 | 0.07 | 16490 | 1154300 | Duplicate PO | Duplicate PO/ POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MB6017 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6017 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 3090 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3090 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
98 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004625 | 2025-03-22 | MUM/Route/11 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/11 | 1000 | 1 | 12500 | 12500000 | Ok | Route
99 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004626 | 2025-03-22 | MUM/Route/107 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/107 Cobuilt | 1768 | 1.768 | 16000 | 28288000 | Ok | Route
99 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004626 | 2025-03-22 | 5342 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5342 | 20 | 0.02 | 16000 | 320000 | Ok | POP
100 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004627 | 2025-03-22 | MA2014 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2014 | 520 | 0.52 | 16490 | 8574800 | Ok | POP
100 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004627 | 2025-03-22 | MA5118 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5118 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA2383 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2383 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA728 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA728 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3258 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3258 | 160 | 0.16 | 16490 | 2638400 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | NSE Mumbai DC | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites NSE Mumbai DC | 500 | 0.5 | 16490 | 8245000 |  | Additional Scop
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4986 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4986 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 358 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 358 | 160 | 0.16 | 16490 | 2638400 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MUM/XNQ/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/XNQ/901 AGG | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4913 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4913 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4932 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4932 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3120 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3120 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 5604 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5604 | 70 | 0.07 | 16490 | 1154300 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA4466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4466 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3177 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3177 | 20 | 0.02 | 16490 | 329800 | Ok | POP
102 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004629 | 2025-03-25 | MUM/Route/55 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/55 IP1 | 11962 | 11.962 | 8900 | 106461800 | Ok | Route
103 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004630 | 2025-03-22 | MUM/Route/101 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/101 IP1 | 1000 | 1 | 8900 | 8900000 | Need to be checked as route no 101 is of 800 mts only in data base | Route
104 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004631 | 2025-03-22 | MUM/Route/23 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/23 IP1 | 6420 | 6.42 | 8900 | 57138000 | Ok | Route
105 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004632 | 2025-03-22 | MUM/Route/8 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/8 IP1 | 11771 | 11.771 | 8900 | 104761900 | Ok | Route
106 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004633 | 2025-03-22 | MUM_Route_10 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM_Route_10 IP1 | 10280 | 10.28 | 8900 | 91492000 | Ok | Route
107 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MUM/BKC/906 LM | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/BKC/906 LM | 480 | 0.48 | 16490 | 7915200 |  | Additional Scop
107 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MB2378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2378 | 250 | 0.25 | 16490 | 4122500 | PO length is less than Feasibility length | POP
107 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MUM/Route/108 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/108 Cobuilt | 600 | 0.6 | 16000 | 9600000 | New Added. | Route
108 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004635 | 2025-03-22 | MUM/Route/106 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/106 IP1 | 2200 | 2.2 | 8900 | 19580000 | Route extended but extended portion was budgeted as per Co-built but PO received for IP1. Co-built surveyed length was 809 mt out off 1.9 km total route length | Route
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 2351 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2351 | 0 | 0 | 16000 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/173 MUM/BHL/909 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/173 MUM/BHL/909 AGG | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 3023 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3023 | 0 | 0 | 16000 | 0 | Ok | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MA3597 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA3597 | 0 | 0 | 16000 | 0 | Ok | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | additional DC Connectivity Netmagic DC7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Netmagic DC7 | 0 | 0 | 16000 | 0 |  | Additional Scop | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/152 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/152 MUM/TJR/901 AGG | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1179 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1179 | 0 | 0 | 16000 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB3249 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB3249 | 0 | 0 | 16000 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 141 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 141 | 0 | 0 | 16000 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/23 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/23 Cobuilt | 0 | 0 | 12500 | 0 | out of 15.6 km route length only 1.42 km received. | Route | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/153 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/153 MUM/TJR/901 AGG | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 5235 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5235 | 0 | 0 | 16000 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 6056 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 6056 | 0 | 0 | 16000 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 1562 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 1562 | 0 | 0 | 16000 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1714 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1714 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/148 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/148 MUM/THA/906 AGG | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/149 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/149 MUM/THA/906 AGG | 0 | 0 | 16000 | 0 | Ok | Route | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | GPX | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity GPX | 0 | 0 | 16000 | 0 |  | Additional Scop | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1348 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1348 | 0 | 0 | 16000 | 0 | Ok | POP | Cancelled PO
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MA6156 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA6156 | 0 | 0 | 16000 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
110 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004637 | 2025-03-22 | MUM/Route/54 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/54 IP1 | 5060 | 5.06 | 8900 | 45034000 | Ok | Route
111 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004638 | 2025-03-22 | MA25 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA25 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
112 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004639 | 2025-03-22 | MUM/Route/80 Mercury Tower | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/80 Mercury Tower | 5070 | 5.07 | 8900 | 45123000 | Ok | Route
113 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004640 | 2025-03-22 | MUM/Route/101 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/101 IP1 | 800 | 0.8 | 8900 | 7120000 | Ok | Route
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/104 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/104 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA1059 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1059 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/103 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/103 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 3054 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3054 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA1885 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1885 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5055 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5055 | 10 | 0.01 | 16490 | 164900 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA6295 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6295 | 30 | 0.03 | 16490 | 494700 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4859 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4859 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5029 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5029 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5451 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5451 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/131 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/131 | 200 | 0.2 | 16490 | 3298000 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA6540 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6540 | 270 | 0.27 | 16490 | 4452300 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5256 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5256 | 150 | 0.15 | 16490 | 2473500 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 2763 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2763 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4847 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4847 | 10 | 0.01 | 16490 | 164900 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MB3135 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3135 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA4226 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4226 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4981 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
115 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004642 | 2025-03-22 | MUM/Route/11 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/11 | 390 | 0.39 | 8900 | 3471000 | Ok | Route
116 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004643 | 2025-03-22 | MUM/Route/108 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/108 IP1 | 2787 | 2.787 | 8900 | 24804300 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/159 Vikroli DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/159 Vikroli DC | 390 | 0.39 | 16000 | 6240000 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/158 Netmagic DC4A | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/158 Netmagic DC4A | 220 | 0.22 | 16000 | 3520000 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/25 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/25 | 8500 | 8.5 | 12500 | 106250000 | Ok | Route
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | MB2236 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB2236 | 80 | 0.08 | 16000 | 1280000 | Site Drop by Airtel but PO Received | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | MA2131 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA2131 | 60 | 0.06 | 16000 | 960000 | Ok | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | 5769 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5769 | 280 | 0.28 | 16000 | 4480000 | PO length is greater than Feasibility Length | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | 2263 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2263 | 170 | 0.17 | 16000 | 2720000 | Ok | POP
119 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004652 | 2025-03-24 | MUM/Route/170 Hiranandani | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/170 Hiranandani | 1110 | 1.11 | 16000 | 17760000 | Ok | Route
120 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004653 | 2025-03-24 | MUM/Route/139 NetMagic DC 5 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/139 NetMagic DC 5 | 50 | 0.05 | 16490 | 824500 | Ok | Route
120 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004653 | 2025-03-24 | MUM/Route/138 NetMagic DC 5 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/138 NetMagic DC 5 | 50 | 0.05 | 16490 | 824500 | Ok | Route
121 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004654 | 2025-03-24 | MUM/Route/160 RJIO | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/160 RJIO | 1430 | 1.43 | 16000 | 22880000 | Ok | Route
121 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004654 | 2025-03-24 | 1777 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1777 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
122 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004655 | 2025-03-24 | MUM/Route/140 NetMagic DC 6 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/140 NetMagic DC 6 | 70 | 0.07 | 16490 | 1154300 | Ok | Route
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MB1917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1917 | 70 | 0.07 | 16490 | 1154300 | Duplicate PO | Duplicate PO/ POP
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MA4450 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4450 | 20 | 0.02 | 16490 | 329800 | Ok | POP
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MA5223 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5223 | 200 | 0.2 | 16490 | 3298000 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 5618 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5618 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MA5656 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5656 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MB2246 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2246 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 1694 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1694 | 200 | 0.2 | 16490 | 3298000 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | Mercury Tower AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mercury Tower AGG | 1200 | 1.2 | 16000 | 19200000 |  | Additional Scop
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/75 Colt | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/75 Colt | 563 | 0.563 | 16000 | 9008000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | Equinix | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Equinix | 563 | 0.563 | 16000 | 9008000 |  | Additional Scop
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/68 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/68 | 3950 | 3.95 | 16000 | 63200000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MA4147 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4147 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/118 Sift Airoli and Lumia | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/118 Sift Airoli and Lumia Airoli | 720 | 0.72 | 16000 | 11520000 | Ok | Route
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/74 Equininx | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/74 Equininx | 390 | 0.39 | 16000 | 6240000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | CapitaLand Data Centre CDC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity CapitaLand Data Centre CDC | 180 | 0.18 | 16000 | 2880000 |  | Additional Scop
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 109 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 109 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
125 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004658 | 2025-03-24 | 4750 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4750 | 330 | 0.33 | 16490 | 5441700 | Ok | POP
125 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004658 | 2025-03-24 | MUM/Route/58 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/58 | 4790 | 4.79 | 12500 | 59875000 | Ok | Route
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MB6371 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6371 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
126 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MUM/Route/57 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/57 | 4860 | 4.86 | 12500 | 60750000 | Ok | Route
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MA3485 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3485 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MB1718 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1718 | 160 | 0.16 | 16490 | 2638400 | PO length is less than Feasibility length | POP
127 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004660 | 2025-03-24 | MUM/Route/172 Web Works DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/172 Web Works DC | 110 | 0.11 | 16000 | 1760000 | Ok | Route
127 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004660 | 2025-03-24 | MUM/Route/172 Web Works DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/172 Web Works DC | 110 | 0.11 | 16000 | 1760000 | Ok | Route
128 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MUM/Route/36 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/36 | 0 | 0 | 12500 | 0 | Route length decreased from 6032 to 3600 according to the new KML but wrong po is issued of length 360 mtr. | Route | Cancelled PO
128 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MA5287 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5287 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
128 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MA4035 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4035 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
129 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004662 | 2025-03-24 | MUM_Route_31 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM_Route_31 | 970 | 0.97 | 12500 | 12125000 | Ok | Route
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB1595 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1595 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | Satyam AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Satyam AGG | 200 | 0.2 | 16490 | 3298000 |  | Additional Scop
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 6359 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6359 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA1165 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1165 | 290 | 0.29 | 16490 | 4782100 | PO length is greater than Feasibility Length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4506 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4506 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB2462 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2462 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4213 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA3996 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3996 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA2586 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2586 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 2731 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2731 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
130 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MUM/Route/19 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/19 | 5920 | 5.92 | 12500 | 74000000 | Ok | Route
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4474 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4474 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB1882 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1882 | 60 | 0.06 | 16490 | 989400 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB2224 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2224 | 60 | 0.06 | 16490 | 989400 | Ok | POP
131 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | 4941 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4941 | 150 | 0.15 | 16490 | 2473500 | Ok | POP
131 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | MUM/Route/124 MUM/CTC/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/124 MUM/CTC/901 AGG | 200 | 0.2 | 16000 | 3200000 | Length is decreased 1.37 to 0.20km | Route
131 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | 1303 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1303 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
131 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | MUM/Route/123 MUM/CTC/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/123 MUM/CTC/901 AGG | 1500 | 1.5 | 16000 | 24000000 | Length is decreased 2.22 to 1.50km | Route
132 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004665 | 2025-03-24 | MUM/Route/49 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/49 | 2800 | 2.8 | 12500 | 35000000 | Ok | Route
132 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004665 | 2025-03-24 | MB2282 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2282 | 60 | 0.06 | 16490 | 989400 | Ok | POP
133 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004666 | 2025-03-24 | MUM/Route/169 DC Yotta | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/169 DC Yotta | 1110 | 1.11 | 16000 | 17760000 | Ok but Orignal route length of 561 mtr but po received 1100 mts | Route
134 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004667 | 2025-03-24 | MUM/Route/150 Lumina Aroli | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/150 Lumina Aroli CapGemini (CG) campus | 200 | 0.2 | 16000 | 3200000 | Ok | Route
134 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004667 | 2025-03-24 | MUM/Route/151 Lumina Aroli | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/151 Lumina Aroli CapGemini (CG) campus | 220 | 0.22 | 16000 | 3520000 | Ok | Route
135 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004668 | 2025-03-24 | MUM/Route/157 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/157 | 1930 | 1.93 | 16000 | 30880000 | Ok | Route
136 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | MUM/Route/30 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/30 | 1150 | 1.15 | 12500 | 14375000 | Ok | Route
136 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | 6502 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6502 | 260 | 0.26 | 16490 | 4287400 | PO length is less than Feasibility length | POP
136 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | MA1878 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1878 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/Route/45 Cobuilt | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/45 Cobuilt | 6432 | 6.432 | 12500 | 80400000 | Ok | Route
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/STS/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/STS/901 AGG | 150 | 0.15 | 16490 | 2473500 |  | Additional Scop
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MB1711 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1711 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA2824 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2824 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 2213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2213 | 350 | 0.35 | 16490 | 5771500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/Route/24 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/24 | 960 | 0.96 | 16000 | 15360000 | Ok | Route
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA638 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA638 | 200 | 0.2 | 16490 | 3298000 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MB2815 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2815 | 180 | 0.18 | 16490 | 2968200 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 496 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 496 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 3817 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3817 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA1907 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1907 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 1677 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1677 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
138 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004671 | 2025-03-24 | MUM/Route/35 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/35 | 360 | 0.36 | 12500 | 4500000 | Ok | Route
138 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004671 | 2025-03-24 | 278 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 278 | 70 | 0.07 | 12500 | 875000 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MB2649 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2649 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA5673 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5673 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 1536 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1536 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA2578 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2578 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA4315 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4315 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 2730 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2730 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 1532 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1532 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MUM/Route/97 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/97 | 12000 | 12 | 12500 | 150000000 | Ok | Route
140 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004673 | 2025-03-24 | MUM/Route/156 Supreme Chamber | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/156 Supreme Chamber | 500 | 0.5 | 16000 | 8000000 | Ok | Route
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MB1103 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1103 | 70 | 0.07 | 16000 | 1120000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MUM/Route/137 Equnix MB GBX 3 DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/137 Equnix MB GBX 3 DC | 300 | 0.3 | 16000 | 4800000 | Ok | Route
141 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MUM/Route/38 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/38 | 3080 | 3.08 | 12500 | 38500000 | Ok | Route
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA5557 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA5557 | 150 | 0.15 | 16000 | 2400000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA4248 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4248 | 250 | 0.25 | 16000 | 4000000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | 3075 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3075 | 260 | 0.26 | 16000 | 4160000 | PO length is greater than Feasibility Length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA4846 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4846 | 120 | 0.12 | 16000 | 1920000 | PO length is less than Feasibility length | POP
142 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004675 | 2025-03-24 | MUM/Route/89 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/89 | 4890 | 4.89 | 12500 | 61125000 | Ok | Route
143 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004676 | 2025-03-24 | MUM/Route/147 MUM/THA/916 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/147 MUM/THA/916 | 180 | 0.18 | 16490 | 2968200 | New Added. | Route
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA1036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1036 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 6094 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6094 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA3495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3495 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA5212 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5212 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 4378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4378 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA1751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1751 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 3354 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3354 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 2587 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2587 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA4138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4138 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA2152 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2152 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MB6417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6417 | 0 | 0 | 16490 | 0 | Ok | POP | Cancelled PO
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 5357 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5357 | 0 | 0 | 16490 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
145 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004678 | 2025-03-24 | MUM/Route/45 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/45 IP1 | 11930 | 11.93 | 8900 | 106177000 | Ok | Route
146 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004679 | 2025-03-24 | MUM/Route/134 Netmagic DC4 DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/134 Netmagic DC4 DC | 1370 | 1.37 | 16000 | 21920000 | Ok | Route
147 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | Mum/Route/46 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mum/Route/46 | 480 | 0.48 | 16000 | 7680000 | Ok | Route
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB5991 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5991 | 200 | 0.2 | 16490 | 3298000 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 6224 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6224 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB1266 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1266 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MUM/Route/81 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/81 | 12010 | 12.01 | 12500 | 150125000 | Ok..70 mtr length increased. | Route
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB2459 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2459 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB3220 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3220 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MA2619 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2619 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB1795 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1795 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB2903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2903 | 190 | 0.19 | 16490 | 3133100 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB3271 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3271 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2253 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2253 | 60 | 0.06 | 16490 | 989400 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 1392 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1392 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 4973 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4973 | 380 | 0.38 | 16490 | 6266200 | PO length is greater than Feasibility Length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2342 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2342 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2234 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2234 | 610 | 0.61 | 16490 | 10058900 | Ok | POP
148 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004681 | 2025-03-24 | MUM/Route/48 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/48 | 3300 | 3.3 | 8900 | 29370000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/168 LUMINA Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/168 LUMINA Mahape | 110 | 0.11 | 16000 | 1760000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/167 LUMINA Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/167 LUMINA Mahape | 110 | 0.11 | 16000 | 1760000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/163 NAV1C NAV1D | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/163 NAV1C NAV1D | 231 | 0.231 | 12500 | 2887500 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/164 and 165 Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/164 and 165 Mahape NAV1A | 560 | 0.56 | 16000 | 8960000 | Ok | Route
150 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004683 | 2025-03-24 | MUM/Route/155 Digital Edge DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/155 Digital Edge DC | 1500 | 1.5 | 16000 | 24000000 | Feasibility needs to be recheck as original routes has been changed. | Route
151 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004684 | 2025-03-24 | MUM/Route_/25 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route_/25 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
152 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004685 | 2025-03-24 | MUM/Route/162 MAP/901/AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/162 MAP/901/AGG | 180 | 0.18 | 16000 | 2880000 | Ok | Route
152 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004685 | 2025-03-24 | MUM/Route/161 MAP/901/AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/161 MAP/901/AGG | 300 | 0.3 | 16000 | 4800000 | Ok | Route
153 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004686 | 2025-03-24 | MUM/Route/133 MUM/SPA/902 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/133 MUM/SPA/902 | 120 | 0.12 | 16490 | 1978800 | Ok | Route
154 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004689 | 2025-03-24 | MB3106 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3106 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
155 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004690 | 2025-03-24 | MA312 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA312 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
156 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004691 | 2025-03-24 | MA4100 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4100 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
157 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004692 | 2025-03-24 | 148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 148 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
158 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004693 | 2025-03-24 | MA183 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA183 | 106 | 0.106 | 16490 | 1747940 | Ok | POP
159 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004694 | 2025-03-24 | 2510 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2510 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
160 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004695 | 2025-03-24 | 596 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 596 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
161 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004696 | 2025-03-24 | 1659 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1659 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
162 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004697 | 2025-03-24 | MA1811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1811 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
163 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004698 | 2025-03-24 | MA184 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA184 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
164 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004699 | 2025-03-24 | 1000 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1000 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
165 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004700 | 2025-03-24 | 1788 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1788 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
166 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004701 | 2025-03-24 | 5541 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5541 | 235 | 0.235 | 16490 | 3875150 | Ok | POP
167 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004702 | 2025-03-24 | 5286 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5286 | 56 | 0.056 | 16490 | 923440 | Ok | POP
168 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004703 | 2025-03-24 | 1342 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1342 | 56 | 0.056 | 16490 | 923440 | Ok | POP
169 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004704 | 2025-03-24 | MA4632 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4632 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
170 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004705 | 2025-03-24 | 142 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 142 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
171 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004706 | 2025-03-24 | MA2816 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2816 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
172 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004707 | 2025-03-24 | 3604 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3604 | 56 | 0.056 | 16490 | 923440 | Ok | POP
173 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004708 | 2025-03-24 | 744 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 744 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
174 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004709 | 2025-03-24 | 1008 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1008 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
175 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004710 | 2025-03-24 | 2322 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2322 | 101 | 0.101 | 16490 | 1665490 | Ok | POP
176 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004711 | 2025-03-24 | 174 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 174 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
177 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004712 | 2025-03-24 | MA6274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6274 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
178 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004713 | 2025-03-24 | 2628 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2628 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
179 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004714 | 2025-03-24 | 4234 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4234 | 56 | 0.056 | 16490 | 923440 | Ok | POP
180 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004715 | 2025-03-24 | MB4699 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4699 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
181 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004716 | 2025-03-24 | MA5238 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5238 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
182 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004717 | 2025-03-24 | MB2495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2495 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
183 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004718 | 2025-03-24 | MB3478 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3478 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
184 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004719 | 2025-03-24 | MA4247 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4247 | 179 | 0.179 | 16490 | 2951710 | Ok | POP
185 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004720 | 2025-03-24 | MA4786 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4786 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
186 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004721 | 2025-03-24 | 341 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 341 | 121 | 0.121 | 16490 | 1995290 | PO length is greater than Feasibility Length | POP
187 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004722 | 2025-03-24 | MA366 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA366 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
188 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004723 | 2025-03-24 | MA4828 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4828 | 231 | 0.231 | 16490 | 3809190 | Ok | POP
189 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004724 | 2025-03-24 | 3107 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3107 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
190 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004725 | 2025-03-24 | 434 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 434 | 56 | 0.056 | 16490 | 923440 | Ok | POP
191 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004726 | 2025-03-24 | MB2863 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2863 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
192 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004727 | 2025-03-24 | MA2512 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2512 | 56 | 0.056 | 16490 | 923440 | Ok | POP
193 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004728 | 2025-03-24 | 356 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 356 | 123 | 0.123 | 16490 | 2028270 | Ok | POP
194 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004729 | 2025-03-24 | 3151 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3151 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
195 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004730 | 2025-03-24 | MA1811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1811 | 123 | 0.123 | 16490 | 2028270 | Duplicate PO | Duplicate PO/ POP
196 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004737 | 2025-03-25 | 4014 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4014 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
197 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004738 | 2025-03-25 | MA2866 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2866 | 246 | 0.246 | 16490 | 4056540 | Ok | POP
198 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004739 | 2025-03-25 | MB2460 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2460 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
199 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004740 | 2025-03-25 | MA73 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA73 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
200 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004742 | 2025-03-25 | 274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 274 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
201 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004743 | 2025-03-25 | 4495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4495 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
202 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004744 | 2025-03-25 | 5979 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5979 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
203 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004745 | 2025-03-25 | 6169 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6169 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
204 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004746 | 2025-03-25 | MA3916 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3916 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
205 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004747 | 2025-03-25 | MA4977 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4977 | 258 | 0.258 | 16490 | 4254420 | Ok | POP
206 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004748 | 2025-03-25 | 5592 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5592 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
207 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004749 | 2025-03-25 | MB4482 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4482 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
208 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004750 | 2025-03-25 | MB2505 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2505 | 257 | 0.257 | 16490 | 4237930 | Ok | POP
209 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004751 | 2025-03-25 | MA5495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5495 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
210 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004752 | 2025-03-25 | MA3055 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3055 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
211 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004753 | 2025-03-25 | 2798 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2798 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
212 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004754 | 2025-03-25 | MA2049 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2049 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
213 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004755 | 2025-03-25 | 3901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3901 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
214 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004756 | 2025-03-25 | MB1481 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1481 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
215 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004757 | 2025-03-25 | MA943 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA943 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
216 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004758 | 2025-03-25 | 5682 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5682 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
217 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004759 | 2025-03-25 | 2122 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2122 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
218 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004761 | 2025-03-25 | MB3311 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3311 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
219 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004762 | 2025-03-25 | 5980 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5980 | 45 | 0.045 | 16490 | 742050 | Ok | POP
220 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004763 | 2025-03-25 | 1251 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1251 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
221 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004765 | 2025-03-25 | MUM/Route/50 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/50 | 6030 | 6.03 | 8900 | 53667000 | Ok | Route
222 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004766 | 2025-03-25 | 4917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4917 | 11 | 0.011 | 16490 | 181390 | Ok | POP
223 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004767 | 2025-03-25 | 5709 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5709 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
224 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004768 | 2025-03-25 | MA4535 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4535 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
225 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004769 | 2025-03-25 | 2610 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2610 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
226 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004771 | 2025-03-25 | MUM/Route/90 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/90 IP1 | 4900 | 4.9 | 8900 | 43610000 | 4.9km po received 14.27 co-built PO awaited. | Route
227 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004773 | 2025-03-25 | 4719 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4719 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
228 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004774 | 2025-03-25 | 6520 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6520 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
229 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004776 | 2025-03-26 | 5525 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5525 | 338 | 0.338 | 16490 | 5573620 | PO length is less than Feasibility length | POP
230 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004777 | 2025-03-26 | 4381 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4381 | 56 | 0.056 | 16490 | 923440 | Ok | POP
231 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004778 | 2025-03-26 | 4883 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4883 | 50 | 0.05 | 16490 | 824500 | Ok | POP
232 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004779 | 2025-03-26 | 2010 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2010 | 251 | 0.251 | 16490 | 4138990 | Ok | POP
233 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004780 | 2025-03-26 | 5436 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5436 | 106 | 0.106 | 16490 | 1747940 | Ok | POP
234 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004781 | 2025-03-26 | 3330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3330 | 67 | 0.067 | 16490 | 1104830 | Duplicate PO | Duplicate PO/ POP
235 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004782 | 2025-03-26 | 3589 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3589 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
236 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004783 | 2025-03-26 | MA28 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA28 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
237 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004784 | 2025-03-26 | 1264 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1264 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
238 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004785 | 2025-03-26 | 6323 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6323 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
239 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004786 | 2025-03-26 | MB2765 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2765 | 560 | 0.56 | 16490 | 9234400 | Ok | POP
240 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004787 | 2025-03-26 | MA2398 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2398 | 346 | 0.346 | 16490 | 5705540 | Ok | POP
241 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004788 | 2025-03-26 | MB3183 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3183 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
242 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004789 | 2025-03-26 | MB2489 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2489 | 34 | 0.034 | 16490 | 560660 | Ok | POP
243 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004790 | 2025-03-26 | 3645 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3645 | 476 | 0.476 | 16490 | 7849240 | Ok | POP
244 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004791 | 2025-03-26 | 5831 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5831 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
245 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004792 | 2025-03-26 | MA4416 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4416 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
246 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004793 | 2025-03-26 | 5687 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5687 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
247 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004794 | 2025-03-26 | MB2484 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2484 | 30 | 0.03 | 16490 | 494700 | Ok | POP
248 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004795 | 2025-03-26 | 400 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 400 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
249 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004796 | 2025-03-26 | MB4330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4330 | 228 | 0.228 | 16490 | 3759720 | Ok | POP
250 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004797 | 2025-03-26 | MB5491 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5491 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
251 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004798 | 2025-03-26 | MA3580 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3580 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
252 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004799 | 2025-03-26 | 721 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 721 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
253 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004800 | 2025-03-26 | 5590 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5590 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
254 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004801 | 2025-03-26 | 2958 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2958 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
255 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004802 | 2025-03-26 | MA649 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA649 | 542 | 0.542 | 16490 | 8937580 | Ok | POP
256 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004803 | 2025-03-26 | MA129 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA129 | 28 | 0.028 | 16490 | 461720 | Ok | POP
257 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004804 | 2025-03-26 | 334 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 334 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
258 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004805 | 2025-03-26 | MB1728 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1728 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
259 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004806 | 2025-03-26 | 4198 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4198 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
260 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004807 | 2025-03-26 | 4534 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4534 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
261 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004808 | 2025-03-26 | 1308 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1308 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
262 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004809 | 2025-03-26 | 8 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 8 | 171 | 0.171 | 16490 | 2819790 | Ok | POP
263 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004810 | 2025-03-26 | 4609 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4609 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
264 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004811 | 2025-03-26 | 1734 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1734 | 302 | 0.302 | 16490 | 4979980 | Ok | POP
265 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004812 | 2025-03-26 | MB3457 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3457 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
266 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004813 | 2025-03-26 | 379 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 379 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
267 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004814 | 2025-03-26 | MA4076 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4076 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
268 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004815 | 2025-03-26 | 5886 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5886 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
269 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004816 | 2025-03-26 | 2372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2372 | 360 | 0.36 | 16490 | 5936400 | PO length is greater than Feasibility Length | POP
270 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004817 | 2025-03-26 | Business/156/205663 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Business/156/205663 | 55 | 0.055 | 16490 | 906950 | Ok | POP
271 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004818 | 2025-03-26 | 4449 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4449 | 1202 | 1.202 | 16490 | 19820980 | PO length is greater than Feasibility Length | POP
272 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004819 | 2025-03-26 | MA4114 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4114 | 726 | 0.726 | 16490 | 11971740 | Ok | POP
273 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004820 | 2025-03-26 | 2477 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2477 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
274 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004821 | 2025-03-26 | MA2877 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2877 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
275 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004822 | 2025-03-26 | MA4659 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4659 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
276 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004823 | 2025-03-26 | MA2282 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2282 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
277 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004824 | 2025-03-26 | MA1794 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1794 | 187 | 0.187 | 16490 | 3083630 | Ok | POP
278 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004825 | 2025-03-26 | 3123 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3123 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
279 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004826 | 2025-03-26 | MA3442 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3442 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
280 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004827 | 2025-03-26 | 6021 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6021 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
281 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004828 | 2025-03-26 | MA4011 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4011 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
282 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004829 | 2025-03-26 | MB640 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB640 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
283 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004830 | 2025-03-26 | MA1048 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1048 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
284 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004831 | 2025-03-26 | 3411 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3411 | 17 | 0.017 | 16490 | 280330 | Ok | POP
285 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004832 | 2025-03-26 | 1371 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1371 | 66 | 0.066 | 16490 | 1088340 | Ok | POP
286 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004833 | 2025-03-26 | MA2115 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2115 | 34 | 0.034 | 16490 | 560660 | PO length is greater than Feasibility Length | POP
287 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004834 | 2025-03-26 | MB1615 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1615 | 482 | 0.482 | 16490 | 7948180 | Ok | POP
288 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004835 | 2025-03-26 | 6195 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6195 | 1 | 0.001 | 16490 | 16490 | PO length is less than Feasibility length | POP
289 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004836 | 2025-03-26 | MB2355 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2355 | 102 | 0.102 | 16490 | 1681980 | Ok | POP
290 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004837 | 2025-03-26 | 4501 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4501 | 64 | 0.064 | 16490 | 1055360 | Ok | POP
291 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004838 | 2025-03-26 | MB6370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6370 | 33 | 0.033 | 16490 | 544170 | Ok | POP
292 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004839 | 2025-03-26 | MB2509 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2509 | 102 | 0.102 | 16490 | 1681980 | PO length is greater than Feasibility Length | POP
293 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004840 | 2025-03-26 | 5237 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5237 | 11 | 0.011 | 16490 | 181390 | Ok | POP
294 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004841 | 2025-03-26 | 4409 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4409 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
295 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004842 | 2025-03-26 | MA5099 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5099 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
296 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004843 | 2025-03-26 | MB1155 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1155 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
297 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004844 | 2025-03-26 | MA72 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA72 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
298 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004845 | 2025-03-26 | MB2981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2981 | 258 | 0.258 | 16490 | 4254420 | Ok | POP
299 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004846 | 2025-03-26 | MA4012 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4012 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
300 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004847 | 2025-03-26 | 2317 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2317 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
301 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004848 | 2025-03-26 | 3071 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3071 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
302 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004849 | 2025-03-26 | MB2148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2148 | 45 | 0.045 | 16490 | 742050 | Ok | POP
303 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004850 | 2025-03-26 | MA6227 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6227 | 154 | 0.154 | 16490 | 2539460 | Ok | POP
304 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004851 | 2025-03-26 | 5504 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5504 | 25 | 0.025 | 16490 | 412250 | Ok | POP
305 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004852 | 2025-03-26 | MB4281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4281 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
306 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004853 | 2025-03-26 | MB1084 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1084 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
307 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004854 | 2025-03-26 | Business/156/205663 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Business/156/205663 | 51 | 0.051 | 16490 | 840990 |  | Additional Scop
308 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004855 | 2025-03-26 | 2931 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2931 | 372 | 0.372 | 16490 | 6134280 | PO length is less than Feasibility length | POP
309 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004856 | 2025-03-26 | MA928 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA928 | 368 | 0.368 | 16490 | 6068320 | Ok | POP
310 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004857 | 2025-03-26 | 297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 297 | 297 | 0.297 | 16490 | 4897530 | Duplicate PO | Duplicate PO/ POP
311 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004858 | 2025-03-26 | MA2545 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2545 | 113 | 0.113 | 16490 | 1863370 | PO length is greater than Feasibility Length | POP
312 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004859 | 2025-03-26 | 1924 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1924 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
313 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004860 | 2025-03-26 | 6006 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6006 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
314 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004861 | 2025-03-26 | 5627 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5627 | 161 | 0.161 | 16490 | 2654890 | Ok | POP
315 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004862 | 2025-03-26 | 3398 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3398 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
316 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004863 | 2025-03-26 | 1387 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1387 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
317 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004864 | 2025-03-26 | 1027 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1027 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
318 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004865 | 2025-03-26 | MA3372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3372 | 45 | 0.045 | 16490 | 742050 | Ok | POP
319 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004866 | 2025-03-26 | MA1044 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1044 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
320 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004867 | 2025-03-26 | MA6019 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6019 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
321 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004868 | 2025-03-26 | MA4127 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4127 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
322 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004869 | 2025-03-26 | MB1608 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1608 | 56 | 0.056 | 16490 | 923440 | Ok | POP
323 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004870 | 2025-03-26 | MA3759 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3759 | 450 | 0.45 | 16490 | 7420500 | Ok | POP
324 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004871 | 2025-03-26 | MA4735 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4735 | 858 | 0.858 | 16490 | 14148420 | Ok | POP
325 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004872 | 2025-03-26 | MA2370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2370 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
326 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004873 | 2025-03-26 | MB1585 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1585 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
327 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004874 | 2025-03-26 | 3330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3330 | 45 | 0.045 | 16490 | 742050 | PO length is greater than Feasibility Length | POP
328 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004875 | 2025-03-26 | MB3226 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3226 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
329 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004876 | 2025-03-26 | MA3670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3670 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
330 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004877 | 2025-03-26 | MB1311 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1311 | 373 | 0.373 | 16490 | 6150770 | Ok | POP
331 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004878 | 2025-03-26 | MA6498 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6498 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
332 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004879 | 2025-03-26 | 3386 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3386 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
333 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004880 | 2025-03-26 | MB1591 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1591 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
334 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004881 | 2025-03-26 | MA4210 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4210 | 11 | 0.011 | 16490 | 181390 | Ok | POP
335 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004882 | 2025-03-26 | MA1621 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1621 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
336 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004883 | 2025-03-26 | 4337 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4337 | 133 | 0.133 | 16490 | 2193170 | PO length is less than Feasibility length | POP
337 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004884 | 2025-03-26 | MA2576 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2576 | 39 | 0.039 | 16490 | 643110 | Ok | POP
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | MA4640 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MA4640 | 0 | 0 | 12500 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 583 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 583 | 0 | 0 | 12500 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
338 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | MUM/Route/166 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/166 Vashi DC | 0 | 0 | 12500 | 0 | Ok | Route | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 5814 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 5814 | 0 | 0 | 12500 | 0 | Ok | POP | Cancelled PO
338 | Co-Built | New Add | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 1614 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 1614 | 0 | 0 | 12500 | 0 |  | Additional Scop | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | Sapata Sangam AGG | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model Sapata Sangam AGG | 0 | 0 | 12500 | 0 |  | Additional Scop | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 5307 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 5307 | 0 | 0 | 12500 | 0 | Ok | POP | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 3625 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 3625 | 0 | 0 | 12500 | 0 | PO length is less than Feasibility length | POP | Cancelled PO
338 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 2475 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 2475 | 0 | 0 | 12500 | 0 | Ok | POP | Cancelled PO
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3827 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3827 | 22 | 0.022 | 16490 | 362780 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB3510 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3510 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3132 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3132 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA1336 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1336 | 11 | 0.011 | 16490 | 181390 | PO length is less than Feasibility length | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB2632 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2632 | 123 | 0.123 | 16490 | 2028270 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3273 | 460 | 0.46 | 16490 | 7585400 | Duplicate PO | Duplicate PO/ POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4936 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4936 | 25 | 0.025 | 16490 | 412250 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA4575 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4575 | 286 | 0.286 | 16490 | 4716140 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 1797 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1797 | 246 | 0.246 | 16490 | 4056540 | Duplicate PO | Duplicate PO/ POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 370 | 66 | 0.066 | 16490 | 1088340 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3828 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3828 | 682 | 0.682 | 16490 | 11246180 | PO length is less than Feasibility length | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 880 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 880 | 420 | 0.42 | 16490 | 6925800 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3144 | 480 | 0.48 | 16490 | 7915200 | Duplicate PO | Duplicate PO/ POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3128 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3128 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 5395 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5395 | 38 | 0.038 | 16490 | 626620 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 5508 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5508 | 435 | 0.435 | 16490 | 7173150 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA1156 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1156 | 50 | 0.05 | 16490 | 824500 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 6281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6281 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4081 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4081 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 1297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1297 | 422 | 0.422 | 16490 | 6958780 | PO length is less than Feasibility length | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB2367 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2367 | 143 | 0.143 | 16490 | 2358070 | Ok | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3099 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3099 | 517 | 0.517 | 16490 | 8525330 | PO length is less than Feasibility length | POP
339 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4690 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4690 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 1670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1670 | 104 | 0.104 | 16490 | 1714960 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4088 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4088 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA1840 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1840 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2736 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2736 | 22 | 0.022 | 16490 | 362780 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 2643 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2643 | 16 | 0.016 | 16490 | 263840 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MB2466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2466 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 5158 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5158 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4546 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4546 | 200 | 0.2 | 16490 | 3298000 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 194 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 194 | 99 | 0.099 | 16490 | 1632510 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5407 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5407 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4998 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4998 | 300 | 0.3 | 16490 | 4947000 | PO length is less than Feasibility length | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA3675 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3675 | 187 | 0.187 | 16490 | 3083630 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5034 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5034 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2088 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2088 | 58 | 0.058 | 16490 | 956420 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5982 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5982 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA981 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4093 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4093 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 1474 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1474 | 33 | 0.033 | 16490 | 544170 | Ok | POP
340 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 636 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 636 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
341 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004772 | 2025-03-25 | MA2181 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2181 | 400 | 0.4 | 16490 | 6596000 | Ok | POP
341 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004772 | 2025-03-25 | MB3667 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3667 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1640 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1640 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA5750 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5750 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 855 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 855 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA751 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1490 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1490 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3273 | 480 | 0.48 | 16490 | 7915200 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3144 | 460 | 0.46 | 16490 | 7585400 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3463 | 0 | 0 | 16490 | 0 | PO length is greater than Feasibility Length | POP | Cancelled PO
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 273 | 448 | 0.448 | 16490 | 7387520 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 4971 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4971 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1365 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1365 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 6479 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6479 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA960 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA960 | 235 | 0.235 | 16490 | 3875150 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB2983 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2983 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA1813 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1813 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 4971 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4971 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1797 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1797 | 460 | 0.46 | 16490 | 7585400 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 6087 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6087 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 247 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 247 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB3502 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3502 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB1785 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1785 | 163 | 0.163 | 16490 | 2687870 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA3567 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3567 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB1584 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1584 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA3897 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3897 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
343 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004736 | 2025-03-26 | MA3832 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3832 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 2351 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2351 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/173 MUM/BHL/909 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/173 MUM/BHL/909 AGG | 550 | 0.55 | 16000 | 8800000 | Ok | Route
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MB1348 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1348 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 5235 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5235 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 1562 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1562 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 6056 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6056 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MA6156 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6156 | 80 | 0.08 | 16490 | 1319200 | PO length is greater than Feasibility Length | POP
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/153 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/153 MUM/TJR/901 AGG | 520 | 0.52 | 16000 | 8320000 | Ok | Route
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MB1714 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1714 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MB1179 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1179 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 3023 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3023 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites 141 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 141 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/149 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/149 MUM/THA/906 AGG | 400 | 0.4 | 16000 | 6400000 | Ok | Route
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites GPX | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites GPX | 800 | 0.8 | 16490 | 13192000 | Ok | Route
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MA3597 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3597 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/23 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/23 Cobuilt | 12500 | 12.5 | 12500 | 156250000 | Ok | Route
344 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites MB3249 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3249 | 90 | 0.09 | 16490 | 1484100 | PO length is greater than Feasibility Length | POP
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/148 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/148 MUM/THA/906 AGG | 280 | 0.28 | 16000 | 4480000 | Ok | Route
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Netmagic DC7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Netmagic DC7 | 100 | 0.1 | 16000 | 1600000 | Ok | Route
344 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/152 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/152 MUM/TJR/901 AGG | 500 | 0.5 | 16000 | 8000000 | Ok | Route
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MA4640 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4640 | 70 | 0.07 | 16000 | 1120000 | PO length is greater than Feasibility Length | POP
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 2475 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2475 | 60 | 0.06 | 16000 | 960000 | Ok
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MUM/Route/166 Vashi DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/166 Vashi DC | 1684 | 1.684 | 16000 | 26944000 | Ok | Route
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 583 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 583 | 60 | 0.06 | 16000 | 960000 | PO length is less than Feasibility length
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 1614 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 1614 | 300 | 0.3 | 16000 | 4800000
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 3625 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3625 | 50 | 0.05 | 16000 | 800000 | PO length is less than Feasibility length
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | Sapata Sangam AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Sapata Sangam AGG | 1200 | 1.2 | 16000 | 19200000 | Ok | Route
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 5814 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5814 | 180 | 0.18 | 16000 | 2880000 | Ok
345 |  | Route | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MUM/Route/90 Cobuilt | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/90 Cobuilt | 14270 | 14.27 | 12500 | 178375000 | Ok | Route
345 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 5307 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5307 | 300 | 0.3 | 16000 | 4800000 | Ok
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA2152 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2152 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 6094 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6094 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 2587 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2587 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA5212 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5212 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MUM/Route/42 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/42 | 7770 | 7.77 | 12500 | 97125000 | Ok | Route
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA1036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1036 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 4378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4378 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 3354 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3354 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA1751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1751 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA3495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3495 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA4138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4138 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MB6417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6417 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
346 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 5357 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5357 | 360 | 0.36 | 16490 | 5936400 | PO length is less than Feasibility length | POP
347 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MA5287 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5287 | 150 | 0.15 | 16490 | 2473500 | Ok | Route
347 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MA4035 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4035 | 90 | 0.09 | 16490 | 1484100 | Ok | Route
347 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MUM/Route/36 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/36 | 3600 | 3.6 | 12500 | 45000000 | Ok | Route
348 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004963 | 2025-04-08 | Mumbai/Coverage/Route35 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route35 | 4070 | 4.07 | 16000 | 65120000 | Ok | Route
349 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004968 | 2025-04-15 | Mumbai/Coverage/Route34 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route34 | 1600 | 1.6 | 16000 | 25600000
349 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004968 | 2025-04-15 | MB4276 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4276 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
349 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004968 | 2025-04-15 | MA2979 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2979 | 70 | 0.07 | 16490 | 1154300 | PO length is less than Feasibility length | POP
350 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004967 | 2025-04-15 | MB1727 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1727 | 40 | 0.04 | 16490 | 659600
350 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004967 | 2025-04-15 | Mumbai/Coverage/Route38 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route38 | 2300 | 2.3 | 16000 | 36800000 | Ok | Route
350 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004967 | 2025-04-15 | 6062 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6062 | 80 | 0.08 | 16490 | 1319200
350 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004967 | 2025-04-15 | MA4005 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4005 | 150 | 0.15 | 16490 | 2473500
351 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004966 | 2025-04-15 | Mumbai/Coverage/Route1 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route1 | 1210 | 1.21 | 16000 | 19360000
351 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004966 | 2025-04-15 | 2309 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2309 | 150 | 0.15 | 16490 | 2473500 | PO length is greater than Feasibility Length | POP
352 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004973 | 2025-04-17 | Center Point to Mint Colony Station | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model Center Point to Mint Colony Station Cobuilt | 200 | 0.2 | 12500 | 2500000
352 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004973 | 2025-04-17 | Center Point to Mint Colony Station IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity Center Point to Mint Colony Station IP1 | 550 | 0.55 | 8900 | 4895000
353 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004972 | 2025-04-17 | Jairamdas to VNP & RC Marg Junction Station | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model Jairamdas to VNP & RC Marg Junction Station | 1000 | 1 | 12500 | 12500000
354 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004974 | 2025-04-17 | Sant Gadge Maharaj Chowk to NM Joshi Marg | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity Sant Gadge Maharaj Chowk to NM Joshi Marg | 880 | 0.88 | 8900 | 7832000
355 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004971 | 2025-04-17 | 5568 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5568 | 60 | 0.06 | 16490 | 989400
355 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004971 | 2025-04-17 | Tamil Sangham to Guru Teg Bahadur Nagar Station | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity Tamil Sangham to Guru Teg Bahadur Nagar Station | 2273 | 2.273 | 8900 | 20229700
355 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004971 | 2025-04-17 | MB3514 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3514 | 250 | 0.25 | 16490 | 4122500
355 | Co-Built |  | BAL-TNG-NLD--Maharashtra/PUR/10004971 | 2025-04-17 | 6027 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6027 | 100 | 0.1 | 16490 | 1649000
356 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004981 | 2025-04-18 | Shimpoli Metro Station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Shimpoli Metro Station | 100 | 0.1 | 16490 | 1649000
357 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004980 | 2025-04-18 | Dindoshi Metro station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Dindoshi Metro station | 120 | 0.12 | 16490 | 1978800
358 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004979 | 2025-04-18 | Bangur Nagar Metro Station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Bangur Nagar Metro Station | 90 | 0.09 | 16490 | 1484100
359 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004978 | 2025-04-18 | CS Road- Near BMC Market, Anand Nagar Metro Station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model CS Road- Near BMC Market, Anand Nagar Metro Station | 290 | 0.29 | 16490 | 4782100
360 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004976 | 2025-04-18 | Malad Marve Road, Valnai Meeth Chowky Metro Station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Malad Marve Road, Valnai Meeth Chowky Metro Station | 160 | 0.16 | 16490 | 2638400
361 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004975 | 2025-04-18 | Model Near Leela Park Dhanukar wadi Metro Station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Near Leela Park Dhanukar wadi Metro Station | 100 | 0.1 | 16490 | 1649000
362 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004977 | 2025-04-18 | Oshiwara Metro Station to Oshiwara CLS | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Oshiwara Metro Station to Oshiwara CLS | 200 | 0.2 | 16490 | 3298000
363 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004983 | 2025-04-20 | Blue Line to 2A Line Connectivity | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Blue Line to 2A Line Connectivity | 200 | 0.2 | 16490 | 3298000
364 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004982 | 2025-04-20 | Lower Oshiwara Metro station Opp Infinity Mall | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model Lower Oshiwara Metro station Opp Infinity Mall | 110 | 0.11 | 16490 | 1813900
365 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004984 | 2025-04-20 | D N Nagar to Andheri West metro station | B0STDDRH7 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last Mile work for Mumbai Intracity Project on Co-Built Model D N Nagar to Andheri West metro station | 120 | 0.12 | 16490 | 1978800

## Sheet1
0.231
0.56
0.11
0.11
0.96
0.56
0.72
0.39
0.18
0.42
1.5
0.07
0.48
0.14
0.44
0.55
0.05
0.05
1.5
0.42
1.11
1.11
0.5

## PO Details (hidden)
[7 empty] | 560 | 0.56 |  | 8960000
S.No | Modality | Category | PO No | PO Date | Route / Site Id | PO Description | Length (Mtrs) | Length(Kms) | Rate | Base Amount | PO Validation Remark (Ops/Sales Team) | Type | 2025-04-09
1 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004510 | 2025-03-11 | 2309 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2309 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
2 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004511 | 2025-03-11 | Mumbai/Coverage/Route28 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route28 | 1860 | 1.86 | 16000 | 29760000 | Ok | Route
3 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004512 | 2025-03-12 | 4634 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4634 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
3 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004512 | 2025-03-12 | 3019 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3019 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
4 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004513 | 2025-03-13 | MUM/Route/141 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/141 Interface Malad | 2280 | 2.28 | 16000 | 36480000 | Ok | Route
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 4919 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4919 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 5181 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5181 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
5 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004514 | 2025-03-13 | 3511 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3511 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
6 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004515 | 2025-03-13 | MUM/Route/111 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/111 MUM/LOK/916 | 841 | 0.841 | 16000 | 13456000 | Ok | Route
6 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004515 | 2025-03-13 | MUM/Route/112 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/112 MUM/LOK/916 | 1020 | 1.02 | 16000 | 16320000 | Ok | Route
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | MB1703 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1703 | 10 | 0.01 | 16490 | 164900 | Ok | POP
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | 5665 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5665 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | AGG GOE 908 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GOE 908 | 50 | 0.05 | 16490 | 824500 |  | Additional Scop
7 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004516 | 2025-03-13 | 5294 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5294 | 30 | 0.03 | 16490 | 494700 | Site Drop by Airtel but PO Received | POP
8 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004517 | 2025-03-13 | MUM/Route/142 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/142 | 2760 | 2.76 | 16000 | 44160000 | Ok | Route
9 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004518 | 2025-03-13 | Mumbai/Coverage/Route1 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route1 | 0 | 0 | 0 | 0 | PO Cancelled | Route
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1046 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1046 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1831 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1831 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 4509 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4509 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | MA6080 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6080 | 300 | 0.3 | 16490 | 4947000 | Ok | POP
10 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004519 | 2025-03-13 | 1742 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1742 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
11 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004520 | 2025-03-13 | MA2979 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2979 | 70 | 0.07 | 16490 | 1154300 | PO length is less than Feasibility length | POP
11 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004520 | 2025-03-13 | MB4276 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4276 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MB1589 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1589 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA2218 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2218 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA5051 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5051 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MB1259 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1259 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
12 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004521 | 2025-03-13 | MA5147 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5147 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
13 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004522 | 2025-03-13 | MUM/Route/4 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/4 | 6820 | 6.82 | 12500 | 85250000 | Ok | Route
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | MA1484 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1484 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 5579 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5579 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | MA6341 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6341 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 3068 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3068 | 10 | 0.01 | 16490 | 164900 | Ok | POP
14 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004523 | 2025-03-13 | 5768 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5768 | 300 | 0.3 | 16490 | 4947000 | Ok | POP
15 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004524 | 2025-03-13 | MUM/Route/33 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/33 Spectrum Tower | 4230 | 4.23 | 12500 | 52875000 | Ok | Route
16 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004525 | 2025-03-13 | MA609 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA609 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
17 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004526 | 2025-03-13 | MUM/Route/114 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/114 | 3720 | 3.72 | 16000 | 59520000 | Ok | Route
18 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004527 | 2025-03-13 | Mumbai_Coverage_Route10 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route10 | 1430 | 1.43 | 16000 | 22880000 | Ok | Route
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | 2257 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2257 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | 5856 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5856 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
19 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004528 | 2025-03-13 | AGG/TVL/903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG/TVL/903 | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
20 | Co-Built | r | BAL-TNG-NLD--Maharashtra/PUR/10004529 | 2025-03-13 | Mumbai_Coverage_Route5 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity | 1900 | 1.9 | 16000 | 30400000 |  | PO Modification WIP
21 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004530 | 2025-03-13 | MUM/Route/122 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/122 MUM/LSK/901 | 2670 | 2.67 | 16000 | 42720000 | Ok | Route
21 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004530 | 2025-03-13 | MUM/Route/121 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/121 MUM/LSK/901 | 2080 | 2.08 | 16000 | 33280000 | Ok | Route
22 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004531 | 2025-03-13 | Mumbai_Coverage_Route7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route7 | 2590 | 2.59 | 16000 | 41440000 | Ok | Route
23 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004532 | 2025-03-13 | Mumbai_Coverage_Route9 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route9 | 3770 | 3.77 | 16000 | 60320000 | Ok | Route
24 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004533 | 2025-03-13 | MUM/Route/115 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/115 | 4550 | 4.55 | 16000 | 72800000 | Ok | Route
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 879 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 879 | 60 | 0.06 | 16490 | 989400 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MB6122 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6122 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MA4382 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4382 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | MB6428 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6428 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 2074 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2074 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 2825 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2825 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
25 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004534 | 2025-03-13 | 5154 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5154 | 170 | 0.17 | 16490 | 2803300 | PO length is greater than Feasibility Length | POP
26 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004535 | 2025-03-13 | MUM/Route/37 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/37 Versova | 2620 | 2.62 | 12500 | 32750000 | Route extended. | Route
27 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004536 | 2025-03-13 | Mumbai_Coverage_Route34 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai_Coverage_Route34 | 0 | 0 | 0 | 0 | PO Cancelled | Route
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | MB3309 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3309 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | 4794 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4794 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | 4553 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4553 | 60 | 0.06 | 16490 | 989400 | Ok | POP
28 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004537 | 2025-03-13 | MB2965 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2965 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA118 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA118 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MB1435 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1435 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | AGG BSN 903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG BSN 903 | 125 | 0.125 | 16490 | 2061250 |  | Additional Scop
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA3616 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3616 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | MA1806 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1806 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | 1455 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1455 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
29 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004538 | 2025-03-13 | 2946 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2946 | 250 | 0.25 | 16490 | 4122500 | PO length is less than Feasibility length | POP
30 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004539 | 2025-03-13 | 5339 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5339 | 140 | 0.14 | 16490 | 2308600 | PO length is less than Feasibility length | POP
30 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004539 | 2025-03-13 | 1949 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1949 | 90 | 0.09 | 16490 | 1484100 | Site Drop by Airtel but PO Received | POP
31 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004540 | 2025-03-13 | Mumbai/Coverage/Route29 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route29 | 2400 | 2.4 | 16000 | 38400000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | 297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 297 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2938 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2938 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2915 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2915 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG GSK 901 MUM/Route/144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GSK 901 MUM/Route/144 | 100 | 0.1 | 16490 | 1649000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MB6450 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6450 | 60 | 0.06 | 16490 | 989400 | Site Drop by Airtel but PO Received | POP
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | 5274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5274 | 60 | 0.06 | 16490 | 989400 | Ok | POP
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG GSK 901 MUM/Route/143 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG GSK 901 MUM/Route/143 | 110 | 0.11 | 16490 | 1813900 | Ok | Route
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG DAH 901 MUM/Route/146 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG DAH 901 MUM/Route/146 | 500 | 0.5 | 16490 | 8245000 | Ok | Route
32 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | AGG DAH 901 MUM/Route/145 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites AGG DAH 901 MUM/Route/145 | 200 | 0.2 | 16490 | 3298000 | Ok | Route
32 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004541 | 2025-03-13 | MA2917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2917 | 240 | 0.24 | 16490 | 3957600 | PO length is less than Feasibility length | POP
33 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004542 | 2025-03-17 | Mumbai/Coverage/Route12 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route12 | 4400 | 4.4 | 16000 | 70400000 | Ok | Route
34 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004543 | 2025-03-17 | Mumbai/Coverage/Route32 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route32 | 6750 | 6.75 | 16000 | 108000000 | Ok | Route
35 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004544 | 2025-03-17 | Mumbai/Coverage/Route3 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route3 | 2200 | 2.2 | 16000 | 35200000 | Ok | Route
36 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004545 | 2025-03-17 | Mumbai/Coverage/Route13 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route13 | 3030 | 3.03 | 16000 | 48480000 | Ok | Route
37 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004546 | 2025-03-17 | 5392 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5392 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | MA5707 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5707 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | MA1352 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1352 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | 2369 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2369 | 250 | 0.25 | 16490 | 4122500 | PO length is greater than Feasibility Length | POP
38 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004547 | 2025-03-17 | 3389 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3389 | 20 | 0.02 | 16490 | 329800 | Ok | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | 1262 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1262 | 400 | 0.4 | 16490 | 6596000 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | 6394 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6394 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MB2213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2213 | 130 | 0.13 | 16490 | 2143700 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MA5208 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5208 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
39 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004548 | 2025-03-17 | MB2836 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2836 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MB1466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1466 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 304 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 304 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 4427 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4427 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 4558 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4558 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | 1955 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1955 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MA818 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA818 | 50 | 0.05 | 16490 | 824500 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MA4606 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4606 | 10 | 0.01 | 16490 | 164900 | Ok | POP
40 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004549 | 2025-03-17 | MB1349 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1349 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | MA3984 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3984 | 30 | 0.03 | 16490 | 494700 | Ok | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | 5995 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5995 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
41 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004550 | 2025-03-17 | 6180 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6180 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
42 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004551 | 2025-03-17 | Mumbai/Coverage/Route15 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route15 | 1580 | 1.58 | 16000 | 25280000 | Ok | Route
43 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004552 | 2025-03-17 | Mumbai/Coverage/Route17 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route17 | 1320 | 1.32 | 16000 | 21120000 | Ok | Route
44 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004553 | 2025-03-17 | Mumbai/Coverage/Route2 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route2 | 910 | 0.91 | 16000 | 14560000 | Ok | Route
45 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004554 | 2025-03-17 | Mumbai/Coverage/Route23 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route23 | 1760 | 1.76 | 16000 | 28160000 | Ok | Route
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | MB2153 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2153 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | Gopi Cinema AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Gopi Cinema AGG | 380 | 0.38 | 16490 | 6266200 |  | Additional Scop
46 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | Gopi Cinema AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Gopi Cinema AGG | 20 | 0.02 | 16490 | 329800 |  | Additional Scop
46 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004555 | 2025-03-17 | BHW6458 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites BHW6458 | 200 | 0.2 | 16490 | 3298000 |  | Additional Scop
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MB5951 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5951 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | 1508 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1508 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MA5231 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5231 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
47 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004556 | 2025-03-17 | MA3332 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3332 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
48 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004557 | 2025-03-17 | MA1356 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1356 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | MA5851 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5851 | 190 | 0.19 | 16490 | 3133100 | Site Drop by Airtel but PO Received | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | 4488 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4488 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
49 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004558 | 2025-03-17 | 4004 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4004 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | 175 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 175 | 800 | 0.8 | 16490 | 13192000 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5153 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5153 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5138 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MB1187 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1187 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA5523 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5523 | 60 | 0.06 | 16490 | 989400 | Ok | POP
50 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004559 | 2025-03-17 | MA599 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA599 | 450 | 0.45 | 16490 | 7420500 | PO length is greater than Feasibility Length | POP
51 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004560 | 2025-03-17 | Mumbai/Coverag/Route4 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverag/Route4 | 1500 | 1.5 | 16000 | 24000000 | Ok | Route
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | MA3429 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3429 LM | 40 | 0.04 | 16490 | 659600 | Ok | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | 6164 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6164 LM | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | 6194 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6194 LM | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
52 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004561 | 2025-03-17 | MA4669 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4669 LM | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
53 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004562 | 2025-03-17 | 4871 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4871 LM | 20 | 0.02 | 16490 | 329800 | Ok | POP
53 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004562 | 2025-03-17 | MB6431 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6431 LM | 170 | 0.17 | 16490 | 2803300 | PO length is greater than Feasibility Length | POP
54 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004563 | 2025-03-17 | Mumbai/Coverage/Route6 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route6 | 1980 | 1.98 | 16000 | 31680000 | Ok | Route
55 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004564 | 2025-03-17 | Mumbai/Coverage/Route21 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route21 | 2000 | 2 | 16000 | 32000000 | Ok | Route
56 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004565 | 2025-03-18 | Mumbai/Coverage/Route33 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route33 | 4860 | 4.86 | 16000 | 77760000 | Ok | Route
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2463 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2028 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2028 | 60 | 0.06 | 16490 | 989400 | Ok | POP
57 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004572 | 2025-03-18 | MA2559 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2559 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
58 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004578 | 2025-03-18 | Mumbai/Coverage/Route31 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route31 | 2200 | 2.2 | 16000 | 35200000 | Ok | Route
59 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004577 | 2025-03-18 | MUM_Route_127 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM_Route_127 DC NSE Mumbai | 1190 | 1.19 | 16000 | 19040000 | Ok | Route
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | MA4376 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4376 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | MA1265 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1265 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
60 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004574 | 2025-03-18 | 4436 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4436 | 60 | 0.06 | 16490 | 989400 | Ok | POP
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | 6062 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6062 | 800 | 0.8 | 16490 | 13192000 | PO length is greater than Feasibility Length | POP
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | MB1727 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1727 | 400 | 0.4 | 16490 | 6596000 | PO length is greater than Feasibility Length | POP
61 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004581 | 2025-03-18 | MA4005 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4005 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 660 | 0.66 | 16490 | 10883400 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | 859 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 859 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MB6174 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6174 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
62 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004571 | 2025-03-18 | MB1917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1917 | 60 | 0.06 | 16490 | 989400 | Ok | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | 6179 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6179 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | 1041 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1041 | 160 | 0.16 | 16490 | 2638400 | Ok | POP
63 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004573 | 2025-03-18 | MA138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA138 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 6407 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6407 | 50 | 0.05 | 16490 | 824500 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 5741 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5741 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 5761 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5761 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 1191 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1191 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
64 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004583 | 2025-03-18 | 1956 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1956 | 310 | 0.31 | 16490 | 5111900 | Ok | POP
65 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004579 | 2025-03-18 | MUM_Route_116 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM_Route_116 MUM/FTB/915 AGG | 940 | 0.94 | 16000 | 15040000 | Ok | Route
66 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004567 | 2025-03-18 | Mumbai/Coverage/Route38 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route38 | 2300 | 2.3 | 16000 | 36800000 | PO Cancelled | Route
67 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004569 | 2025-03-18 | Mumbai/Coverage/Route25 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route25 | 1650 | 1.65 | 16000 | 26400000 | Ok | Route
68 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004566 | 2025-03-18 | Mumbai/Coverage/Route30 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route30 | 2050 | 2.05 | 16000 | 32800000 | Ok | Route
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | MA1260 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1260 | 400 | 0.4 | 16490 | 6596000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 3700 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax Sites 3700 | 300 | 0.3 | 16490 | 4947000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 2460 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2460 | 300 | 0.3 | 16490 | 4947000 | PO length is greater than Feasibility Length | POP
69 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004582 | 2025-03-18 | 5619 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5619 | 230 | 0.23 | 16490 | 3792700 | PO length is less than Feasibility length | POP
70 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004568 | 2025-03-18 | MB1626 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1626 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
71 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004576 | 2025-03-18 | Mumbai/Coverage/Route35 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route35 | 3500 | 3.5 | 16000 | 56000000 | Orignal route length of 4070 mtr but po received 3500 mts | Route | PO cancelled
72 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004575 | 2025-03-18 | Mumbai/Coverage/Route37 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route37 | 1900 | 1.9 | 16000 | 30400000 | Ok | Route
73 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004584 | 2025-03-18 | Mumbai/Coverage/Route36 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route36 | 870 | 0.87 | 16000 | 13920000 | Ok | Route
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | 4991 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax Sites 4991 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | 2452 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2452 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA285 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA285 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA954 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA954 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MB1581 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1581 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
74 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004580 | 2025-03-18 | MA1400 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1400 | 180 | 0.18 | 16490 | 2968200 | PO length is greater than Feasibility Length | POP
75 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004570 | 2025-03-18 | Mumbai/Coverage/Route39 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route39 | 2310 | 2.31 | 16000 | 36960000 | Ok | Route
76 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004585 | 2025-03-19 | MUM/Route/109 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/109 | 2900 | 2.9 | 16000 | 46400000 | Ok | Route
77 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004586 | 2025-03-19 | MUM/Route/13 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/13 | 3030 | 3.03 | 12500 | 37875000 | Ok | Route
78 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004587 | 2025-03-19 | MUM/Route/16 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/16 | 9230 | 9.23 | 12500 | 115375000 | According to data base PO should be by the name of MUM_Route_27 but the PO is under MUM_Route_16 | Route
79 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004588 | 2025-03-19 | 2895 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2895 | 220 | 0.22 | 16490 | 3627800 | Duplicate PO | Duplicate PO/ POP
80 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004589 | 2025-03-19 | MUM/Route/110 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/110 | 6220 | 6.22 | 16000 | 99520000 | Ok | Route
81 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004590 | 2025-03-19 | 999 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 999 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP
81 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004590 | 2025-03-19 | MUM/LBS/906 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/LBS/906 AGG | 120 | 0.12 | 16490 | 1978800 |  | Additional Scop
82 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004591 | 2025-03-19 | MUM/Route/117 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/117 | 1760 | 1.76 | 16000 | 28160000 | Ok | Route
83 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004592 | 2025-03-19 | MUM/Route/16 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/16 | 1830 | 1.83 | 12500 | 22875000 | Ok | Route
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA5500 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5500 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA3417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3417 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 3170 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3170 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | MA2281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2281 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 4070 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4070 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
84 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004593 | 2025-03-19 | 4670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4670 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 2283 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2283 | 150 | 0.15 | 16490 | 2473500 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB3372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3372 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MA4901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4901 | 250 | 0.25 | 16490 | 4122500 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 139 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 139 | 210 | 0.21 | 16490 | 3462900 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | 1148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1148 | 480 | 0.48 | 16490 | 7915200 | Ok | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB6434 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6434 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB1250 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1250 | 200 | 0.2 | 16490 | 3298000 | PO length is greater than Feasibility Length | POP
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MUM/VRL/901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/VRL/901 | 200 | 0.2 | 16490 | 3298000 |  | Additional Scop
85 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004594 | 2025-03-19 | MB2875 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2875 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
86 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004595 | 2025-03-19 | 2161 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2161 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/135 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/135 AGG AND/905 | 440 | 0.44 | 16000 | 7040000 | Ok | Route
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/113 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/113 | 1890 | 1.89 | 16000 | 30240000 | Ok | Route
87 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004596 | 2025-03-19 | MUM/Route/136 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/136 AGG AND/905 | 140 | 0.14 | 16000 | 2240000 | Ok | Route
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | 2359 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2359 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MUM/KAI/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/KAI/901 AGG | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MB4811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4811 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | MB5402 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5402 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
88 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004597 | 2025-03-19 | 5827 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5827 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MA6116 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6116 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MUM/AND/933 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/AND/933 | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MB3864 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3864 | 260 | 0.26 | 16490 | 4287400 | PO length is less than Feasibility length | POP
89 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004598 | 2025-03-19 | MA6036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6036 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
90 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004599 | 2025-03-19 | MUM/Route/62 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/62 AGG SMP/901 | 900 | 0.9 | 12500 | 11250000 | Ok | Route
91 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004600 | 2025-03-19 | 2895 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2895 | 130 | 0.13 | 16490 | 2143700 | PO length is greater than Feasibility Length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA256 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA256 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6102 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6102 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 4207 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4207 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6463 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MUM/Route/8 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/8 Cobuilt | 2424 | 2.424 | 12500 | 30300000 | Ok | Route
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 4545 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4545 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 5385 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5385 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 6239 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6239 | 60 | 0.06 | 16490 | 989400 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA3668 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3668 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 3879 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3879 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA5269 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5269 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MA742 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA742 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | MB5997 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5997 | 60 | 0.06 | 16490 | 989400 | Ok | POP
92 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004619 | 2025-03-22 | 810 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 810 | 230 | 0.23 | 16490 | 3792700 | PO length is greater than Feasibility Length | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | MA1542 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1542 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | 1135 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1135 | 60 | 0.06 | 16490 | 989400 | Ok | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | 1456 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1456 | 230 | 0.23 | 16490 | 3792700 | PO length is less than Feasibility length | POP
93 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004620 | 2025-03-22 | MA4021 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4021 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | 5372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5372 | 60 | 0.06 | 16490 | 989400 | Ok | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | MB3940 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3940 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
94 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | 4324 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4324 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
94 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004621 | 2025-03-22 | MUM/Route/106 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/106 Cobuilt | 200 | 0.2 | 16000 | 3200000 | Ok | Route
95 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004622 | 2025-03-22 | MUM_Route_99 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM_Route_99 IP1 | 1970 | 1.97 | 8900 | 17533000 | Ok | Route
96 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004623 | 2025-03-22 | MUM/Route/107 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/107 IP1 | 650 | 0.65 | 8900 | 5785000 | Ok | Route
96 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004623 | 2025-03-22 | Route55 to Route 107 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity Route55 to Route 107 Connectivity | 600 | 0.6 | 8900 | 5340000 | New Added and CE existing network Present. | Route
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MB6015 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6015 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 907 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 907 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 80 | 0.08 | 16490 | 1319200 | Duplicate PO | Duplicate PO/ POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 3310 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3310 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | BSE Iindia DC | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites BSE Iindia DC | 1000 | 1 | 16490 | 16490000 |  | Additional Scop
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 6369 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6369 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MA2726 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2726 | 70 | 0.07 | 16490 | 1154300 | Duplicate PO | Duplicate PO/ POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | MB6017 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6017 | 70 | 0.07 | 16490 | 1154300 | PO length is greater than Feasibility Length | POP
97 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004624 | 2025-03-22 | 3090 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3090 | 10 | 0.01 | 16490 | 164900 | PO length is less than Feasibility length | POP
98 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004625 | 2025-03-22 | MUM/Route/55 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/55 Cobuilt | 1000 | 1 | 12500 | 12500000 | Actual length 2044 Mtr but PO received 1000 Mtr need to be checked.. | Route
99 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004626 | 2025-03-22 | MUM/Route/107 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/107 Cobuilt | 1768 | 1.768 | 16000 | 28288000 | Ok | Route
99 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004626 | 2025-03-22 | 5342 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5342 | 20 | 0.02 | 16000 | 320000 | Ok | POP
100 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004627 | 2025-03-22 | MA2014 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2014 | 520 | 0.52 | 16490 | 8574800 | Ok | POP
100 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004627 | 2025-03-22 | MA5118 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5118 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA2383 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2383 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA728 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA728 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3258 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3258 | 160 | 0.16 | 16490 | 2638400 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | NSE Mumbai DC | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites NSE Mumbai DC | 500 | 0.5 | 16490 | 8245000 |  | Additional Scop
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4986 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4986 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 358 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 358 | 160 | 0.16 | 16490 | 2638400 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MUM/XNQ/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/XNQ/901 AGG | 100 | 0.1 | 16490 | 1649000 |  | Additional Scop
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4913 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4913 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 4932 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4932 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3120 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3120 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 5604 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5604 | 70 | 0.07 | 16490 | 1154300 | PO length is less than Feasibility length | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | MA4466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4466 | 60 | 0.06 | 16490 | 989400 | Ok | POP
101 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004628 | 2025-03-22 | 3177 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3177 | 20 | 0.02 | 16490 | 329800 | Ok | POP
102 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004629 | 2025-03-25 | MUM/Route/55 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/55 IP1 | 11962 | 11.962 | 8900 | 106461800 | Ok | Route
103 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004630 | 2025-03-22 | MUM/Route/101 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/101 IP1 | 1000 | 1 | 8900 | 8900000 | Need to be checked as route no 101 is of 800 mts only in data base | PO Modification WIP
104 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004631 | 2025-03-22 | MUM/Route/23 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/23 IP1 | 6420 | 6.42 | 8900 | 57138000 | Ok | Route
105 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004632 | 2025-03-22 | MUM/Route/8 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/8 IP1 | 11771 | 11.771 | 8900 | 104761900 | Ok | Route
106 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004633 | 2025-03-22 | MUM_Route_10 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM_Route_10 IP1 | 10280 | 10.28 | 8900 | 91492000 | Ok | Route
107 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MUM/BKC/906 LM | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/BKC/906 LM | 480 | 0.48 | 16490 | 7915200 |  | Additional Scop
107 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MB2378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2378 | 250 | 0.25 | 16490 | 4122500 | PO length is less than Feasibility length | POP
107 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004634 | 2025-03-22 | MUM/Route/108 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/108 Cobuilt | 600 | 0.6 | 16000 | 9600000 | New Added. | Route
108 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004635 | 2025-03-22 | MUM/Route/106 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/106 IP1 | 2200 | 2.2 | 8900 | 19580000 | Route extended but extended portion was budgeted as per Co-built but PO received for IP1. Co-built surveyed length was 809 mt out off 1.9 km total route length | Route
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 2351 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2351 | 50 | 0.05 | 16000 | 800000 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/173 MUM/BHL/909 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/173 MUM/BHL/909 AGG | 550 | 0.55 | 16000 | 8800000 | Ok | Route | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 3023 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3023 | 110 | 0.11 | 16000 | 1760000 | Ok | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MA3597 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA3597 | 110 | 0.11 | 16000 | 1760000 | Ok | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | additional DC Connectivity Netmagic DC7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Netmagic DC7 | 100 | 0.1 | 16000 | 1600000 |  | Additional Scop | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/152 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/152 MUM/TJR/901 AGG | 500 | 0.5 | 16000 | 8000000 | Ok | Route | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1179 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1179 | 50 | 0.05 | 16000 | 800000 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB3249 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB3249 | 90 | 0.09 | 16000 | 1440000 | PO length is greater than Feasibility Length | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 141 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 141 | 80 | 0.08 | 16000 | 1280000 | PO length is greater than Feasibility Length | POP | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/23 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/23 Cobuilt | 1420 | 1.42 | 12500 | 17750000 | out of 15.6 km route length only 1.42 km received. | Route | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/153 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/153 MUM/TJR/901 AGG | 520 | 0.52 | 16000 | 8320000 | Ok | Route | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 5235 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5235 | 50 | 0.05 | 16000 | 800000 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 6056 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 6056 | 80 | 0.08 | 16000 | 1280000 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | 1562 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 1562 | 50 | 0.05 | 16000 | 800000 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1714 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1714 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/148 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/148 MUM/THA/906 AGG | 280 | 0.28 | 16000 | 4480000 | Ok | Route | PO cancelled
109 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MUM/Route/149 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/149 MUM/THA/906 AGG | 400 | 0.4 | 16000 | 6400000 | Ok | Route | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | GPX | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity GPX | 800 | 0.8 | 16000 | 12800000 |  | Additional Scop | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MB1348 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1348 | 110 | 0.11 | 16000 | 1760000 | Ok | POP | PO cancelled
109 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004636 | 2025-03-22 | MA6156 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA6156 | 80 | 0.08 | 16000 | 1280000 | PO length is greater than Feasibility Length | POP | PO cancelled
110 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004637 | 2025-03-22 | MUM/Route/54 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/54 IP1 | 5060 | 5.06 | 8900 | 45034000 | Ok | Route
111 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004638 | 2025-03-22 | MA25 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA25 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
112 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004639 | 2025-03-22 | MUM/Route/80 Mercury Tower | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/80 Mercury Tower | 5070 | 5.07 | 8900 | 45123000 | Ok | Route
113 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004640 | 2025-03-22 | MUM/Route/101 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/101 IP1 | 800 | 0.8 | 8900 | 7120000 | Ok | Route
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/104 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/104 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA1059 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1059 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/103 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/103 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 3054 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3054 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA1885 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1885 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5055 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5055 | 10 | 0.01 | 16490 | 164900 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA6295 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6295 | 30 | 0.03 | 16490 | 494700 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4859 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4859 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5029 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5029 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5451 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5451 | 120 | 0.12 | 16490 | 1978800 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MUM/Route/131 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/131 | 200 | 0.2 | 16490 | 3298000 | Ok | Route
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA6540 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6540 | 270 | 0.27 | 16490 | 4452300 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 5256 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5256 | 150 | 0.15 | 16490 | 2473500 | PO length is greater than Feasibility Length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 2763 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2763 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4847 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4847 | 10 | 0.01 | 16490 | 164900 | Ok | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MB3135 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3135 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | MA4226 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4226 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
114 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004641 | 2025-03-22 | 4981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4981 | 30 | 0.03 | 16490 | 494700 | PO length is less than Feasibility length | POP
115 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004642 | 2025-03-22 | MUM/Route/11 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/11 | 390 | 0.39 | 8900 | 3471000 | Ok | Route
116 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004643 | 2025-03-22 | MUM/Route/108 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/108 IP1 | 2787 | 2.787 | 8900 | 24804300 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/159 Vikroli DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/159 Vikroli DC | 390 | 0.39 | 16000 | 6240000 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/158 Netmagic DC4A | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/158 Netmagic DC4A | 220 | 0.22 | 16000 | 3520000 | Ok | Route
117 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004650 | 2025-03-24 | MUM/Route/25 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/25 | 8500 | 8.5 | 12500 | 106250000 | Ok | Route
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | MB2236 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB2236 | 80 | 0.08 | 16000 | 1280000 | Site Drop by Airtel but PO Received | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | MA2131 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA2131 | 60 | 0.06 | 16000 | 960000 | Ok | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | 5769 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5769 | 280 | 0.28 | 16000 | 4480000 | PO length is greater than Feasibility Length | POP
118 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004651 | 2025-03-24 | 2263 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2263 | 170 | 0.17 | 16000 | 2720000 | Ok | POP
119 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004652 | 2025-03-24 | MUM/Route/170 Hiranandani | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/170 Hiranandani | 1110 | 1.11 | 16000 | 17760000 | Ok | Route
120 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004653 | 2025-03-24 | MUM/Route/139 NetMagic DC 5 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/139 NetMagic DC 5 | 50 | 0.05 | 16490 | 824500 | Ok | Route
120 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004653 | 2025-03-24 | MUM/Route/138 NetMagic DC 5 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/138 NetMagic DC 5 | 50 | 0.05 | 16490 | 824500 | Ok | Route
121 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004654 | 2025-03-24 | MUM/Route/160 RJIO | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/160 RJIO | 1430 | 1.43 | 16000 | 22880000 | Ok | Route
121 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004654 | 2025-03-24 | 1777 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1777 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
122 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004655 | 2025-03-24 | MUM/Route/140 NetMagic DC 6 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/140 NetMagic DC 6 | 70 | 0.07 | 16490 | 1154300 | Ok | Route
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MB1917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1917 | 70 | 0.07 | 16490 | 1154300 | Duplicate PO | Duplicate PO/ POP
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MA4450 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4450 | 20 | 0.02 | 16490 | 329800 | Ok | POP
123 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004656 | 2025-03-24 | MA5223 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5223 | 200 | 0.2 | 16490 | 3298000 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 5618 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5618 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MA5656 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5656 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MB2246 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2246 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 1694 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1694 | 200 | 0.2 | 16490 | 3298000 | PO length is less than Feasibility length | POP
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | Mercury Tower AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mercury Tower AGG | 1200 | 1.2 | 16000 | 19200000 |  | Additional Scop
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/75 Colt | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/75 Colt | 563 | 0.563 | 16000 | 9008000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | Equinix | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Equinix | 563 | 0.563 | 16000 | 9008000 |  | Additional Scop
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/68 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/68 | 3950 | 3.95 | 16000 | 63200000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MA4147 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4147 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/118 Sift Airoli and Lumia | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/118 Sift Airoli and Lumia Airoli | 720 | 0.72 | 16000 | 11520000 | Ok | Route
124 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | MUM/Route/74 Equininx | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/74 Equininx | 390 | 0.39 | 16000 | 6240000 | Ok | Route
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | CapitaLand Data Centre CDC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity CapitaLand Data Centre CDC | 180 | 0.18 | 16000 | 2880000 |  | Additional Scop
124 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004657 | 2025-03-24 | 109 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 109 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP
125 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004658 | 2025-03-24 | 4750 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4750 | 330 | 0.33 | 16490 | 5441700 | Ok | POP
125 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004658 | 2025-03-24 | MUM/Route/58 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/58 | 4790 | 4.79 | 12500 | 59875000 | Ok | Route
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MB6371 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6371 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
126 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MUM/Route/57 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/57 | 4860 | 4.86 | 12500 | 60750000 | Ok | Route
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MA3485 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3485 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
126 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004659 | 2025-03-24 | MB1718 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1718 | 160 | 0.16 | 16490 | 2638400 | PO length is less than Feasibility length | POP
127 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004660 | 2025-03-24 | MUM/Route/172 Web Works DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/172 Web Works DC | 110 | 0.11 | 16000 | 1760000 | Ok | Route
127 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004660 | 2025-03-24 | MUM/Route/172 Web Works DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/172 Web Works DC | 110 | 0.11 | 16000 | 1760000 | Ok | Route
128 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MUM/Route/36 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/36 | 360 | 0.36 | 12500 | 4500000 | Route length decreased from 6032 to 3600 according to the new KML but wrong po is issued of length 360 mtr. | Route | PO cancelled
128 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MA5287 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5287 | 150 | 0.15 | 16490 | 2473500 | PO Cancelled | POP | PO cancelled
128 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004661 | 2025-03-24 | MA4035 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4035 | 90 | 0.09 | 16490 | 1484100 | PO Cancelled | POP | PO cancelled
129 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004662 | 2025-03-24 | MUM_Route_31 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM_Route_31 | 970 | 0.97 | 12500 | 12125000 | Ok | Route
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB1595 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1595 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | Satyam AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Satyam AGG | 200 | 0.2 | 16490 | 3298000 |  | Additional Scop
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 6359 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6359 | 130 | 0.13 | 16490 | 2143700 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA1165 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1165 | 290 | 0.29 | 16490 | 4782100 | PO length is greater than Feasibility Length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4506 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4506 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB2462 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2462 | 80 | 0.08 | 16490 | 1319200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4213 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA3996 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3996 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MA2586 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2586 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 2731 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2731 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
130 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MUM/Route/19 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/19 | 5920 | 5.92 | 12500 | 74000000 | Ok | Route
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | 4474 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4474 | 80 | 0.08 | 16490 | 1319200 | PO length is less than Feasibility length | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB1882 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1882 | 60 | 0.06 | 16490 | 989400 | Ok | POP
130 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004663 | 2025-03-24 | MB2224 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2224 | 60 | 0.06 | 16490 | 989400 | Ok | POP
131 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | 4941 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4941 | 150 | 0.15 | 16490 | 2473500 | Ok | POP
131 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | MUM/Route/124 MUM/CTC/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/124 MUM/CTC/901 AGG | 200 | 0.2 | 16000 | 3200000 | Length is decreased 1.37 to 0.20km | Route
131 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | 1303 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1303 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
131 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004664 | 2025-03-24 | MUM/Route/123 MUM/CTC/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/123 MUM/CTC/901 AGG | 1500 | 1.5 | 16000 | 24000000 | Length is decreased 2.22 to 1.50km | Route
132 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004665 | 2025-03-24 | MUM/Route/49 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/49 | 2800 | 2.8 | 12500 | 35000000 | Ok | Route
132 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004665 | 2025-03-24 | MB2282 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2282 | 60 | 0.06 | 16490 | 989400 | Ok | POP
133 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004666 | 2025-03-24 | MUM/Route/169 DC Yotta | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/169 DC Yotta | 1110 | 1.11 | 16000 | 17760000 | Ok but Orignal route length of 561 mtr but po received 1100 mts | Route
134 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004667 | 2025-03-24 | MUM/Route/150 Lumina Aroli | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/150 Lumina Aroli CapGemini (CG) campus | 200 | 0.2 | 16000 | 3200000 | Ok | Route
134 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004667 | 2025-03-24 | MUM/Route/151 Lumina Aroli | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/151 Lumina Aroli CapGemini (CG) campus | 220 | 0.22 | 16000 | 3520000 | Ok | Route
135 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004668 | 2025-03-24 | MUM/Route/157 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/157 | 1930 | 1.93 | 16000 | 30880000 | Ok | Route
136 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | MUM/Route/30 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/30 | 1150 | 1.15 | 12500 | 14375000 | Ok | Route
136 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | 6502 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6502 | 260 | 0.26 | 16490 | 4287400 | PO length is less than Feasibility length | POP
136 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004669 | 2025-03-24 | MA1878 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1878 | 60 | 0.06 | 16490 | 989400 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/Route/45 Cobuilt | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/45 Cobuilt | 6432 | 6.432 | 12500 | 80400000 | Ok | Route
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/STS/901 AGG | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/STS/901 AGG | 150 | 0.15 | 16490 | 2473500 |  | Additional Scop
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MB1711 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1711 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA2824 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2824 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 2213 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2213 | 350 | 0.35 | 16490 | 5771500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MUM/Route/24 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/24 | 960 | 0.96 | 16000 | 15360000 | Ok | Route
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA638 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA638 | 200 | 0.2 | 16490 | 3298000 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MB2815 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2815 | 180 | 0.18 | 16490 | 2968200 | PO length is greater than Feasibility Length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 496 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 496 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 3817 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3817 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | MA1907 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1907 | 20 | 0.02 | 16490 | 329800 | PO length is less than Feasibility length | POP
137 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004670 | 2025-03-24 | 1677 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1677 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
138 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004671 | 2025-03-24 | MUM/Route/35 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/35 | 360 | 0.36 | 12500 | 4500000 | Ok | Route
138 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004671 | 2025-03-24 | 278 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 278 | 70 | 0.07 | 12500 | 875000 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MB2649 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2649 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA5673 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5673 | 40 | 0.04 | 16490 | 659600 | PO length is less than Feasibility length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 1536 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1536 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA2578 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2578 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MA4315 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4315 | 100 | 0.1 | 16490 | 1649000 | PO length is greater than Feasibility Length | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 2730 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2730 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | 1532 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1532 | 70 | 0.07 | 16490 | 1154300 | Ok | POP
139 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004672 | 2025-03-24 | MUM/Route/97 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/97 | 12000 | 12 | 12500 | 150000000 | Ok | Route
140 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004673 | 2025-03-24 | MUM/Route/156 Supreme Chamber | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/156 Supreme Chamber | 500 | 0.5 | 16000 | 8000000 | Ok | Route
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MB1103 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MB1103 | 70 | 0.07 | 16000 | 1120000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MUM/Route/137 Equnix MB GBX 3 DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/137 Equnix MB GBX 3 DC | 300 | 0.3 | 16000 | 4800000 | Ok | Route
141 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MUM/Route/38 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/38 | 3080 | 3.08 | 12500 | 38500000 | Ok | Route
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA5557 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA5557 | 150 | 0.15 | 16000 | 2400000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA4248 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4248 | 250 | 0.25 | 16000 | 4000000 | PO length is less than Feasibility length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | 3075 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3075 | 260 | 0.26 | 16000 | 4160000 | PO length is greater than Feasibility Length | POP
141 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004674 | 2025-03-24 | MA4846 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4846 | 120 | 0.12 | 16000 | 1920000 | PO length is less than Feasibility length | POP
142 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004675 | 2025-03-24 | MUM/Route/89 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/89 | 4890 | 4.89 | 12500 | 61125000 | Ok | Route
143 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004676 | 2025-03-24 | MUM/Route/147 MUM/THA/916 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/147 MUM/THA/916 | 180 | 0.18 | 16490 | 2968200 | New Added. | Route
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA1036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1036 | 280 | 0.28 | 16490 | 4617200 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 6094 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6094 | 170 | 0.17 | 16490 | 2803300 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA3495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3495 | 110 | 0.11 | 16490 | 1813900 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA5212 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5212 | 280 | 0.28 | 16490 | 4617200 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 4378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4378 | 60 | 0.06 | 16490 | 989400 | PO length is less than Feasibility length | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA1751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1751 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 3354 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3354 | 110 | 0.11 | 16490 | 1813900 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 2587 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2587 | 120 | 0.12 | 16490 | 1978800 | PO length is less than Feasibility length | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA4138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4138 | 50 | 0.05 | 16490 | 824500 | PO length is less than Feasibility length | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MA2152 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2152 | 110 | 0.11 | 16490 | 1813900 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | MB6417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6417 | 220 | 0.22 | 16490 | 3627800 | Ok | POP | PO cancelled
144 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004677 | 2025-03-24 | 5357 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5357 | 360 | 0.36 | 16490 | 5936400 | PO length is less than Feasibility length | POP | PO cancelled
145 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004678 | 2025-03-24 | MUM/Route/45 IP1 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/45 IP1 | 11930 | 11.93 | 8900 | 106177000 | Ok | Route
146 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004679 | 2025-03-24 | MUM/Route/134 Netmagic DC4 DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/134 Netmagic DC4 DC | 1370 | 1.37 | 16000 | 21920000 | Ok | Route
147 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | Mum/Route/46 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mum/Route/46 | 480 | 0.48 | 16000 | 7680000 | Ok | Route
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB5991 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5991 | 200 | 0.2 | 16490 | 3298000 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 6224 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6224 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB1266 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1266 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MUM/Route/81 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/81 | 12010 | 12.01 | 12500 | 150125000 | Ok..70 mtr length increased. | Route
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB2459 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2459 | 150 | 0.15 | 16490 | 2473500 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB3220 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3220 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MA2619 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2619 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB1795 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1795 | 170 | 0.17 | 16490 | 2803300 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB2903 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2903 | 190 | 0.19 | 16490 | 3133100 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | MB3271 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3271 | 100 | 0.1 | 16490 | 1649000 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2253 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2253 | 60 | 0.06 | 16490 | 989400 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 1392 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1392 | 180 | 0.18 | 16490 | 2968200 | PO length is less than Feasibility length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 4973 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4973 | 380 | 0.38 | 16490 | 6266200 | PO length is greater than Feasibility Length | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2342 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2342 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
147 | Co-Built | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004680 | 2025-03-24 | 2234 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2234 | 610 | 0.61 | 16490 | 10058900 | Ok | POP
148 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004681 | 2025-03-24 | MUM/Route/48 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/48 | 3300 | 3.3 | 8900 | 29370000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/168 LUMINA Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/168 LUMINA Mahape | 110 | 0.11 | 16000 | 1760000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/167 LUMINA Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/167 LUMINA Mahape | 110 | 0.11 | 16000 | 1760000 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/163 NAV1C NAV1D | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/163 NAV1C NAV1D | 231 | 0.231 | 12500 | 2887500 | Ok | Route
149 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004682 | 2025-03-24 | MUM/Route/164 and 165 Mahape | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/164 and 165 Mahape NAV1A | 560 | 0.56 | 16000 | 8960000 | Ok | Route
150 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004683 | 2025-03-24 | MUM/Route/155 Digital Edge DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/155 Digital Edge DC | 1500 | 1.5 | 16000 | 24000000 | Feasibility needs to be recheck as original routes has been changed. | Route
151 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004684 | 2025-03-24 | MUM/Route_/25 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route_/25 | 190 | 0.19 | 16490 | 3133100 | Ok | Route
152 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004685 | 2025-03-24 | MUM/Route/162 MAP/901/AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/162 MAP/901/AGG | 180 | 0.18 | 16000 | 2880000 | Ok | Route
152 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004685 | 2025-03-24 | MUM/Route/161 MAP/901/AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/161 MAP/901/AGG | 300 | 0.3 | 16000 | 4800000 | Ok | Route
153 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004686 | 2025-03-24 | MUM/Route/133 MUM/SPA/902 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MUM/Route/133 MUM/SPA/902 | 120 | 0.12 | 16490 | 1978800 | Ok | Route
154 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004689 | 2025-03-24 | MB3106 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3106 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
155 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004690 | 2025-03-24 | MA312 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA312 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
156 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004691 | 2025-03-24 | MA4100 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4100 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
157 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004692 | 2025-03-24 | 148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 148 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
158 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004693 | 2025-03-24 | MA183 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA183 | 106 | 0.106 | 16490 | 1747940 | Ok | POP
159 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004694 | 2025-03-24 | 2510 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2510 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
160 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004695 | 2025-03-24 | 596 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 596 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
161 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004696 | 2025-03-24 | 1659 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1659 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
162 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004697 | 2025-03-24 | MA1811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1811 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
163 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004698 | 2025-03-24 | MA184 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA184 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
164 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004699 | 2025-03-24 | 1000 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1000 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
165 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004700 | 2025-03-24 | 1788 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1788 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
166 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004701 | 2025-03-24 | 5541 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5541 | 235 | 0.235 | 16490 | 3875150 | Ok | POP
167 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004702 | 2025-03-24 | 5286 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5286 | 56 | 0.056 | 16490 | 923440 | Ok | POP
168 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004703 | 2025-03-24 | 1342 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1342 | 56 | 0.056 | 16490 | 923440 | Ok | POP
169 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004704 | 2025-03-24 | MA4632 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4632 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
170 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004705 | 2025-03-24 | 142 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 142 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
171 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004706 | 2025-03-24 | MA2816 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2816 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
172 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004707 | 2025-03-24 | 3604 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3604 | 56 | 0.056 | 16490 | 923440 | Ok | POP
173 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004708 | 2025-03-24 | 744 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 744 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
174 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004709 | 2025-03-24 | 1008 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1008 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
175 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004710 | 2025-03-24 | 2322 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2322 | 101 | 0.101 | 16490 | 1665490 | Ok | POP
176 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004711 | 2025-03-24 | 174 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 174 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
177 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004712 | 2025-03-24 | MA6274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6274 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
178 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004713 | 2025-03-24 | 2628 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2628 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
179 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004714 | 2025-03-24 | 4234 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4234 | 56 | 0.056 | 16490 | 923440 | Ok | POP
180 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004715 | 2025-03-24 | MB4699 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4699 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
181 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004716 | 2025-03-24 | MA5238 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5238 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
182 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004717 | 2025-03-24 | MB2495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2495 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
183 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004718 | 2025-03-24 | MB3478 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3478 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
184 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004719 | 2025-03-24 | MA4247 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4247 | 179 | 0.179 | 16490 | 2951710 | Ok | POP
185 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004720 | 2025-03-24 | MA4786 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4786 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
186 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004721 | 2025-03-24 | 341 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 341 | 121 | 0.121 | 16490 | 1995290 | PO length is greater than Feasibility Length | POP
187 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004722 | 2025-03-24 | MA366 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA366 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
188 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004723 | 2025-03-24 | MA4828 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4828 | 231 | 0.231 | 16490 | 3809190 | Ok | POP
189 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004724 | 2025-03-24 | 3107 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3107 | 291 | 0.291 | 16490 | 4798590 | Ok | POP
190 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004725 | 2025-03-24 | 434 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 434 | 56 | 0.056 | 16490 | 923440 | Ok | POP
191 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004726 | 2025-03-24 | MB2863 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2863 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
192 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004727 | 2025-03-24 | MA2512 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2512 | 56 | 0.056 | 16490 | 923440 | Ok | POP
193 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004728 | 2025-03-24 | 356 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 356 | 123 | 0.123 | 16490 | 2028270 | Ok | POP
194 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004729 | 2025-03-24 | 3151 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3151 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
195 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004730 | 2025-03-24 | MA1811 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1811 | 123 | 0.123 | 16490 | 2028270 | Duplicate PO | Duplicate PO/ POP
196 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004737 | 2025-03-25 | 4014 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4014 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
197 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004738 | 2025-03-25 | MA2866 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2866 | 246 | 0.246 | 16490 | 4056540 | Ok | POP
198 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004739 | 2025-03-25 | MB2460 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2460 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
199 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004740 | 2025-03-25 | MA73 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA73 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
200 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004742 | 2025-03-25 | 274 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 274 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
201 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004743 | 2025-03-25 | 4495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4495 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
202 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004744 | 2025-03-25 | 5979 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5979 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
203 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004745 | 2025-03-25 | 6169 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6169 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
204 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004746 | 2025-03-25 | MA3916 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3916 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
205 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004747 | 2025-03-25 | MA4977 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4977 | 258 | 0.258 | 16490 | 4254420 | Ok | POP
206 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004748 | 2025-03-25 | 5592 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5592 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
207 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004749 | 2025-03-25 | MB4482 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4482 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
208 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004750 | 2025-03-25 | MB2505 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2505 | 257 | 0.257 | 16490 | 4237930 | Ok | POP
209 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004751 | 2025-03-25 | MA5495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5495 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
210 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004752 | 2025-03-25 | MA3055 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3055 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
211 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004753 | 2025-03-25 | 2798 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2798 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
212 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004754 | 2025-03-25 | MA2049 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2049 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
213 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004755 | 2025-03-25 | 3901 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3901 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
214 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004756 | 2025-03-25 | MB1481 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1481 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
215 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004757 | 2025-03-25 | MA943 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA943 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
216 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004758 | 2025-03-25 | 5682 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5682 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
217 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004759 | 2025-03-25 | 2122 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2122 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
218 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004761 | 2025-03-25 | MB3311 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3311 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
219 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004762 | 2025-03-25 | 5980 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5980 | 45 | 0.045 | 16490 | 742050 | Ok | POP
220 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004763 | 2025-03-25 | 1251 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1251 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
221 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004765 | 2025-03-25 | MUM/Route/50 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/50 | 6030 | 6.03 | 8900 | 53667000 | Ok | Route
222 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004766 | 2025-03-25 | 4917 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4917 | 11 | 0.011 | 16490 | 181390 | Ok | POP
223 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004767 | 2025-03-25 | 5709 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5709 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
224 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004768 | 2025-03-25 | MA4535 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4535 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
225 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004769 | 2025-03-25 | 2610 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2610 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
226 | IP1 | Route | BAL-TNG-NLD--Maharashtra/PUR/10004771 | 2025-03-25 | MUM/Route/90 | B0STDDRF4 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:IRU Lease 2*96F Dark Fiber Connectivity on IP1 model for Mumbai Intracity MUM/Route/90 IP1 | 4900 | 4.9 | 8900 | 43610000 | 4.9km po received 14.27 co-built PO awaited. | Route
227 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004773 | 2025-03-25 | 4719 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4719 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
228 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004774 | 2025-03-25 | 6520 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6520 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
229 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004776 | 2025-03-26 | 5525 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5525 | 338 | 0.338 | 16490 | 5573620 | PO length is less than Feasibility length | POP
230 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004777 | 2025-03-26 | 4381 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4381 | 56 | 0.056 | 16490 | 923440 | Ok | POP
231 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004778 | 2025-03-26 | 4883 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4883 | 50 | 0.05 | 16490 | 824500 | Ok | POP
232 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004779 | 2025-03-26 | 2010 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2010 | 251 | 0.251 | 16490 | 4138990 | Ok | POP
233 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004780 | 2025-03-26 | 5436 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5436 | 106 | 0.106 | 16490 | 1747940 | Ok | POP
234 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004781 | 2025-03-26 | 3330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3330 | 67 | 0.067 | 16490 | 1104830 | Duplicate PO | Duplicate PO/ POP
235 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004782 | 2025-03-26 | 3589 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3589 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
236 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004783 | 2025-03-26 | MA28 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA28 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
237 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004784 | 2025-03-26 | 1264 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1264 | 30 | 0.03 | 16490 | 494700 | PO length is greater than Feasibility Length | POP
238 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004785 | 2025-03-26 | 6323 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6323 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
239 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004786 | 2025-03-26 | MB2765 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2765 | 560 | 0.56 | 16490 | 9234400 | Ok | POP
240 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004787 | 2025-03-26 | MA2398 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2398 | 346 | 0.346 | 16490 | 5705540 | Ok | POP
241 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004788 | 2025-03-26 | MB3183 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3183 | 40 | 0.04 | 16490 | 659600 | PO length is greater than Feasibility Length | POP
242 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004789 | 2025-03-26 | MB2489 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2489 | 34 | 0.034 | 16490 | 560660 | Ok | POP
243 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004790 | 2025-03-26 | 3645 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3645 | 476 | 0.476 | 16490 | 7849240 | Ok | POP
244 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004791 | 2025-03-26 | 5831 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5831 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
245 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004792 | 2025-03-26 | MA4416 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4416 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
246 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004793 | 2025-03-26 | 5687 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5687 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
247 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004794 | 2025-03-26 | MB2484 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2484 | 30 | 0.03 | 16490 | 494700 | Ok | POP
248 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004795 | 2025-03-26 | 400 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 400 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
249 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004796 | 2025-03-26 | MB4330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4330 | 228 | 0.228 | 16490 | 3759720 | Ok | POP
250 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004797 | 2025-03-26 | MB5491 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB5491 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
251 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004798 | 2025-03-26 | MA3580 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3580 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
252 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004799 | 2025-03-26 | 721 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 721 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
253 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004800 | 2025-03-26 | 5590 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5590 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
254 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004801 | 2025-03-26 | 2958 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2958 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
255 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004802 | 2025-03-26 | MA649 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA649 | 542 | 0.542 | 16490 | 8937580 | Ok | POP
256 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004803 | 2025-03-26 | MA129 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA129 | 28 | 0.028 | 16490 | 461720 | Ok | POP
257 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004804 | 2025-03-26 | 334 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 334 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
258 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004805 | 2025-03-26 | MB1728 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1728 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
259 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004806 | 2025-03-26 | 4198 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4198 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
260 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004807 | 2025-03-26 | 4534 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4534 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
261 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004808 | 2025-03-26 | 1308 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1308 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
262 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004809 | 2025-03-26 | 8 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 8 | 171 | 0.171 | 16490 | 2819790 | Ok | POP
263 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004810 | 2025-03-26 | 4609 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4609 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
264 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004811 | 2025-03-26 | 1734 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1734 | 302 | 0.302 | 16490 | 4979980 | Ok | POP
265 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004812 | 2025-03-26 | MB3457 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3457 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
266 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004813 | 2025-03-26 | 379 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 379 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
267 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004814 | 2025-03-26 | MA4076 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4076 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
268 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004815 | 2025-03-26 | 5886 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5886 | 140 | 0.14 | 16490 | 2308600 | PO length is greater than Feasibility Length | POP
269 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004816 | 2025-03-26 | 2372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2372 | 360 | 0.36 | 16490 | 5936400 | PO length is greater than Feasibility Length | POP
270 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004817 | 2025-03-26 | Business/156/205663 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Business/156/205663 | 55 | 0.055 | 16490 | 906950 |  | Additional Scop
271 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004818 | 2025-03-26 | 4449 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4449 | 1202 | 1.202 | 16490 | 19820980 | PO length is greater than Feasibility Length | POP
272 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004819 | 2025-03-26 | MA4114 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4114 | 726 | 0.726 | 16490 | 11971740 | Ok | POP
273 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004820 | 2025-03-26 | 2477 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2477 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
274 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004821 | 2025-03-26 | MA2877 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2877 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
275 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004822 | 2025-03-26 | MA4659 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4659 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
276 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004823 | 2025-03-26 | MA2282 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2282 | 90 | 0.09 | 16490 | 1484100 | Ok | POP
277 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004824 | 2025-03-26 | MA1794 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1794 | 187 | 0.187 | 16490 | 3083630 | Ok | POP
278 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004825 | 2025-03-26 | 3123 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3123 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
279 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004826 | 2025-03-26 | MA3442 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3442 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
280 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004827 | 2025-03-26 | 6021 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6021 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
281 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004828 | 2025-03-26 | MA4011 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4011 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
282 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004829 | 2025-03-26 | MB640 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB640 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
283 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004830 | 2025-03-26 | MA1048 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1048 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
284 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004831 | 2025-03-26 | 3411 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3411 | 17 | 0.017 | 16490 | 280330 | Ok | POP
285 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004832 | 2025-03-26 | 1371 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1371 | 66 | 0.066 | 16490 | 1088340 | Ok | POP
286 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004833 | 2025-03-26 | MA2115 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2115 | 34 | 0.034 | 16490 | 560660 | PO length is greater than Feasibility Length | POP
287 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004834 | 2025-03-26 | MB1615 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1615 | 482 | 0.482 | 16490 | 7948180 | Ok | POP
288 | Co-Built | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004835 | 2025-03-26 | 6195 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6195 | 1 | 0.001 | 16490 | 16490 | PO length is less than Feasibility length | POP
289 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004836 | 2025-03-26 | MB2355 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2355 | 102 | 0.102 | 16490 | 1681980 | Ok | POP
290 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004837 | 2025-03-26 | 4501 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4501 | 64 | 0.064 | 16490 | 1055360 | Ok | POP
291 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004838 | 2025-03-26 | MB6370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6370 | 33 | 0.033 | 16490 | 544170 | Ok | POP
292 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004839 | 2025-03-26 | MB2509 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2509 | 102 | 0.102 | 16490 | 1681980 | PO length is greater than Feasibility Length | POP
293 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004840 | 2025-03-26 | 5237 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5237 | 11 | 0.011 | 16490 | 181390 | Ok | POP
294 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004841 | 2025-03-26 | 4409 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4409 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
295 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004842 | 2025-03-26 | MA5099 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5099 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
296 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004843 | 2025-03-26 | MB1155 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1155 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
297 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004844 | 2025-03-26 | MA72 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA72 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
298 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004845 | 2025-03-26 | MB2981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2981 | 258 | 0.258 | 16490 | 4254420 | Ok | POP
299 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004846 | 2025-03-26 | MA4012 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4012 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
300 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004847 | 2025-03-26 | 2317 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2317 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
301 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004848 | 2025-03-26 | 3071 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3071 | 157 | 0.157 | 16490 | 2588930 | Ok | POP
302 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004849 | 2025-03-26 | MB2148 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2148 | 45 | 0.045 | 16490 | 742050 | Ok | POP
303 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004850 | 2025-03-26 | MA6227 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6227 | 154 | 0.154 | 16490 | 2539460 | Ok | POP
304 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004851 | 2025-03-26 | 5504 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5504 | 25 | 0.025 | 16490 | 412250 | Ok | POP
305 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004852 | 2025-03-26 | MB4281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB4281 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
306 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004853 | 2025-03-26 | MB1084 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1084 | 220 | 0.22 | 16490 | 3627800 | Ok | POP
307 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004854 | 2025-03-26 | Business/156/205663 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites Business/156/205663 | 51 | 0.051 | 16490 | 840990 |  | Additional Scop
308 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004855 | 2025-03-26 | 2931 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2931 | 372 | 0.372 | 16490 | 6134280 | PO length is less than Feasibility length | POP
309 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004856 | 2025-03-26 | MA928 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA928 | 368 | 0.368 | 16490 | 6068320 | Ok | POP
310 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004857 | 2025-03-26 | 297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 297 | 297 | 0.297 | 16490 | 4897530 | Duplicate PO | Duplicate PO/ POP
311 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004858 | 2025-03-26 | MA2545 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2545 | 113 | 0.113 | 16490 | 1863370 | PO length is greater than Feasibility Length | POP
312 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004859 | 2025-03-26 | 1924 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1924 | 1924 | 1.924 | 16490 | 31726760 | PO length is greater than Feasibility Length | POP
313 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004860 | 2025-03-26 | 6006 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6006 | 6006 | 6.006 | 16490 | 99038940 | PO length is greater than Feasibility Length | POP
314 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004861 | 2025-03-26 | 5627 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5627 | 161 | 0.161 | 16490 | 2654890 | Ok | POP
315 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004862 | 2025-03-26 | 3398 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3398 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
316 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004863 | 2025-03-26 | 1387 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1387 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
317 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004864 | 2025-03-26 | 1027 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1027 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
318 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004865 | 2025-03-26 | MA3372 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3372 | 45 | 0.045 | 16490 | 742050 | Ok | POP
319 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004866 | 2025-03-26 | MA1044 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1044 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
320 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004867 | 2025-03-26 | MA6019 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6019 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
321 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004868 | 2025-03-26 | MA4127 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4127 | 146 | 0.146 | 16490 | 2407540 | Ok | POP
322 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004869 | 2025-03-26 | MB1608 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1608 | 56 | 0.056 | 16490 | 923440 | Ok | POP
323 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004870 | 2025-03-26 | MA3759 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3759 | 450 | 0.45 | 16490 | 7420500 | Ok | POP
324 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004871 | 2025-03-26 | MA4735 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4735 | 858 | 0.858 | 16490 | 14148420 | Ok | POP
325 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004872 | 2025-03-26 | MA2370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2370 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
326 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004873 | 2025-03-26 | MB1585 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1585 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
327 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004874 | 2025-03-26 | 3330 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3330 | 45 | 0.045 | 16490 | 742050 | PO length is greater than Feasibility Length | POP
328 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004875 | 2025-03-26 | MB3226 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3226 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
329 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004876 | 2025-03-26 | MA3670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3670 | 67 | 0.067 | 16490 | 1104830 | Ok | POP
330 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004877 | 2025-03-26 | MB1311 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1311 | 373 | 0.373 | 16490 | 6150770 | Ok | POP
331 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004878 | 2025-03-26 | MA6498 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6498 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
332 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004879 | 2025-03-26 | 3386 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3386 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
333 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004880 | 2025-03-26 | MB1591 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1591 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
334 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004881 | 2025-03-26 | MA4210 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4210 | 11 | 0.011 | 16490 | 181390 | Ok | POP
335 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004882 | 2025-03-26 | MA1621 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1621 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
336 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004883 | 2025-03-26 | 4337 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4337 | 133 | 0.133 | 16490 | 2193170 | PO length is less than Feasibility length | POP
337 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004884 | 2025-03-26 | MA2576 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2576 | 39 | 0.039 | 16490 | 643110 | Ok | POP
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | MA4640 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MA4640 | 70 | 0.07 | 12500 | 875000 | PO length is greater than Feasibility Length | POP | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 583 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 583 | 60 | 0.06 | 12500 | 750000 | PO length is less than Feasibility length | POP | PO cancelled
338 |  | Route | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | MUM/Route/166 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/166 Vashi DC | 1684 | 1.684 | 12500 | 21050000 | Ok | Route | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 5814 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 5814 | 180 | 0.18 | 12500 | 2250000 | Ok | POP | PO cancelled
338 |  | New Add | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 1614 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 1614 | 300 | 0.3 | 12500 | 3750000 |  | Additional Scop | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | Sapata Sangam AGG | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model Sapata Sangam AGG | 1200 | 1.2 | 12500 | 15000000 |  | Additional Scop | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 5307 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 5307 | 300 | 0.3 | 12500 | 3750000 | Ok | POP | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 3625 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 3625 | 50 | 0.05 | 12500 | 625000 | PO length is less than Feasibility length | POP | PO cancelled
338 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004741 | 2025-03-25 | 2475 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model 2475 | 60 | 0.06 | 12500 | 750000 | Ok | POP | PO cancelled
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3827 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3827 | 22 | 0.022 | 16490 | 362780 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB3510 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3510 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3132 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3132 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA1336 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1336 | 11 | 0.011 | 16490 | 181390 | PO length is less than Feasibility length | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB2632 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2632 | 123 | 0.123 | 16490 | 2028270 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3273 | 460 | 0.46 | 16490 | 7585400 | Duplicate PO | Duplicate PO/ POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4936 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4936 | 25 | 0.025 | 16490 | 412250 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA4575 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4575 | 286 | 0.286 | 16490 | 4716140 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 1797 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1797 | 246 | 0.246 | 16490 | 4056540 | Duplicate PO | Duplicate PO/ POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 370 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 370 | 66 | 0.066 | 16490 | 1088340 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA3828 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3828 | 682 | 0.682 | 16490 | 11246180 | PO length is less than Feasibility length | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 880 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 880 | 420 | 0.42 | 16490 | 6925800 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3144 | 480 | 0.48 | 16490 | 7915200 | Duplicate PO | Duplicate PO/ POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3128 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3128 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 5395 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5395 | 38 | 0.038 | 16490 | 626620 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 5508 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5508 | 435 | 0.435 | 16490 | 7173150 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MA1156 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1156 | 50 | 0.05 | 16490 | 824500 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 6281 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6281 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4081 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4081 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 1297 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1297 | 422 | 0.422 | 16490 | 6958780 | PO length is less than Feasibility length | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | MB2367 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2367 | 143 | 0.143 | 16490 | 2358070 | Ok | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 3099 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3099 | 517 | 0.517 | 16490 | 8525330 | PO length is less than Feasibility length | POP
339 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004760 | 2025-03-25 | 4690 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4690 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2 | 78 | 0.078 | 16490 | 1286220 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 1670 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1670 | 104 | 0.104 | 16490 | 1714960 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4088 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4088 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA1840 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1840 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2736 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2736 | 22 | 0.022 | 16490 | 362780 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 2643 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2643 | 16 | 0.016 | 16490 | 263840 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MB2466 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2466 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 5158 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5158 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4546 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4546 | 200 | 0.2 | 16490 | 3298000 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 194 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 194 | 99 | 0.099 | 16490 | 1632510 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5407 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5407 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4998 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4998 | 300 | 0.3 | 16490 | 4947000 | PO length is less than Feasibility length | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA3675 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3675 | 187 | 0.187 | 16490 | 3083630 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5034 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5034 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA2088 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2088 | 58 | 0.058 | 16490 | 956420 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA5982 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5982 | 11 | 0.011 | 16490 | 181390 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | MA981 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA981 | 110 | 0.11 | 16490 | 1813900 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 4093 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4093 | 165 | 0.165 | 16490 | 2720850 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 1474 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1474 | 33 | 0.033 | 16490 | 544170 | Ok | POP
340 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004770 | 2025-03-25 | 636 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 636 | 253 | 0.253 | 16490 | 4171970 | Ok | POP
341 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004772 | 2025-03-25 | MA2181 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2181 | 400 | 0.4 | 16490 | 6596000 | Ok | POP
341 |  | Route LM | BAL-TNG-NLD--Maharashtra/PUR/10004772 | 2025-03-25 | MB3667 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3667 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1640 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1640 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA5750 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5750 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 855 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 855 | 168 | 0.168 | 16490 | 2770320 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA751 | 784 | 0.784 | 16490 | 12928160 | PO length is greater than Feasibility Length | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1490 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1490 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3273 | 480 | 0.48 | 16490 | 7915200 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3144 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3144 | 460 | 0.46 | 16490 | 7585400 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 3463 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3463 | 672 | 0.672 | 16490 | 11081280 | PO length is greater than Feasibility Length | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 273 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 273 | 448 | 0.448 | 16490 | 7387520 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 4971 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4971 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1365 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1365 | 134 | 0.134 | 16490 | 2209660 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 6479 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6479 | 190 | 0.19 | 16490 | 3133100 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA960 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA960 | 235 | 0.235 | 16490 | 3875150 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB2983 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB2983 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA1813 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1813 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 4971 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4971 | 100 | 0.1 | 16490 | 1649000 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 1797 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1797 | 460 | 0.46 | 16490 | 7585400 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 6087 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6087 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | 247 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 247 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB3502 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3502 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB1785 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1785 | 163 | 0.163 | 16490 | 2687870 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA3567 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3567 | 280 | 0.28 | 16490 | 4617200 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MB1584 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1584 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
342 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004888 | 2025-03-26 | MA3897 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3897 | 224 | 0.224 | 16490 | 3693760 | Ok | POP
343 |  | Fibmax | BAL-TNG-NLD--Maharashtra/PUR/10004736 | 2025-03-26 | MA3832 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3832 | 112 | 0.112 | 16490 | 1846880 | Ok | POP
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 2351 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2351 | 50 | 0.05 | 16490 | 824500 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/173 MUM/BHL/909 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/173 MUM/BHL/909 AGG | 550 | 0.55 | 16000 | 8800000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MB1348 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1348 | 110 | 0.11 | 16490 | 1813900 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 5235 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5235 | 50 | 0.05 | 16490 | 824500 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 1562 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 1562 | 50 | 0.05 | 16490 | 824500 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 6056 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6056 | 80 | 0.08 | 16490 | 1319200 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MA6156 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA6156 | 80 | 0.08 | 16490 | 1319200 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/153 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/153 MUM/TJR/901 AGG | 520 | 0.52 | 16000 | 8320000 | Ok | Route
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MB1714 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1714 | 60 | 0.06 | 16490 | 989400 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MB1179 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB1179 | 50 | 0.05 | 16490 | 824500 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 3023 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3023 | 110 | 0.11 | 16490 | 1813900 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | 141 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 141 | 80 | 0.08 | 16490 | 1319200 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/149 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/149 MUM/THA/906 AGG | 400 | 0.4 | 16000 | 6400000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Fibmax sites GPX | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites GPX | 800 | 0.8 | 16490 | 13192000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MA3597 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3597 | 110 | 0.11 | 16490 | 1813900 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/23 Cobuilt | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/23 Cobuilt | 12500 | 12.5 | 12500 | 156250000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MB3249 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB3249 | 90 | 0.09 | 16490 | 1484100 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/148 MUM/THA/906 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/148 MUM/THA/906 AGG | 280 | 0.28 | 16000 | 4480000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | Netmagic DC7 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Netmagic DC7 | 100 | 0.1 | 16000 | 1600000 | Ok
344 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004959 | 2025-04-05 | MUM/Route/152 MUM/TJR/901 AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/152 MUM/TJR/901 AGG | 500 | 0.5 | 16000 | 8000000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MA4640 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MA4640 | 70 | 0.07 | 16000 | 1120000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 2475 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 2475 | 60 | 0.06 | 16000 | 960000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MUM/Route/166 Vashi DC | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity MUM/Route/166 Vashi DC | 1684 | 1.684 | 16000 | 26944000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 583 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 583 | 60 | 0.06 | 16000 | 960000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 1614 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 1614 | 300 | 0.3 | 16000 | 4800000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 3625 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 3625 | 50 | 0.05 | 16000 | 800000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | Sapata Sangam AGG | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Sapata Sangam AGG | 1200 | 1.2 | 16000 | 19200000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 5814 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5814 | 180 | 0.18 | 16000 | 2880000 | Ok
345 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | MUM/Route/90 Cobuilt | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/90 Cobuilt | 14270 | 14.27 | 12500 | 178375000 | Ok
345 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004960 | 2025-04-08 | 5307 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity 5307 | 300 | 0.3 | 16000 | 4800000 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA2152 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA2152 | 110 | 0.11 | 16490 | 1813900 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 6094 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 6094 | 170 | 0.17 | 16490 | 2803300 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 2587 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 2587 | 120 | 0.12 | 16490 | 1978800 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA5212 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5212 | 280 | 0.28 | 16490 | 4617200 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MUM/Route/42 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/42 | 7770 | 7.77 | 12500 | 97125000 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA1036 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1036 | 280 | 0.28 | 16490 | 4617200 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 4378 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 4378 | 60 | 0.06 | 16490 | 989400 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 3354 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 3354 | 110 | 0.11 | 16490 | 1813900 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA1751 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA1751 | 180 | 0.18 | 16490 | 2968200 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA3495 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA3495 | 110 | 0.11 | 16490 | 1813900 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MA4138 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4138 | 50 | 0.05 | 16490 | 824500 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | MB6417 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MB6417 | 220 | 0.22 | 16490 | 3627800 | Ok
346 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004961 | 2025-04-08 | 5357 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites 5357 | 360 | 0.36 | 16490 | 5936400 | Ok
347 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MA5287 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA5287 | 150 | 0.15 | 16490 | 2473500 | Ok
347 |  |  | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MA4035 | B0STDDSS1 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For LM POPs and Fibmax sites MA4035 | 90 | 0.09 | 16490 | 1484100 | Ok
347 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004962 | 2025-04-08 | MUM/Route/36 | B0STDDRH6 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Backbone work for Mumbai Intracity Project on Co-Built Model MUM/Route/36 | 3600 | 3.6 | 12500 | 45000000 | Ok
348 | Co-Built | Route | BAL-TNG-NLD--Maharashtra/PUR/10004963 | 2025-04-08 | Mumbai/Coverage/Route35 | B0STDDSL5 - Trenching and Ducting services,Type:Trenching & Digging,Scope:Per Site,Details:OFC laying, Trenching & digging of Last mile work for Mumbai Intracity Project on Co-Built Model - For Coverage and additional DC Connectivity Mumbai/Coverage/Route35 | 4070 | 4.07 | 16000 | 65120000 | Ok

## De-scope
| 89.1191 | 67.282 | 21.8371
RouteNo | Surved Length | PO Length | De-Scope Km | Part of
MUM_Route_124 | 1.3662 | 0.2 | 1.1662 | 52 Km | 10004587 | 9.23 | wrong PO
MUM_Route_64 | 2.0328 | 0 | 2.0328 | 52 Km |  | 9.23
MUM_Route_76 | 0.4598 | 0 | 0.4598 | 52 Km
MUM_Route_77 | 0.5324 | 0 | 0.5324 | 52 Km
Mumbai_Coverage_Route11 | 1.98 | 0 | 1.98 | 89 Km
MUM_Route_36 | 6.0324 | 3.6 | 2.4324 | 232km
MUM_Route_109 | 4.02 | 2.9 | 1.12 | 232km
MUM_Route_23 | 22.09 | 18.92 | 3.17 | 232km
MUM_Route_25 | 9.537 | 8.5 | 1.037 | 232km
MUM_Route_49 | 4.8675 | 2.8 | 2.0675 | 232km
MUM_Route_55 | 14.0063 | 12.962 | 1.0443 | 232km | De-Scope Km | 21.8371
MUM_Route_97 | 15.0502 | 12 | 3.0502 | 232km | In-Crease Km | 5.4129
Mumbai_Coverage_Route21 | 2.937 | 2 | 0.937 | 89 Km | Additional Route | 8.755
Mumbai_Coverage_Route37 | 2.0295 | 1.9 | 0.1295 | 89 Km |  | -3.3421
Mumbai_Coverage_Route 4 | 2.178 | 1.5 | 0.678 | 89 Km |  | 14.1679
7.6692
| 43.9941 | 49.407 | 5.4129
RouteNo | Surved Length | PO Length | In-Crease Km | Part of |  |  |  | 5829
MUM_Route_10 | 10.274 | 10.28 | 0.006 | 232 Km Route
MUM_Route_101 | 0.7117 | 0.8 | 0.0883 | 52 Km Route
MUM_Route_106 | 1.9426 | 2.4 | 0.4574 | 52 Km Route
MUM_Route_108 | 2.7874 | 3.387 | 0.5996 | 52 Km Route
MUM_Route_150 & 151 | 0.2046 | 0.42 | 0.2154 | 89 Km Route
MUM_Route_155 | 0.5973 | 1.5 | 0.9027 | 89 Km Route
MUM_Route_156 | 0.30429 | 0.5 | 0.19571 | 89 Km Route
MUM_Route_169 | 0.561 | 1.11 | 0.549 | 89 Km Route
MUM_Route_170 | 1.1 | 1.11 | 0.01 | 89 Km Route
MUM_Route_152 | 0.495 | 0.5 | 0.005 | 89 Km Route
MUM_Route_37 | 2.4915 | 2.62 | 0.1285 | 232 Km Route
MUM_Route_48 | 3.2384 | 3.3 | 0.0616 | 232 Km Route
MUM_Route_164 & 165 | 0.231 | 0.56 | 0.329 | 89 Km Route
MUM_Route_62 | 0.3113 | 0.9 | 0.5887 | 232 Km Route
MUM_Route_118 | 0.6468 | 0.72 | 0.0732 | 52 Km Route
MUM_Route_74 | 0.2651 | 0.39 | 0.1249 | 52 Km Route
MUM_Route_81 | 11.9383 | 12.01 | 0.0717 | 232 Km Route
Mumbai_Coverage_Route29 | 2.0603 | 2.4 | 0.3397 | 89 Km Route
Mumbai_Coverage_Route31 | 1.7765 | 2.2 | 0.4235 | 89 Km Route
Mumbai_Coverage_Route38 | 2.057 | 2.3 | 0.243 | 89 Km Route

## Summary (hidden)
| Tentative Month | Route Length | No. of POP | Length of Route | No. of Fibmax Node | Length of Fibmax Node | Total
| Apr-25 | 0 | 0 | 0 | #REF! | #REF! | #REF!
| May-25 | 29.6474 | 24 | 4.6228 | #REF! | #REF! | #REF!
| June-25 | 0.074929 | 0 | 0 | #REF! | #REF! | #REF!
| July-25 | 0.84244 | 0 | 0 | #REF! | #REF! | #REF!
| Aug-25 | 2.0016 | 0 | 0 | #REF! | #REF! | #REF!
| sept-25 | 0.86529 | 0 | 0 | #REF! | #REF! | #REF!
| Oct-25 | 5.6133 | 5 | 0.176 | #REF! | #REF! | #REF!
| Nov-25 | 31.4858 | 27 | 4.6055 | #REF! | #REF! | #REF!
| Dec-25 | 39.8237 | 32 | 4.0681 | #REF! | #REF! | #REF!
| Jan-26 | 18.9351 | 14 | 1.8665 | #REF! | #REF! | #REF!
| Feb-26 | 42.7544 | 41 | 9.4305 | #REF! | #REF! | #REF!
| Mar-26 | 29.4888 | 24 | 2.7252 | #REF! | #REF! | #REF!
| Apr-26 | 25.4155 | 26 | 3.2579 | #REF! | #REF! | #REF!
| May-26 | 13.8852 | 16 | 1.7834 | #REF! | #REF! | #REF!
| Oct-26 | 22.3601 | 33 | 4.1048 | #REF! | #REF! | #REF!
| Nov-26 | 36.276 | 30 | 3.5354 | #REF! | #REF! | #REF!
| Dec-26 | 30.913 | 35 | 6.449 | #REF! | #REF! | #REF!
| Jan-27 | 20.1707 | 7 | 1.8295 | #REF! | #REF! | #REF!
| Feb-27 | 19.3201 | 9 | 1.892 | #REF! | #REF! | #REF!
Feasible | Total | 369.8734 | 323 | 50.3466 | #REF! | #REF! | #REF!
Not Feasible |  |  |  |  | 43 | 19.05
Grand Total |  | 369.8734 | 323 | 50.3466 | #REF! | #REF!