## DN details
[13 empty] | 2590 | 2587 | 2128 | 24301724.8 | 3645258.71 | 2430172.5 |  | 425600 |  |  | 30802756 | 30802756
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Start point | End Point | DN received date | DN Number | PO length | Route Length | DN Length | RI (INR) | Supervision charges | Deposit (INR) | Access Charges Amount (INR) | Ground Rent | Administrative Charge | Multiplying Factor | Total (INR) | DD required of amount for payment to KDMC (INR)
1 | Subsection | Airtel | Mumbai_Coverage_Route7 | 2026-05-31 | Co-build | New | Non-strategic | MUMU25NL001MCWA250404D3C3L0002 | Hanuman Road | Nr jankalayan multispeciality hospital | 2025-04-15 | Ref.No.KDMC/10 | 2590 | 2587 | 2128 | 24301724.8 | 3645258.71 | 2430172.5 | 0 | 425600 | 0 | 0 | 30802756 | 30802756

## Capex details
Coverage Route7 - Section Capex details
Route length (Meter) | PO length (meter) | Total DN length of Sub Section (Meter) | PO Value | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Budgeted per meter cost (INR) | Total DN RI cost (RI+Land Rent+Supervision) w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Actual per meter cost (INR) | Percentage length covered | Projected Total cost of route on completion (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Remark
2587 | 2590 | 2128 | 3729600 | 30011520 | 4087767 | 34099287 | 13181.0155 | 28372583.51 | 2936640 | 31309223.51 | 14712.981 | 82.26% | 38062481.7765 | -1531.9655 | -3963194.7765

## Post
Post current approval