## DN details
[16 empty] | 184 | 3067716 |  | 1533768.5 | 0 | 368 | 173 |  | 4601857 | 4601857 | 2280301 | 1520200 | 1281065.06
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Survey ID | Start point | End Point | DN received date | DN Number | Route Length (METER) | Survey section Length (METER) | DN Length (METER) | RI (INR) | Supervision charges | Deposit (INR) | Access Charges Amount (INR) | Ground Rent (INR) | Administrative Charge (INR) | Multiplying Factor | Total (INR) | Payment Displayed on MCGM portal (INR) | Total DN - RI cost including deposit | Total DN - RI cost w/o deposit | Budgeted RI cost w/o deposit | ROW Status | DN payment date | Permit receipt date | Execution Status
1 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWE241221D2C6L0012 | AIR52K24R010001 | BOB Mirza Galibh road | Byculla Fire Bricade | 2024-12-21 | 783326066 | 10274 | 10274 | 33 | 1152439 |  | 576220 | 0 | 66 | 22 | 5 | 1728758 | 1728758 | 1728659 | 1152439 | 1281065.06
2 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWE241221D3C6L0013 | AIR52K24R010001 | BMC E ward office | Mirza Galibh road junction | 2024-12-21 | 783326083 | 10274* | 10274* | 39 | 367761 |  | 183880.5 | 0 | 78 | 39 | 1 | 551759 | 551759 | 551642 | 367761 | 1281065.06*
3 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWA250408D3C3L0020 | AIR52K24R010001 | PNB HOUSE (PNB BANK) | APNA NAZAR (GREAT SOCIAL BLDG | 2025-04-08 | 783339910 | 10274* | 10274* | 52 | 651176 | 0 | 325588 | 0 | 104 | 52 | 1 | 976920 | 976920
4 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWB250403D3C3L0029 | AIR52K24R010001 | GODEE AREA (FR/114) | HOTEL ELPHINSTONE ANNEXE | 2025-04-19 | 783339575 | 10274* | 10274* | 60 | 896340 | 0 | 448080 | 0 | 120 | 60 | 1 | 1344420 | 1344420

## Pre Capex details
Route 10 - Section Capex details
Route Length (Meter) | Section Surveyed Length (Meter) | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Percentage Budget covered | At current _ Projected cost to complete balance section (INR) | Projected Total cost of route (INR) | Projected Total Tentative Savings (INR) | Projected Percentage Budget covered | Remark
10274 | 10274 | 1281065.06 | 6546592.8 | 7827657.86 | 72 | 367761 | 6982210.4 | 7349971.4 | 102082.9361 | 0.7008% | 93.9% | 1041450114.2056 | 1048800085.6056 | -1040972427.7456 | -13299% | This route is entirely part of our existing network where minimal execution in some areas is requried.

## Present Capex details
Route 10 - Section Capex details
Route Length (Meter) | Section Surveyed Length (Meter) | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Percentage Budget covered | At current _ Projected cost to complete balance section (INR) | Projected Total cost of route (INR) | Projected Total Tentative Savings (INR) | Projected Percentage Budget covered | Remark
10274 | 10274 | 1281065.06 | 6546592.8 | 7827657.86 | 72 | 1520200 | 6982210.4 | 8502410.4 | 118089.0333 | 0.7008% | 108.6% | 1204744318.0667 | 1213246728.4667 | -1205419070.6067 | -15399% | This route is entirely part of our existing network where minimal execution in some areas is requried.

## Post Capex details
Post current approval
Route 10 - Section Capex details
Route Length (Meter) | Section Surveyed Length (Meter) | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Percentage Budget covered | At current _ Projected cost to complete balance section (INR) | Projected Total cost of route (INR) | Projected Total Tentative Savings (INR) | Projected Percentage Budget covered | Remark
10274 | 10274 | 1281065.06 | 6546592.8 | 7827657.86 | 72 | 367761 | 6982210.4 | 7349971.4 | 102082.9361 | 0.7008% | 93.9% | 1041450114.2056 | 1048800085.6056 | -1040972427.7456 | -13299% | This route is entirely part of our existing network where minimal execution in some areas is requried.