## DN details
[14 empty] | 5241.5 | 18362.3 | 4765 | 2721434 | 0 | 500000 |  | 0 |  |  | 3238308 | 3238308
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Survey ID | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Start point | End Point | DN received date | DN Number | Section length (mtr) | Route Length (Mtr) | DN Length (Mtr) | RI (INR) | Supervision charges (Rs.) | Deposit (INR) | Access Charges Amount (INR) | Ground Rent (INR) | Administrative Charge (INR) | Multiplying Factor | Total (INR) | Payment dispalyed on portal (INR)
1 | Subsection | Airtel | Route No. 45 | AIR52K24R045005 | 46446 | Co-build | New | Strategic | MUMU25R045NMKK250327D3C3L0004 | Near Stockholding company | Shilphata junction | 45771 | I110310 | 5241.5 | 18362.3 | 4765 | 2721434 | 0 | 500000 | 0 | 0 | 0 | 0 | 3238308 | 3238308
AIR52K24R045006
AIR52K24R045007
AIR52K24R045008
AIR52K24R045009

## Present - Capex details
Route 45 - Section-wise Capex details
Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost - For the Section (INR) | Budgeted Material and Service cost for the section (INR) | Total Budgeted Cost for the section (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost -DN length (INR) | Total DN RI + Projected Material and service - DN length (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tentative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
5241.5 | AIR52K24R045005 | 18362.3 | 6432 | 80400000 | 38542845 | 8658958 | 47201803 | 9005.3998 | 4765 | 2721434 | 7061730 | 9783164 | 2053.1299 | 90.91% | 10761480.4 | 6952.2699 | 36440322.6 | 10761480.4
AIR52K24R045006
AIR52K24R045007
AIR52K24R045008
AIR52K24R045009

## Pre - Capex details
Route 90 - Section Capex details
Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
1430 | AIR52K24R090010 | 19170 | 4900 | 51459800 | 21358480 | 2362360 | 23720840 | 16588 | 0 | 0 | 2531100 | 2531100 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Post - Capex details
Route 90 - Section Capex details
Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
1430 | AIR52K24R090010 | 19170 | 4900 | 51459800 | 21358480 | 2362360 | 23720840 | 16588 | 0 | 0 | 2531100 | 2531100 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!