## PRE
Route No. | PO No. | PO Length (meter) | Route Length (meter) | Target Completion date | Contract | Build Type | Category Type | No of 40 mm duct | No of 3 way duct | 96F | 144F | 288F | Work Completed | ROW paid | Avg Row paid for work completed | Budgeted ROW for completed section | Difference
48 | 100046321 | 3300 | 3238.4 | 2025-05-01 | IP1 | Sify-common | Strategic | 2 | 2 | 4 | 1 | 0 | 0 | 0 | 0 |  | 0

## Present
[14 empty] | 3238 | 3238 | 2620 | 1872000 | 280800 | 215280 |  | 524000 |  |  | 2892080 | 2892080 | 2892080 | 1872000 | 29145600
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Survey ID | Start point | End Point | DN received date | DN Number | Route Length | Survey section Length | DN Length | RI (INR) | Supervision charges | Deposit (INR) | Access Charges Amount (INR) | Ground Rent | Administrative Charge | Multiplying Factor | Total (INR) | Payment Displayed on MCGM portal while making payment (INR) | Total DN - RI cost including deposit | Total DN - RI cost w/o deposit | Budgeted RI cost w/o deposit | ROW Status | DN payment date | Permit receipt date | Execution Status
1 | Subsection | CE | MUM_Route 48 | 2025-05-31 | IP1 | Sify-Common | Strategic | MUMUR048NMKK250220D4C5L0011 | AIR52K24R048008 | TTC Industrial area Bharti Airtel Office | Gami Industrial Park Pawne | 18th March 2025 | NMMC/Z-2/265/2025 | 3238 | 3238 | 975 | 624000 | 93600 | 71760 | 0 | 195000 | 0 | 1 | 984360 | 984360 | 984360 | 624000 | 9715200 | DN Received_Payment pending
2 | Subsection | CE | MUM_Route 48 | 2025-05-31 | IP1 | Sify-Common | Strategic | MUMUR048NMKK250220D4C5L0010 | AIR52K24R048008 | Gami Industrial Park Pawne | Ashwini Infra Development | 18th March 2025 | NMMC/Z-2/264/2025 | 3238* | 3238* | 820 | 624000 | 93600 | 71760 | 0 | 164000 | 0 | 1 | 953360 | 953360 | 953360 | 624000 | 9715200 | DN Received_Payment pending
3 | Subsection | CE | MUM_Route 48 | 2025-05-31 | IP1 | Sify-Common | Strategic | MUMUR048NMKK250220D4C5L0009 | AIR52K24R048008 | Ashwini Infra Development | CTRL S Data Center | 18th March 2025 | NMMC/Z-2/266/2025 | 3238* | 3238* | 825 | 624000 | 93600 | 71760 | 0 | 165000 | 0 | 1 | 954360 | 954360 | 954360 | 624000 | 9715200 | DN Received_Payment pending

## Post
Post current approval
Route No. | PO No. | PO Length | Route Length | Target Completion date | Contract | Build Type | Category Type | No of 40 mm duct | No of 3 way duct | 96F | 144F | 288F | Work Completed | ROW paid | Avg Row paid for work completed | Budgeted ROW for completed section | Difference
48 | 100046321 | 3300 | 3238.4 | 2025-05-01 | IP1 | Sify-common | Strategic | 2 | 2 | 4 | 1 | 0 | 0 | 0 | 0 |  | 0

## Capex details
Route 48- Section Capex details
Route Length (Meter) | Section Surveyed Length (Meter) | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Percentage Budget covered | At current _ Projected cost to complete balance section (INR) | Projected Total cost of route (INR) | Projected Total Tentative Savings (INR) | Projected Percentage Budget covered | Remark
3238.4 | 3238.4 | 9715200 | 3730636.8 | 13445836.8 | 2620 | 1872000 | 6425633.28 | 8297633.28 | 3167.0356 | 80.9% | 61.71% | 1958494.8169 | 10256128.0969 | 3189708.7031 | 76.28% | Airtel and Sify common portion, material cost and execution is higher then actual budgeted for Airtel standalone model