## Info (hidden)
Template Information
File Information |  |  | Quick Start Help
| File Name: | Ultimate Excel Gantt Chart Template |  | Template Structure: | This template has two relevant worksheets: - Gantt (Main Worksheet) - Settings (Setup of basic project info + project role & team management)
| File Author: | The Office Lab
| File License: | With the purchase of this template you have one license for your personal use and one licence for work. You are allowed to use and share the template within your work context. As long as you are involved in the use of the template, everything will be fine. However, an unauthorized redistribution of this file or any sort of derivate of this file for commercial gain is not permitted. |  | Basic Schedule Setup: | A project schedule consists of different items. This template allows you to structure your project into Stages (S) and add as many Task (T) and Milestone (M) items as you wish to each Stage. These are the basic steps to add a new items to the project schedule in the Gantt worksheet: 1. Select the item type (S, T, or M) in the Type column 2. Add an item description in the Description column 3. Set up the schedule in the 'Actual Plan' section: - For Tasks (T) and Milestones (M): Enter the number of required workdays in the Workdays column and provide a start or end date by either (a) entering an independent start date in the ind.start column (b) entering an independent end date in the ind.end column (c) referencing an other item's id in the d.id column and selecting one of the available dependency connection types (FS, SS, SF, FF) in the d.conn column - For Stage (S) items, we recommend to not enter dates or dependencies directly, but rather to automate the calculation of their dates and duration. For this, you can make use of the Auto Stage formulas prepared on top of the 'Actual Plan' section. Just copy them over into the respective input cells (ind.start, workdays, %) and replace the placeholders with range references to the respective columns for all sub-items.
| Documentation & Help: | excelfind.com/documentation/ultimate-excel-gantt-chart
| Disclaimer: | No liability is taken for any damage that might arise related to the use of this template in a business or personal context.
Other Templates |  |  |  | Team & Role Management: | To add your project team to this template and assign different project roles, start in the Settings worksheet: 1. Add up to 8 project roles in the 'Project Role Type' section by entering a role name in the Role column and a short code in the Code column 2. Add your project team members in the 'Project Team' section by entering the team member's name in the Name column and assign one of the defined roles via the drop down selection in the Role column After that, all the added team members are available in the Gantt worksheet and can be assigned to an item in the Team Member column. The assigned role of a selected team member is automatically displayed in the Role column and can even be visualized by selecting 'Team Roles' as the color mode in the Color By Menu at the top.
To thank you for your purchase, we offer you a massive discount on our Ultimate Excel Dashboard (also known from YouTube: https://youtu.be/cKkXtyjleX4). It is the edible version of a new impressive Excel Dashboard design and even contains a bonus showcase file with advanced dashboard features. Click here to claim your discount today!
|  |  |  | More information: | For more detailed information on all features and how they were built, take a look at the 'Documentation & Help' page (link on the left).
Click here to claim your discount

## Settings
Settings | [10 empty] | Gantt
Project Details |  |  | Project Role Types |  |  |  | Project Team
| Project Title: | Route 48 |  | Role | Code | # |  | Name | Role | Code
|  |  |  | ROW Manager | ROW | 1 |  | Yogesh Deshpande | Route Manager | RM
| Route Manager: | Yogesh Deshpande |  | Route Manager | RM | 1 |  | Samir More | ROW Manager | ROW
|  |  |  | Field Engineer 1 | FE1 | 1 |  | Abdul | Field Engineer 1 | FE1
| Project Priority: | High |  | Field Engineer 2 | FE2 | 1 |  | Manoj Ligade | Field Engineer 2 | FE2

## Gantt
Route 48 | [20 empty] | Project Timespan: | [7 empty] | 2025-03-17 |  |  |  | - | 2025-06-20 |  |  |  | (70) |  |  |  |  | Route Manager: | [7 empty] | Yogesh Deshpande | [9 empty] | Settings
| Input Column | [6 empty] | Auto Stage ind.start |  | =MIN(ITEMS_START) | [10 empty] | Color By | [8 empty] | Display | [8 empty] | Show Progress | [21 empty] | Highlight
| Calculated Column (don't delete the cell content!) | [6 empty] | Auto Stage workdays |  | =NETWORKDAYS(plan_start, MAX(ITEMS_END)) | [10 empty] | Project Structure | [8 empty] | Plan vs Base | [8 empty] | Yes | [21 empty] | Today
| Snapshot Column | [6 empty] | Auto Stage % |  | =SUM(ITEMS_PERCENT*ITEMS_WORKDAYS)/SUM(ITEMS_WORKDAYS)
x | Reference to other Cell(s)
[8 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | time axis 2025-03-17 to 2025-05-19
[8 empty] | Updated on: | [9 empty] | Saved on: |  | 0
ids |  |  | Item Details |  |  |  |  | x-xxx-xx | [9 empty] | x-xxx-xx
id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. item |  | d. conn | d. lag | Work days | Start | End | Start | End | % | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M
1 | 1 | -1 | S | Route 48 - Bird's eye view |  |  |  | 2025-03-17 |  |  |  |  | FS |  | 70 | 2025-03-17 | 2025-06-20 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 1 | T | Application | ROW | Samir More | ⚠ | 2025-03-17 |  |  |  |  | FS |  | 10 | 2025-03-17 | 2025-03-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 2 | ↖ | (T) Applica… | FS |  | 25 | 2025-03-31 | 2025-05-02 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 1 | T | DN payment | ROW | Samir More | ⚠ |  |  | 3 | ↖ | (T) Demand … | FS |  | 25 | 2025-05-05 | 2025-06-06 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | 1 | T | Permit Receipt | ROW | Samir More | ⚠ |  |  | 4 | ↖ | (T) DN paym… | FS |  | 10 | 2025-06-09 | 2025-06-20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1 | 2 | T | Execution progress - Route | RM | Yogesh Deshpande | ⚠ | 2025-04-04 |  | 5 | ↖ | (T) Permit … | FS |  |  | 2025-04-04 | 2025-04-04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1 | 2 | T | Execution progress - LMC | RM | Yogesh Deshpande | ⚠ | 2025-04-09 |  | 5 | ↖ | (T) Permit … | FS |  |  | 2025-04-09 | 2025-04-09 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1 | 2 | T | Execution progress - Fibmax | RM | Yogesh Deshpande | ⚠ | 2025-04-04 |  | 5 | ↖ | (T) Permit … | FS |  |  | 2025-04-04 | 2025-04-04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | -1 | S | Subsection IP1 (SSID) |  |  |  | 2025-03-17 |  |  |  |  | FS |  | 55 | 2025-03-17 | 2025-05-30 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2 | 1 | T | Application | ROW | Samir More |  | 2025-03-17 | [6 empty] | 2 | 2025-03-17 | 2025-03-18 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 10 | ↖ | (T) Applica… | FS |  | 5 | 2025-03-19 | 2025-03-25 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2 | 1 | T | DN payment | ROW | Samir More |  |  |  | 11 | ↖ | (T) Demand … | FS |  | 5 | 2025-03-26 | 2025-04-01 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2 | 1 | T | Permit Receipt | ROW | Samir More |  |  |  | 12 | ↖ | (T) DN paym… | FS |  | 2 | 2025-04-02 | 2025-04-03 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | 3 | T | Ducting completed | FE1 | Abdul |  |  |  | 13 | ↖ | (T) Permit … | FS |  | 7 | 2025-04-04 | 2025-04-14 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2 | 3 | T | Blowing & Splicing completed | FE1 | Abdul |  |  |  | 14 | ↖ | (T) Ducting… | SS | 3 | 2 | 2025-04-09 | 2025-04-10 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2 | 2 | T | T1 target - Vendor AT | RM | Yogesh Deshpande |  |  |  | 15 | ↖ | (T) Blowing… | FS |  | 3 | 2025-04-11 | 2025-04-15 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2 | 2 | T | T2 Target - Internal AT | RM | Yogesh Deshpande |  |  |  | 16 | ↖ | (T) T1 targ… | SS |  | 15 | 2025-04-11 | 2025-05-01 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | 2 | M | T3 Target - Customer AT | RM | Yogesh Deshpande |  |  |  | 17 | ↖ | (T) T2 Targ… | SS |  | 30 | 2025-04-11 | 2025-05-22 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2 | 2 | M | Airtel Works clearance (ATC) | RM | Yogesh Deshpande |  |  |  | 18 | ↖ | (M) T3 Targ… | FS |  | 5 | 2025-05-23 | 2025-05-29 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2 | 2 | M | Finance invoicing | RM | Yogesh Deshpande |  |  |  | 19 | ↖ | (M) Airtel … | FS |  | 1 | 2025-05-30 | 2025-05-30 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3 | -1 | S | Subsection IP1 (SSID) |  |  |  | 2025-03-19 |  |  |  |  | FS |  | 52 | 2025-03-19 | 2025-05-29 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3 | 1 | T | Application | ROW | Samir More |  | 2025-03-19 | [6 empty] | 2 | 2025-03-19 | 2025-03-20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 3 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 22 | ↖ | (T) Applica… | FS |  | 5 | 2025-03-21 | 2025-03-27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | 1 | T | DN payment | ROW | Samir More |  |  |  | 23 | ↖ | (T) Demand … | FS |  | 5 | 2025-03-28 | 2025-04-03 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3 | 1 | T | Permit Receipt | ROW | Samir More |  |  |  | 24 | ↖ | (T) DN paym… | FS |  | 2 | 2025-04-04 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3 | 4 | T | Ducting completed | FE2 | Manoj Ligade |  |  |  | 25 | ↖ | (T) Permit … | FS |  | 7 | 2025-04-08 | 2025-04-16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3 | 4 | T | Blowing & Splicing completed | FE2 | Manoj Ligade |  |  |  | 26 | ↖ | (T) Ducting… | SS |  | 2 | 2025-04-08 | 2025-04-09 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3 | 2 | T | T1 target - Vendor AT | RM | Yogesh Deshpande |  |  |  | 27 | ↖ | (T) Blowing… | FS |  | 3 | 2025-04-10 | 2025-04-14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3 | 2 | T | T2 Target - Internal AT | RM | Yogesh Deshpande |  |  |  | 28 | ↖ | (T) T1 targ… | SS |  | 15 | 2025-04-10 | 2025-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3 | 2 | M | T3 Target - Customer AT | RM | Yogesh Deshpande |  |  |  | 29 | ↖ | (T) T2 Targ… | SS |  | 30 | 2025-04-10 | 2025-05-21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 3 | 2 | M | Airtel Works clearance (ATC) | RM | Yogesh Deshpande |  |  |  | 30 | ↖ | (M) T3 Targ… | FS |  | 5 | 2025-05-22 | 2025-05-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 3 | 2 | M | Finance invoicing | RM | Yogesh Deshpande |  |  |  | 31 | ↖ | (M) Airtel … | FS |  | 1 | 2025-05-29 | 2025-05-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 4 | -1 | S | Subsection Co-build (SSID) |  |  |  | 2025-03-17 |  |  |  |  | FS |  | 52 | 2025-03-17 | 2025-05-27 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 4 | 1 | T | Application | ROW | Samir More |  | 2025-03-17 |  |  |  |  | SF |  | 2 | 2025-03-17 | 2025-03-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 4 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 34 | ↖ | (T) Applica… | FS |  | 5 | 2025-03-19 | 2025-03-25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 4 | 1 | T | DN payment | ROW | Samir More |  |  |  | 35 | ↖ | (T) Demand … | FS |  | 5 | 2025-03-26 | 2025-04-01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 4 | 1 | T | Permit Receipt | ROW | Samir More |  |  |  | 36 | ↖ | (T) DN paym… | FS |  | 2 | 2025-04-02 | 2025-04-03 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 4 | 4 | T | Ducting completed | FE2 | Manoj Ligade |  |  |  | 37 | ↖ | (T) Permit … | FS |  | 7 | 2025-04-04 | 2025-04-14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 4 | 4 | T | Blowing & Splicing completed | FE2 | Manoj Ligade |  |  |  | 38 | ↖ | (T) Ducting… | SS |  | 2 | 2025-04-04 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 4 | 2 | T | T1 target - Vendor AT | RM | Yogesh Deshpande |  |  |  | 39 | ↖ | (T) Blowing… | FS |  | 3 | 2025-04-08 | 2025-04-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4 | 2 | T | T2 Target - Internal AT | RM | Yogesh Deshpande |  |  |  | 40 | ↖ | (T) T1 targ… | SS |  | 15 | 2025-04-08 | 2025-04-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4 | 2 | M | T3 Target - Customer AT | RM | Yogesh Deshpande |  |  |  | 41 | ↖ | (T) T2 Targ… | SS |  | 30 | 2025-04-08 | 2025-05-19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4 | 2 | M | Airtel Works clearance (ATC) | RM | Yogesh Deshpande |  |  |  | 42 | ↖ | (M) T3 Targ… | FS |  | 5 | 2025-05-20 | 2025-05-26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4 | 2 | M | Finance invoicing | RM | Yogesh Deshpande |  |  |  | 43 | ↖ | (M) Airtel … | FS |  | 1 | 2025-05-27 | 2025-05-27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 5 | -1 | S | LMC execution (LMC ID) |  |  |  | 2025-03-20 |  |  |  |  | FS |  | 52 | 2025-03-20 | 2025-05-30 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 5 | 1 | T | Application | ROW | Samir More |  | 2025-03-20 |  |  |  |  | SF |  | 2 | 2025-03-20 | 2025-03-21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 5 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 46 | ↖ | (T) Applica… | FS |  | 5 | 2025-03-24 | 2025-03-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 5 | 1 | T | DN payment | ROW | Samir More |  |  |  | 47 | ↖ | (T) Demand … | FS |  | 5 | 2025-03-31 | 2025-04-04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 5 | 1 | T | Permit Receipt | ROW | Samir More |  |  |  | 48 | ↖ | (T) DN paym… | FS |  | 2 | 2025-04-07 | 2025-04-08 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 5 | 3 | T | Ducting completed | FE1 | Abdul |  |  |  | 49 | ↖ | (T) Permit … | FS |  | 7 | 2025-04-09 | 2025-04-17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 5 | 3 | T | Blowing & Splicing completed | FE1 | Abdul |  |  |  | 50 | ↖ | (T) Ducting… | SS |  | 2 | 2025-04-09 | 2025-04-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 5 | 2 | T | T1 target - Vendor AT | RM | Yogesh Deshpande |  |  |  | 51 | ↖ | (T) Blowing… | FS |  | 3 | 2025-04-11 | 2025-04-15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 5 | 2 | T | T2 Target - Internal AT | RM | Yogesh Deshpande |  |  |  | 52 | ↖ | (T) T1 targ… | SS |  | 15 | 2025-04-11 | 2025-05-01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 5 | 2 | M | T3 Target - Customer AT | RM | Yogesh Deshpande |  |  |  | 53 | ↖ | (T) T2 Targ… | SS |  | 30 | 2025-04-11 | 2025-05-22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 5 | 2 | M | Airtel Works clearance (ATC) | RM | Yogesh Deshpande |  |  |  | 54 | ↖ | (M) T3 Targ… | FS |  | 5 | 2025-05-23 | 2025-05-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 5 | 2 | M | Finance invoicing | RM | Yogesh Deshpande |  |  |  | 55 | ↖ | (M) Airtel … | FS |  | 1 | 2025-05-30 | 2025-05-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 6 | -1 | S | Fibmax execution (Fibmax ID) |  |  |  | 2025-03-17 |  |  |  |  | FS |  | 52 | 2025-03-17 | 2025-05-27 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 6 | 1 | T | Application | ROW | Samir More |  | 2025-03-17 |  |  |  |  | SF |  | 2 | 2025-03-17 | 2025-03-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 6 | 1 | T | Demand Note receipt | ROW | Samir More |  |  |  | 58 | ↖ | (T) Applica… | FS |  | 5 | 2025-03-19 | 2025-03-25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 6 | 1 | T | DN payment | ROW | Samir More |  |  |  | 59 | ↖ | (T) Demand … | FS |  | 5 | 2025-03-26 | 2025-04-01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 6 | 1 | T | Permit Receipt | ROW | Samir More |  |  |  | 60 | ↖ | (T) DN paym… | FS |  | 2 | 2025-04-02 | 2025-04-03 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 6 | 3 | T | Ducting completed | FE1 | Abdul |  |  |  | 61 | ↖ | (T) Permit … | FS |  | 7 | 2025-04-04 | 2025-04-14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 6 | 3 | T | Blowing & Splicing completed | FE1 | Abdul |  |  |  | 62 | ↖ | (T) Ducting… | SS |  | 2 | 2025-04-04 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 6 | 2 | T | T1 target - Vendor AT | RM | Yogesh Deshpande |  |  |  | 63 | ↖ | (T) Blowing… | FS |  | 3 | 2025-04-08 | 2025-04-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 6 | 2 | T | T2 Target - Internal AT | RM | Yogesh Deshpande |  |  |  | 64 | ↖ | (T) T1 targ… | SS |  | 15 | 2025-04-08 | 2025-04-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 6 | 2 | M | T3 Target - Customer AT | RM | Yogesh Deshpande |  |  |  | 65 | ↖ | (T) T2 Targ… | SS |  | 30 | 2025-04-08 | 2025-05-19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 6 | 2 | M | Airtel Works clearance (ATC) | RM | Yogesh Deshpande |  |  |  | 66 | ↖ | (M) T3 Targ… | FS |  | 5 | 2025-05-20 | 2025-05-26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 6 | 2 | M | Finance invoicing | RM | Yogesh Deshpande |  |  |  | 67 | ↖ | (M) Airtel … | FS |  | 1 | 2025-05-27 | 2025-05-27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0