## DN details
[14 empty] | 1430 | 19170 | 452 | 3033372 | 0 | 1516686 |  | 904 | 452 |  | 4550934 | 4550934
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Survey ID | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Start point | End Point | DN received date | DN Number | Section length (mtr) | Route Length (Mtr) | DN Length (Mtr) | RI (INR) | Supervision charges (Rs.) | Deposit (INR) | Access Charges Amount (INR) | Ground Rent (INR) | Administrative Charge (INR) | Multiplying Factor | Total (INR) | Payment dispalyed on portal (INR)
1 | Subsection | Airtel | Route No. 90 | AIR52K24R090010 | 2027-01-31 | Co-build | Sify-Common | Strategic | MUMUR090MCME08042025D4C5L0003 | NR ASHTVINAYAK CHS | POLE NO. YJS/005/023 | 2025-04-12 | 783339980 | 1430 | 19170 | 156 | 1046916 | 0 | 523458 | 0 | 312 | 156 | 0 | 1570842 | 1570842
2 | Subsection | Airtel | Route No. 90 | AIR52K24R090010 | 2027-01-31 | Co-build | Sify-Common | Strategic | MUMUR090MCME08042025D4C5L0002 | POLE NO. YJS/005/023 | MCGM MOTOR LODER CHOWKY( AAGARWADI JN.) | 2025-04-12 | 783340005 | 1430* | 19170* | 136 | 912696 | 0 | 456348 | 0 | 272 | 136 | 0 | 1369452 | 1369452
3 | Subsection | Airtel | Route No. 90 | AIR52K24R090010 | 2027-01-31 | Co-build | Sify-Common | Strategic | MUMU25R090MCME250424D4C5L0005 | ZARINA PARK GATE NO 02 | MCGM MOTOR LOADER CHOWKY | 2025-04-25 | 783341644 | 1430* | 19170* | 160 | 1073760 | 0 | 536880 | 0 | 320 | 160 | 0 | 1610640 | 1610640

## Present - Capex details
Route 90 - Section-wise Capex details
| Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost - For the Section (INR) | Budgeted Material and Service cost for the section (INR) | Total Budgeted Cost for the section (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost -DN length (INR) | Total DN RI + Projected Material and service - DN length (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tentative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
1 | 1430 | AIR52K24R090010 | 19170 | 14270 | 210482500 | 21358480 | 2362360 | 23720840 | 16588 | 292 | 3033372 | 516840 | 3550212 | 12158.2603 | 20.42% | 17386312.1918 | 4429.7397 | 6334527.8082 | 17386312.1918
2 | 1430 | AIR52K24R090010 | 19170 | 14270 | 210482500 | 21358480 | 2362360 | 23720840 | 16588 | 160 | 1073760 | 283200 | 1356960 | 8481 |  | 12127830 | 8107

## Pre - Capex details
Route 90 - Section Capex details
Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
1430 | AIR52K24R090010 | 19170 | 14270 | 178375000 | 21358480 | 2362360 | 23720840 | 16588 | 292 | 1959612 | 516840 | 2476452 | 8481 | 20.42% | 12127830 | 8107 | 11593010 | 12127830

## Post - Capex details
Route 90 - Section Capex details
Surveyed section length (Meter) | Survey ID | Total route length (Meter) | PO length (meter) | PO Value (INR | Budgeted RI Cost (INR) | Budgeted Material and Service cost (INR) | Total Budgeted Cost (INR) | Budgeted per meter cost (INR) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Current per meter cost (INR) | Percentage length covered | Projected Total cost of section on completion (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total Tentative Savings against the budgeted cost (INR) | Projected Total Tentative Savings (INR) | Remark
1430 | AIR52K24R090010 | 19170 | 14270 | 178375000 | 21358480 | 2362360 | 23720840 | 16588 | 452 | 3033372 | 800040 | 3833412 | 8481 | 31.61% | 12127830 | 8107 | 11593010 | 12127830