## DN details
[16 empty] | 184 | 3067716 |  | 1533768.5 | 0 | 368 | 173 |  | 4601857 | 4601857 | 2280301 | 1520200 | 1281065.06
Sr. No. | Subsection / LMC | DN Recipient | Route No. | Target date of completion | Contract type | Build Type | Category type | Subsection ID / LMC ID | Survey ID | Start point | End Point | DN received date | DN Number | Route Length (METER) | Survey section Length (METER) | DN Length (METER) | RI (INR) | Supervision charges | Deposit (INR) | Access Charges Amount (INR) | Ground Rent (INR) | Administrative Charge (INR) | Multiplying Factor | Total (INR) | Payment Displayed on MCGM portal (INR) | Total DN - RI cost including deposit | Total DN - RI cost w/o deposit | Budgeted RI cost w/o deposit | ROW Status | DN payment date | Permit receipt date | Execution Status
1 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWE241221D2C6L0012 | AIR52K24R010001 | BOB Mirza Galibh road | Byculla Fire Bricade | 2024-12-21 | 783326066 | 10274 | 10274 | 33 | 1152439 |  | 576220 | 0 | 66 | 22 | 5 | 1728758 | 1728758 | 1728659 | 1152439 | 1281065.06
2 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWE241221D3C6L0013 | AIR52K24R010001 | BMC E ward office | Mirza Galibh road junction | 2024-12-21 | 783326083 | 10274* | 10274* | 39 | 367761 |  | 183880.5 | 0 | 78 | 39 | 1 | 551759 | 551759 | 551642 | 367761 | 1281065.06*
3 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWA250408D3C3L0020 | AIR52K24R010001 | PNB HOUSE (PNB BANK) | APNA NAZAR (GREAT SOCIAL BLDG | 2025-04-08 | 783339910 | 10274* | 10274* | 52 | 651176 | 0 | 325588 | 0 | 104 | 52 | 1 | 976920 | 976920
4 | Subsection | CE | Route No. 10 | 2025-05-31 | IP1 | Existing | Strategic | MUMU25R010MCWB250403D3C3L0029 | AIR52K24R010001 | GODEE AREA (FR/114) | HOTEL ELPHINSTONE ANNEXE | 2025-04-19 | 783339575 | 10274* | 10274* | 60 | 896340 | 0 | 448080 | 0 | 120 | 60 | 1 | 1344420 | 1344420

## Current DN
[22 empty] | 60 | 896160 | 39956.7577 | 936116.7577
| 43943.9 | 92722561.668 |  | 8027607.72 |  | 21236655 |  | 121986824.388 |  | SOBO existing IP1 routes
Routes | Total Surveyed Length with Markup Mtr | Total RI Cost | Total RI Cost / meter | Total Material cost | Total material cost / meter | Total Execution Cost including HH | Total Execution Cost including HH / meter | Total Cost | Total Cost / meter | Routes | Total Surveyed Length |  | Effective length to be executed | Budgeted Total RI Cost | Budgeted Total RI Cost / meter | Budgeted Total Material cost | Budgeted Total material cost / meter | Budgeted Total Execution Cost including HH | Budgeted Total Execution Cost including HH / meter | Budgeted Total Cost | Budgeted Total Cost / meter (Effective length) | Total DN length of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Percentage Budget covered | Actual per meter cost (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total cost of IP1 existing routes on completion (INR)
MUM_Route_107 | 652.3 | 978450 | 1500 | 94583.5 | 145 | 456610 | 700 | 1529643.5 | 2345 | MUM_Route_107 | 43943.9 | 1500 | 14500 | 92722561.668 | 2110.0212 | 8027607.72 | 182.6785 | 21236655 | 483.2674 | 121986824.388 | 8412.8844 | [5 empty] | 15601.946 | -7189.0615 | 685610353.12
MUM_Route_106 | 1133 | 1699500 | 1500 | 164285 | 145 | 793100 | 700 | 2656885 | 2345 | MUM_Route_106 |  | 1500
MUM_Route_105 | 440 | 660000 | 1500 | 63800 | 145 | 308000 | 700 | 1031800 | 2345 | MUM_Route_105 |  | 1500
MUM_Route_11 | 787.6 | 5428596.8 | 6892.581 | 130541.84 | 165.7464 | 454520 | 577.095 | 6013658.64 | 7635.4223 | MUM_Route_11 |  | 1500
MUM_Route_99 | 1970.1 | 2955150 | 1500 | 285664.5 | 145 | 1379070 | 700 | 4619884.5 | 2345 | MUM_Route_99 |  | 1500
MUM_Route_101 | 711.7 | 2397714 | 3368.9954 | 146261.5 | 205.51 | 527890 | 741.7311 | 3071865.5 | 4316.2365 | MUM_Route_101 |  | 1500
MUM_Route_102 | 421.3 | 631950 | 1500 | 61088.5 | 145 | 294910 | 700 | 987948.5 | 2345 | MUM_Route_102 |  | 1500
MUM_Route_8 | 11771.1 | 48851921.03 | 4150.1577 | 2203549.92 | 187.2 | 5296995 | 450 | 56352465.95 | 4787.3577 | MUM_Route_8 |  | 12469
MUM_Route_10 | 10274 | 1281065.06 | 124.69 | 1923292.8 | 187.2 | 4623300 | 450 | 7827657.86 | 761.89 | MUM_Route_10 |  | 12469 | [9 empty] | 60 | 896160 | 39956.7577 | 936116.7577 | 0.7674%
MUM_Route_54 | 5060 | 1261862.8 | 249.38 | 947232 | 187.2 | 2277000 | 450 | 4486094.8 | 886.58 | MUM_Route_54 |  | 12469
MUM_Route_55 | 10722.8 | 26576351.978 | 2478.4899 | 2007308.16 | 187.2 | 4825260 | 450 | 33408920.138 | 3115.6899 | MUM_Route_55 |  | 10187
1547992

## PRE
[11 empty] | 124 | 2171376 | 82577.2992 | 2253953.2992
SOBO existing IP1 routes
Routes | Total Surveyed Length | Effective length to be executed | Budgeted Total RI Cost | Budgeted Total RI Cost / meter | Budgeted Total Material cost | Budgeted Total material cost / meter | Budgeted Total Execution Cost including HH | Budgeted Total Execution Cost including HH / meter | Budgeted Total Cost | Budgeted Total Cost / meter (Effective length) | Total DN length RECEIVED of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Percentage Budget covered | Actual per meter cost (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total cost of IP1 existing routes on completion (INR)
MUM_Route_107 | 43943.9 | 14500 | 92722561.668 | 2110.0212 | 8027607.72 | 182.6785 | 21236655 | 483.2674 | 121986824.388 | 8412.8844 | [5 empty] | 18177.0427 | -9764.1583 | 798770148.2555
MUM_Route_106
MUM_Route_105
MUM_Route_11
MUM_Route_99
MUM_Route_101
MUM_Route_102
MUM_Route_8
MUM_Route_10 | [10 empty] | 124 | 2171376 | 82577.2992 | 2253953.2992 | 1.848%
MUM_Route_54
MUM_Route_55

## POST
[11 empty] | 184 | 3067536 | 122534.0568 | 3190070.0568
SOBO existing IP1 routes
Routes | Total Surveyed Length | Effective length to be executed | Budgeted Total RI Cost | Budgeted Total RI Cost / meter | Budgeted Total Material cost | Budgeted Total material cost / meter | Budgeted Total Execution Cost including HH | Budgeted Total Execution Cost including HH / meter | Budgeted Total Cost | Budgeted Total Cost / meter (Effective length) | Total DN length RECEIVED of Sub Section (Meter) | Total DN RI cost w/o deposit (INR) | Projected Material and Service cost (INR) | Total DN RI + Projected Material and service (INR) | Percentage Budget covered | Actual per meter cost (INR) | Tetative savings per meter against the budgeted cost (INR) | Projected Total cost of IP1 existing routes on completion (INR)
MUM_Route_107 | 43943.9 | 14500 | 92722561.668 | 2110.0212 | 8027607.72 | 182.6785 | 21236655 | 483.2674 | 121986824.388 | 8412.8844 | [5 empty] | 17337.3373 | -8924.4528 | 761870215.0591
MUM_Route_106
MUM_Route_105
MUM_Route_11
MUM_Route_99
MUM_Route_101
MUM_Route_102
MUM_Route_8
MUM_Route_10 | [10 empty] | 184 | 3067536 | 122534.0568 | 3190070.0568 | 2.615%
MUM_Route_54
MUM_Route_55