## Sheet1
[20 empty] | 17119 | [6 empty] | 18.165 | 18165 |  | 16.9 | 1.265 |  |  |  |  | 57273209.64 |  |  | 7596 | 4415476.157 |  | 727830.56 | 15375157.937 | 78864590.294 |  | 200156251.7733 | 62761601.797 |  | 44017.4669 | 15375157.937 | 78864591.544 | [12 empty] | 254592472.4
Sr. No. | Route Type | LMC/Route | IP1 / Co-built | DN receipient | Project Name | Site ID | UID | Contract type | Build Type | Category type | Survey ID | PO Number | PO Length | Route ID/LMC ID | Parent Route | Route/LMC ID | Route/LMC Section ID | Route/LMC Subsection ID | Application Number | Application Length (Mtr) | Application Date | From | To | Authority | Ward | Survey Done (Mtr) | DN Number | DN Length (Mtr) | DN Received date | Type | Trench Type | OT /HDD | PIT | Surface | RI Rate (GO) (Rs.) | DN RI Amount | Multiplying factor | Ground Rent | Administrative Charge | Supervision Charges | Chamber Fee | GST | Deposit | Total DN amount | RI Budget amount per meter (for the section) | Projected Budget RI amount for DN | Actual Total Non Refundable Amount (RI+Ground+Admin+Supervision) | Non refundable Actual Amount/mtr | Non Refundable Savings/Mtr | Deposit | Total DN amount | ROW Network ID | Route Network ID | New Revised DN Number | New Revised DN against | Internal approval start date | Internal approval end date | Ticket raised date | DN payment date | TAT (ticket raised and DN Payment) | Civil Completion date |  |  | RI Budget amount(For Entire section)
1 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_50 | MUM_Route_50 | IP-1 | Sify - Common | Strategic | AIR52K24R050001 | 10004765 | 6030 | MUM_Route_50 | NA | MUMUR050 | MUMUR050NIMI | MUMUR050NMMI250129D4C4L0001 | I96966 | 4766 | 2025-01-29 | A SIFY Rabale | F Mahape | MIDC | MIDC | Yes | I96966 | 4766 | 2025-02-10 | Legal | Open Trench |  |  | Embankment Soil | 41 | 195406 | 0 | 0 | 4766 |  |  | 36030.96 | 250000 | 486202.96 | 19200 | 91507200 | 200172 | 42 | 19158 | 250000 | 486202.96 | MUM-ROW000000060 | MUM-RTE002 |  |  | 2025-02-01 | 2025-02-06 | 2025-02-06 | 2025-02-12 | 6 |  | 6 |  | 99411840
2 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_50 | MUM_Route_50 | IP-1 | Sify - Common | Strategic | AIR52K24R050002 | 10004765 | 6030 | MUM_Route_50 | NA | MUMUR050 | MUMUR050NIMI | MUMUR050NMMI250212D4C4L0001 | I99340 | 600 |  | F Mahape Police Chowky | G CNTRL S Mahape | MIDC | MIDC | Yes | I99340 | 600 | 2025-02-12 | Legal | Open Trench |  |  | Embankment Soil+CC Crossing | 41/1797 | 59720 | 0 | 0 | 600 |  |  | 10857.6 | 60000 | 131177.6 | 3000 | 1800000 | 60320 | 100.5333 | 2899.4667 | 60000 | 131177.6 | MUM-ROW000000069 | MUM-RTE002 |  |  | 2025-02-18 | 2025-02-19 | 2025-02-23 | 2025-03-13 | 18 |  | 18 |  | 2567400
3 | Additional Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | MUM_Route_131 | MUM_Route_131 | Co-build | New-build | Non-Strategic |  | 10004641 | 200 | MUM_Route_131 | NA | MUMU25R131 | MUMU25R131MCWA | MUMU25R131MCWA250328D3C3 | 783339212 | 145 | 2025-03-28 | NEAR SUCHITA BUILDING | NEAR HOTEL VICTORIA | MCGM | A | Yes | 783339212 | 155 | 2025-04-04 | Legal | Open Trench |  |  | Carriageway+footpath/Passages | 10187/10454 | 1613962 | 0 | 310 | 155 |  |  |  | 806981 | 2421408 | 8413 | 1304015 | 1614427 | 10415.6581 | -2002.6581 | 806981 | 2421408 | MUM-ROW000000082 |  |  |  | 2025-04-15 | 2025-04-16 | 2025-04-16 | 2025-04-17 | 1 |  | 1
4 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project |  | MU-MA6295 | Co-build | New-build | Non-Strategic |  | 10004641 | 30 | NA | MUMU25R010 | MUMU25NL002 | MUMU25NL002MCWA | MUMU25NL002MCWA250404D3C3L0003 | 783339141 | 20 | 2025-03-27 | NEAR EP NO-F/R-9 HOTEL POPULAR PALACE | NEAR MINT ROAD | MCGM | A | Yes | 783339141 | 27 | 2025-04-04 | Legal | Open Trench |  |  | Carriageway | 10187 | 275049 | 0 | 54 | 27 |  |  |  | 137524.5 | 412654.5 | 12469 | 336663 | 275130 | 10190 | 2279 | 137524.5 | 412654.5 | MUM-ROW000000080 |  |  |  | 2025-04-04 | 2025-04-11 | 2025-04-11 | 2025-04-15 | 4 |  | 4 |  | 274318
5 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA4226 | MU-MA4226 | Co-build | New-build | Non-Strategic |  | 10004641 | 20 | NA | MUMU25R010 | MUMU25NL003 | MUMU25NL003MCWA | MUMU25NL003MCWA250404D3C3L0004 | 783339100 | 8 | 2025-03-27 | NEAR HOTEL CASTLE IN HIRA BLDG | NEAR HOTEL CASTLE IN HIRA BLDG | MCGM | A | Yes | 783339100 | 8 | 2025-04-04 | Legal | Open Trench |  |  | Footpath/Passages(Finished in Stencil) | 11211 | 448440 | 5 | 16 | 8 |  |  |  | 0 | 448464 | 12469 | 99752 | 448464 | 56058 | -43589 |  | 448464 | MUM-ROW000000081 |  |  |  | 2025-04-04 | 2025-04-11 | 2025-04-11 | 2025-04-15 | 4 |  | 4 |  | 274318
6 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_48 | MUM_Route_48 | IP-1 | Sify - Common | Strategic | AIR52K24R048008 | 10004681 | 3300 | MUM_Route_48 | NA | MUMU25R048 | MUMUR048NMKK | MUMUR048NMKK250220D4C5L0011 | ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/01 | 975 | 2025-03-18 | TTC Industrial area Bharti Airtel Office | Gami Industrial Park Pawne | NMMC | KK | Yes | NMMC/Z-2/265/2025 | 975 | 2025-03-18 | Legal | Open Trench/HDD | 975 | 144000 | Asphalt | 9600 | 624000 | 0 | 195000 | 0 | 93600 |  |  | 71760 | 984360 | 3000 | 2925000 | 912600 | 936 | 2064 | 71760 | 984360 | MUM-ROW000000057 | MUM-RTE004 |  |  | 2025-03-25 | 2025-04-01 | 2025-04-01 | 2025-04-09 | 8 |  | 8 |  | 9715200
7 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_48 | MUM_Route_48 | IP-1 | Sify - Common | Strategic | AIR52K24R048008 | 10004681 | 3300 | MUM_Route_48 | NA | MUMU25R048 | MUMUR048NMKK | MUMUR048NMKK250220D4C5L0010 | ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/02 | 820 | 2025-03-18 | Gami Industrial Park Pawne | Ashwini Infra Development | NMMC | KK | Yes | NMMC/Z-2/264/2025 | 820 | 2025-03-18 | Legal | Open Trench/HDD | 820 | 144000 | Asphalt | 9600 | 624000 | 0 | 164000 | 0 | 93600 |  |  | 71760 | 953360 | 3000 | 2460000 | 881600 | 1075.122 | 1924.878 | 71760 | 953360 | MUM-ROW000000051 | MUM-RTE004 |  |  | 2025-03-25 | 2025-04-01 | 2025-04-01 | 2025-04-09 | 8 |  | 8 |  | *9715200
8 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_48 | MUM_Route_48 | IP-1 | Sify - Common | Strategic | AIR52K24R048008 | 10004681 | 3300 | MUM_Route_48 | NA | MUMU25R048 | MUMUR048NMKK | MUMUR048NMKK250220D4C5L0009 | ETIPL/OSP/Koperkhairne MIDC/HDD/2024-25/03 | 825 | 2025-03-18 | Ashwini Infra Development | CTRL S Data Center | NMMC | KK | Yes | NMMC/Z-2/266/2025 | 825 | 2025-03-18 | Legal | Open Trench/HDD | 825 | 144000 | Asphalt | 9600 | 624000 | 0 | 165000 | 0 | 93600 |  |  | 71760 | 954360 | 3000 | 2475000 | 882600 | 1069.8182 | 1930.1818 | 71760 | 954360 | MUM-ROW000000046 | MUM-RTE004 |  |  | 2025-03-25 | 2025-04-01 | 2025-04-01 | 2025-04-09 | 8 |  | 8 |  | *9715200
9 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_10 | MUM_Route_10 | IP-1 | Existing | Strategic |  | 10004633 | 10280 | MUM_Route_10 | NA | MUMU25R010 | MUMU25R010MCWA | MUMU25R010MCWA250408D3C3L0020 | 783339910 | 42 | 2025-04-08 | PNB HOUSE (PNB BANK) | APNA BAZAR (GREAT SOCIAL BLDG | MCGM | A | Yes | 783339910 | 52 | 2025-04-08 | Legal | Open Trench |  |  | Mastic Asphalt 40 m+Concrete Finished | 14936/28 | 651176 |  | 104 | 52 |  |  |  | 325588 | 976920 | 8413 | 437476 | 651332 | 12525.6154 | -4112.6154 | 325588 | 976920 | MUM-ROW000000070 |  |  |  | 2025-04-09 | 2025-04-20 | 2025-04-20 | 2025-04-25 | 5 |  | 5 |  | 1281065
10 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 6195 | MU-6195 | Co-Build | New-build | Non-Strategic |  | 10004835 | 242 | NA | NA | MUMU25FL004 | MUMU25FL004MCRS | MUMU25FL004MCRS250415D33L0005 | 783341287 | 65 | 2025-04-09 | AVERSHINE MILLENIUM PAIRADISE | THAKUR SHYAM NARAYAN SCHOOL | MCGM | RS | Yes | 783341287 | 75 | 2025-04-15 | Legal | Open Trench |  |  | Carriageway | 11378 | 853350 | 1 | 150 | 75 |  |  |  | 426675 | 1280250 | 14936 | 1120200 | 853575 | 11381 |  | 426675 | 1280250 | MUM-ROW000000077 |  |  |  | 2025-04-15 | 2025-04-17 | 2025-04-18 | 2025-04-29 | 11 |  | 11 |  | 3614512
11 | DC Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | MUM_Route_90 | MUM_Route_90 | Co-build | Sify - Common | Strategic | AIR52K24R090010 | 10004960 | 14270 | MUM_Route_90 | NA | MUMU25R090 | MUMU25R090MCME | MUMU25R090MCME250412D3C3L0023 | 783339980 | 156 | 2025-04-08 | NR ASHTVINAYAK CHS | POLE NO. YJS/005/023 | MCGM | ME | Yes | 783339980 | 156 | 2025-04-12 | Legal | Open Trench |  |  | Carriageway | 6711 | 1046916 | 0 | 312 | 156 |  |  |  | 523458 | 1570842 | 14936 | 2330016 | 1047384 | 6714 | 8222 | 523458 | 1570842 | MUM-ROW000000074 |  |  |  | 2025-04-18 | 2025-04-21 | 2025-04-21 | 2025-04-23 | 2 |  | 2 |  | 21358480
12 | DC Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | MUM_Route_90 | MUM_Route_90 | Co-build | Sify - Common | Strategic | AIR52K24R090010 | 10004960 | 14270 | MUM_Route_90 | NA | MUMU25R090 | MUMU25R090MCME | MUMU25R090MCME250412D3C3L0024 | 783340005 | 126 | 2025-04-08 | POLE NO. YJS/005/023 | MCGM MOTOR LODER CHOWKY( AAGARWADI JN.) | MCGM | ME | Yes | 783340005 | 136 | 2025-04-12 | Legal | Open Trench |  |  | Carriageway | 6711 | 912696 | 0 | 272 | 136 |  |  |  | 456348 | 1369452 | 14936 | 2031296 | 913104 | 6714 | 8222 | 456348 | 1369452 | MUM-ROW000000073 |  |  |  | 2025-04-18 | 2025-04-21 | 2025-04-21 | 2025-04-23 | 2 |  | 2 |  | 21358480
13 | Additional Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | Mumbai_Coverage_Route7 | Mumbai_Coverage_Route7 | Co-build | New-build | Non-Strategic | Entire route DN achieved in single go. | 10004531 | 2590 | Mumbai_Coverage_Route7 | NA | MUMU25RC07 | MUMU25RC07KDWI | MUMU25RC07KDWI250325D3C3L0025 | AIRTEL/OSP/2024-25/Open Trench-HDD/kdmc/01 | 2128 | 2025-03-25 | Hanuman Road | Nr jankalayan multispeciality hospital | KDMC | KD | Yes | KDMC/Ex.Engg/Construction/K-W/10 | 2128 | 2025-04-15 | Legal | Open Trench | 2128 |  | Paverblock+Asphalt | 9269.27/12326.53 | 24301725 |  | 425600 |  | 3645258.717 |  |  | 2430172.478 | 30802756.195 | 11600 | 24684800 | 28372583.717 | 13332.9811 | -1732.9811 | 2430172.478 | 30802756.195 | MUM-ROW000000078 |  |  |  | 2025-04-18 | 2025-04-20 | 2025-04-20 | 2025-05-02 | 12 |  | 12 |  | 30011520
14 | Additional Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | Mumbai_Coverage_Route13 | Mumbai_Coverage_Route13 | Co-build | New-build | Non-Strategic | AIR52K24RC13007 | 10004545 | 3030 | Mumbai_Coverage_Route13 | NA | MUMU25RC13 | MUMU25RC13KDKD | MUMU25RC13KDKD250325D3C3L0026 | AIRTEL/OSP/2024-25/Open Trench-HDD/kdmc/02 | 80 | 2025-03-25 | Jhulelal Chowk | Gold Gym | KDMC | KD | Yes | KDMC/Ex.Engg/Construction/K-W/06 | 80 | 2025-04-11 | Legal | Open Trench | 80 |  | Paverblock | 9269.27 | 741541.6 |  | 160 | 0 |  |  |  | 74170.16 | 815871.76 |  |  | 741701.6 |  |  | 74170.16 | 815871.76 | MUM-ROW000000079 | [7 empty] | 0 |  | 0 |  | 3828000
15 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 5831 | MU-5831 | Co-Build | New-build | Non-Strategic |  | 10004791 | 67 | NA | NA | MUMU25FL005 | MUMU25FL005MCRN | MUMU25FL005MCRN250401D3C30027 | 783339323 | 116 | 2025-04-01 | JAYWANT SAWANT MARG | SAI AMRUT CHS | MCGM | RN | Yes | 783339323 | 136 | 2025-04-17 | Legal | Open Trench |  |  | Carriageway(PB 80(OnlyGrey+Use of Existing Duct) | 8246/2900 | 1067996 | 0 | 272 | 136 |  |  |  | 533998 | 1602402 | 7487 | 1018232 | 1068404 | 7855.9118 | -368.9118 | 533998 | 1602402 | MUM-ROW000000086 |  |  |  | 2025-04-18 | 2025-04-20 | 2025-04-20 | 2025-04-23 | 3 |  | 3 |  | 503126.4
16 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB6370 | MU-MB6370 | Co-Build | New-build | Non-Strategic |  | 10004838 | 33 | NA | NA | MUMU25FL005 | MUMU25FL005MCRN | MUMU25FL005MCRN250409D3C30028 | 783340181 | 81 | 2025-04-09 | RAJ HERITAGE TOWER | MARY JAMMACULATE GIRLS SCHOOL | MCGM | RN | Yes | 783340181 | 91 | 2025-04-17 | Legal | Open Trench |  |  | Carriageway(Bituminous Concrete) | 11378 | 1035398 | 1 | 182 | 91 |  |  |  | 517699 | 1553370 | 14936 | 1359176 | 1035671 | 11381 | 3555 | 517699 | 1553370 | MUM-ROW000000088 |  |  |  | 2025-04-18 | 2025-04-20 | 2025-04-20 | 2025-04-23 | 3 |  | 3 |  | 492888
17 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_10 | MUM_Route_10 | IP-1 | Existing | Strategic |  | 10004633 | 10280 | MUM_Route_10 | NA | MUMU25R010 | MUMU25R010MCWB | MUMU25R010MCWB250403D3C3L0029 | 783339575 | 50 | 2025-04-03 | Hotel Elphinstone Annexe | Godee Area opp. Navratna Premises | MCGM | B | Yes | 783339575 | 60 | 2025-04-19 | Legal | Open Trench |  |  | Mastic Asphalt 40 m | 14936 | 896160 |  | 120 | 60 |  |  |  | 448080 | 1344420 | 8413 | 504780 | 896340 | 14939 | -6526 | 448080 | 1344420 | MUM-ROW000000083 |  |  |  | 2025-04-22 | 2025-04-24 | 2025-04-24 | 2025-04-25 | 1 |  | 1 |  | *1281065
18 | DC Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | MUM_Route_45 | MUM_Route_45 | Co-build | New-build | Strategic | AIR52K24R045005, AIR52K24R045006, AIR52K24R045007, AIR52K24R045008, AIR52K24R045009 | 10004670 | 6432 | MUM_Route_45 | NA | MUMU25R045 | MUMU25R045NMKK | MUMU25R045NMKK250327D3C3L0004 | I110310 | 4765 | 45743 | Stock Holding Corporation | Shilphata Road | MIDC | KK | Yes | I110310 | 4765 | 2025-04-24 | Legal | Open Trench |  |  | Embankment Soil | 484 | 2306260 | 0 | 14300 | 0 |  |  | 417908 | 500000 | 3238468 | 7354.1013 | 35042292.7733 | 2320560 | 487.001 | 6867.1003 | 500000 | 3238468 |  |  |  |  | 2025-04-25 | 2025-04-25 | 2025-04-28 | 2025-05-01 | 3 |  | 3 | 160 rs gap due to wrong DN calculation by MIDC | 38542845
19 | DC Route | Route | Co-Built | Airtel | Mumbai Fiber Refresh Project | MUM_Route_90 | MUM_Route_90 | Co-build | Sify - Common | Strategic | AIR52K24R090010 | 10004960 | 14270 | MUM_Route_90 | NA | MUMU25R090 | MUMU25R090MCME | MUMU25R090MCME250424D4C5L0005 | 783341644 | 160 | 2025-04-24 | AGARWADI VILLAGE ROAD | ZARINA PARK GATE NO 02 | MCGM | ME | Yes | 783341644 | 160 | 2025-04-25 | Legal | Open Trench |  |  | Carriageway(Trench on already ex) | 6711 | 1073760 | 0 | 320 | 160 |  |  |  | 536880 | 1611120 | 14936 | 2389760 | 1074240 | 6714 | 8222 | 536880 | 1611120 | MUM-ROW000000087 |  |  |  | 2025-04-25 | 2025-04-26 | 2025-04-26 | 2025-05-05 | 9 |  | 9 |  | 21358480
20 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_10 | MUM_Route_10 | IP-1 | Existing | Strategic |  | 10004633 | 10280 | MUM_Route_10 | NA | MUMU25R010 | MUMU25R010MCWB | MUMU25R010MCWE241221D2C6L0012 | 783326066 | 23 | 2024-06-26 | BOB Mirza Galibh road | Byculla Fire Bricade | MCGM | E | Yes | 783326066 | 33 | 2024-12-21 | Legal | Open Trench |  |  | Carriageway(Mastic Asphalt 25 mm)+footpath/Passages(Finished in Stencil/) | 12469/11211 | 1152439 |  | 66 | 33 |  |  |  | 576219.5 | 1728757.5 | 8413 | 277629 | 1152538 | 34925.3939 | -26512.3939 | 576219.5 | 1728757.5 |  |  |  |  | 2025-04-04 | 2025-04-05 | 2025-04-05 | 2025-04-10 | 5 |  | 5
21 | DC Route | Route | IP-1 | CE | Mumbai Fiber Refresh Project | MUM_Route_10 | MUM_Route_10 | IP-1 | Existing | Strategic |  | 10004633 | 10280 | MUM_Route_10 | NA | MUMU25R010 | MUMU25R010MCWB | MUMU25R010MCWE241221D3C6L0013 | 783326083 | 29 | 2024-06-26 | BMC E ward office | Mirza Galibh road junction | MCGM | E | Yes | 783326083 | 39 | 2024-12-21 | Legal | Open Trench |  |  | Carriageway(Mastic Asphalt 25 mm)+footpath/Passages(Grey or Any Color) | 12469/8518 | 367761 |  | 78 | 39 |  |  |  | 183880.5 | 551758.5 | 8413 | 328107 | 367878 | 9432.7692 | -1019.7692 | 183880.5 | 551758.5 |  |  |  |  | 2025-04-04 | 2025-04-05 | 2025-04-05 | 2025-04-10 | 5 |  | 5
22 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA2115 | MU-MA2115 | Co-Build | New-build | Non-Strategic |  | 10004833 | 34 | NA |  | MUMU25NL004 | MUMU25NL004MCRC | MUMU25NL004MCRC250415D3C3L0005 | 783340659 | 3 | 2025-04-15 | KRISHNA HERITAGE | KRISHNA HERITAGE FOOTPATH | MCGM | RC | Yes | 783340659 | 4 | 2025-04-25 | Legal | Open Trench |  |  | footpath/Passages(Grey or Any Color) | 8518 | 68144 | 2 | 8 | 4 |  |  |  | 34072 | 102228 | 32019 | 128076 | 68156 | 17039 | 14980 | 34072 | 102228 |  |  |  |  | 2025-04-26 | 2025-04-28 | 2025-04-28 | 2025-05-09 | 11 |  | 11
23 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA928 | MU-MA928 | Co-Build | New-build | Non-Strategic |  | 10004856 | 368 | NA | NA | MUMU25FL012 | MUMU25FL012MCRC | MUMU25FL012MCRC250415D3C3L0018 | 783340711 | 132 | 2025-04-15 | PM KULKARNI ROAD | ACHARYA ASHRAM | MCGM | RC | Yes | 783340711 | 100 | 2025-04-25 | Legal | Open Trench |  |  | On Carriageway(Mastic Asphalt 40 m) | 14936 | 1493600 | 1 | 200 | 100 |  |  |  | 746800 | 2240700 | 14936 | 1493600 | 1493900 | 14939 | -3 | 746800 | 2240700 |  |  |  |  | 2025-04-26 | 2025-04-28 | 2025-04-28 | 2025-05-09 | 11 |  | 11
24 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA928 | MU-MA928 | Co-Build | New-build | Non-Strategic |  | 10004856 | 368 | NA | NA | MUMU25FL012 | MUMU25FL012MCRC | MUMU25FL012MCRC250415D3C3L0007 | 783340697 | 90 | 2025-04-15 | PM KULKARNI ROAD | ACHARYA ASHRAM | MCGM | RC | Yes | 783340697 | 100 | 2025-04-25 | Legal | Open Trench |  |  | Carriageway(Mastic Asphalt 40 m) | 14936 | 1493600 | 0 | 200 | 100 |  |  |  | 746800 | 2240700 | 14936 | 1493600 | 1493900 | 14939 | -3 | 746800 | 2240700 |  |  |  |  | 2025-04-26 | 2025-04-28 | 2025-04-28 | 2025-05-09 | 11 |  | 11
25 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 3386 | MU-3386 | Co-Build | New-build | Non-Strategic |  | 10004879 | 280 | NA | NA | MUMU25FL006 | MUMU25FL006MCHW | MUMU25FL006MCHW250424D3C30029 | 783341573 | 166 | 2025-04-24 | DR. KESHAW BALRAM CHOWK | GAEITY GALAXY THEATER | MCGM | HW | Yes | 783341573 | 196 | 2025-04-26 | Legal | Open Trench |  |  | Carriageway | 6711 | 1315356 | 0 | 392 | 196 |  |  |  | 657678 | 1973622 | 8518 | 1669528 | 1315944 | 6714 | 1804 | 657678 | 1973622 |  |  |  |  | 2025-04-27 | 2025-04-28 | 2025-04-28 | 2025-04-29 | 1 |  | 1
26 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 148 | MU-148 | Co-Build | New-build | Non-Strategic |  | 10004692 | 67 | NA | NA | MUMU25FL007 | MUMU25FL007MCHW | MUMU25FL007MCHW250424D3C30030 | 783341566 | 130 | 2025-04-24 | OPP. JASHMIN HOUSE | PANJETANI VILLA | MCGM | HW | Yes | 783341566 | 140 | 2025-04-26 | Legal | Open Trench |  |  | Carriageway | 10187 | 1426180 | 1 | 280 | 140 |  |  |  | 713090 | 2139690 | 14936 | 2091040 | 1426600 | 10190 | 4746 | 713090 | 2139690 |  |  |  |  | 2025-04-27 | 2025-04-28 | 2025-04-19 | 2025-04-19 | 0 |  | 0
27 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 5541 | MU-5541 | Co-Build | New-build | Non-Strategic |  | 10004701 | 235 | NA | NA | MUMU25FL008 | MUMU25FL008MCHW | MUMU25FL008MCHW250424D3C30031 | 783341581 | 130 | 2024-09-09 | WINNIE APARTMENT | EDVIN 189 BUILDING | MCGM | HW | Yes | 783341581 | 135 | 2025-04-26 | Legal | Open Trench |  |  | Carriageway(Bituminous Concrete)+footpath/Passages(Concrete Finished) | 10187/10454 | 1427515 | 1 | 280 | 140 |  |  |  | 713757.5 | 2141692.5 | 14936 | 2016360 | 1427935 | 10577.2963 | 4358.7037 | 713757.5 | 2141692.5 |  |  |  |  | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-29 | 0 |  | 0
28 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 5541 | MU-5541 | Co-Build | New-build | Non-Strategic |  | 10004701 | 235 | NA | NA | MUMU25FL009 | MUMU25FL009MCHW | MUMU25FL009MCHW250424D3C30032 | 783341568 | 100 | 2024-09-09 | EDVIN 189 BUILDING | CHIMBAI ROAD CORNER | MCGM | HW | Yes | 783341568 | 120 | 2025-04-26 | Legal | Open Trench |  |  | On Carriageway(Bituminous Concrete) | 10187 | 1222440 |  | 240 | 120 |  |  |  | 611220 | 1834020 | 14936 | 1792320 | 1222800 | 10190 | 4746 | 611220 | 1834020 |  |  |  |  | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-29 | 0 |  | 0
29 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 2958 | MU-2958 | Co-Build | New-build | Non-Strategic |  | 10004801 | 224 | NA | NA | MUMU25FL010 | MUMU25FL010MCMW | MUMU25FL010MCMW250417D3C3L0013 | 783340898 | 80 | 2024-04-17 | OPP. SANKET APARTMENT | NEAR EESH KRIPA BLDG | MCGM | MW | Yes | 783340898 | 90 | 2025-04-29 | Legal | Open Trench |  |  | Carriageway(Bituminous Concrete+Others) | 10187 | 916830 | 1 | 180 | 90 |  |  |  | 458415 | 1375515 | 14936 | 1344240 | 917100 | 10190 | 4746 | 458415 | 1375515 | MUM-ROW000000090 |  |  |  | 2025-04-29 | 2025-02-05 | 2025-03-05 |  | -45721 |  | -45721
30 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | 2958 | MU-2958 | Co-Build | New-build | Non-Strategic |  | 10004801 | 224 | NA | NA | MUMU25FL010 | MUMU25FL010MCMW | MUMU25FL010MCMW250417D3C3L0014 | 783340954 | 130 | 2024-04-17 | NEAR EESH KRIPA BLDG | NEAR MAHESH KUTIR BLDG | MCGM | MW | Yes | 783340954 | 140 | 2025-04-29 | Legal | Open Trench |  |  | Carriageway(Bituminous Concrete+Others) | 10187 | 1426180 |  | 280 | 140 |  |  |  | 713090 | 2139690 | 14936 | 2091040 | 1426600 | 10190 | 4746 | 713090 | 2139690 |  |  |  |  | 2025-04-29 | 2025-02-05 | 2025-03-05 |  | -45721 |  | -45721
31 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | 3054 | MU-3054 | Co-build | New-build | Non-Strategic |  | 10004641 | 30 | NA | MUMU25R010 | MUMU25NL006 | MUMU25NL006MCWA | MUMU25NL006MCWA250415D3C3L0015 | 783340693 | 20 | 2025-04-15 | SUN CLINIC | ANIL MILK SUPPLIER | MCGM | A | Yes | 783340693 | 34 | 2025-05-02 | Legal | Open Trench |  |  | Carriageway(Bituminous Concrete) | 10187 | 346358 | 1 | 68 | 34 |  |  |  | 173179 | 519639 | 14946 | 508164 | 346460 | 10190 | 4756 | 173179 | 519639 | MUM-ROW000000093 |  |  |  | 2025-05-05 | 2025-05-06 | 2025-05-06 | 2025-05-08 | 2 |  | 2
32 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB3135 | MU-MB3135 | Co-build | New-build | Non-Strategic |  | 10004641 | 130 | NA | MUMU25R010 | MUMU25NL007 | MUMU25NL007MCWA | MUMU25NL007MCWA250414D3C3L0016 | 783340649 | 28 | 2025-04-14 | HOTEL MANAMA | FRIENDS PREMISES | MCGM | A | Yes | 783340649 | 38 | 2025-05-02 | Legal | Open Trench |  |  | Carriageway(Mastic Asphalt 40 m) | 14936 | 567568 | 1 | 76 | 38 |  |  |  | 283784 | 851466 | 14958 | 568404 | 567682 | 14939 | 19 | 283784 | 851466 | MUM-ROW000000094 |  |  |  | 2025-05-05 | 2025-05-06 | 2025-05-06 | 2025-05-09 | 3 |  | 3
33 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB1585 | MU-MB1585 | Co-Build | New-build | Non-Strategic |  | 10004873 | 112 | NA | NA | MUMU25FL011 | MUMU25FL011KDWA | MUMU25FL011KDWA250424D3C3L0017 | Airtel/OSP/2025-26/Open Trench/KDMC/MB-1585/130 Mtrs | 130 | 2024-04-24 | BHIWANDI MURBAD ROAD | SHREE GANESH VANDAN BUILDING | KDMC | A | Yes | KMDC/KA/Const./25 | 130 |  | Legal |  |  |  |  | 9269.27 | 1205005.1 |  | 26000 | 0 | 180750.76 |  |  | 120500.51 | 1532256.37 | 11600 | 1508000 | 1411755.86 | 10859.6605 | 740.3395 | 120500.51 | 1532256.37 |  |  |  |  | 2025-05-06 | 2025-05-07 | 2025-05-07 |  | -45784 |  | -45784
34 | Additional Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA2218 | MU-MA2218 | Co-build | New-build | Non-Strategic |  | 10004521 | 20 | NA | MUMU25RC07 | MUMU25NL008 | MUMU25NL008KDWA | MUMU25NL008KDWA250429D3C3L0004 | Airtel/OSP/2025-26/Open Trench/KDMC/MA-2218/20 Mtrs | 20 |  |  |  | KDMC | KDMC |  | KMDC/KA/Const./27 | 20 |  | Legal |  |  |  |  | 9269.27 | 185385.4 |  | 4000 | 0 | 27807.81 |  |  | 18538.54 | 235731.75 | 11600 | 232000 | 217193.21 | 10859.6605 | 740.3395 | 18538.54 | 235733 |  |  |  |  | 2025-05-06 | 2025-05-07 | 2025-05-07 | 2025-05-14 | 7 |  | 7
35 | Additional Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB1589 | MU-MB1589 | Co-build | New-build | Non-Strategic |  | 10004521 | 90 | NA | MUMU25RC07 | MUMU25NL009 | MUMU25NL009KDWA | MUMU25NL009KDWA250429D3C3L0001 | Airtel/OSP/2025-26/Open Trench/KDMC/MB-1589/75 Mtrs | 75 |  |  |  | KDMC | KDMC |  | KMDC/KA/Const./28 | 75 |  | Legal |  |  |  |  | 9269.27 | 695195.25 |  | 15000 | 0 | 104279.28 |  |  | 69519.52 | 883994.05 | 11600 | 870000 | 814474.53 | 10859.6604 | 740.3396 | 69519.52 | 883994.05 | MUM-ROW000000092 |  |  |  | 2025-05-06 | 2025-05-07 | 2025-05-07 | 2025-05-14 | 7 |  | 7
36 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA1048 | MU-MA1048 | Co-Build | New-build | Non-Strategic |  | 10004830 | 280 | NA | NA | MUMU25FL012 | MUMU25FL012KDWB | MUMU25FL012KDWB250418D3C3L0020 | Airtel / MBMC /OSP/2025-26/OPEN TRENCH/KDMC/MA-1048/127 Mtrs | 127 | 2024-04-18 | Khadkapada Road | Reliance Digital Building | KDMC | B | Yes | KMDC/KA/Const./26 | 127 | 2025-05-02 | Legal | Open Trench |  |  | Paver Block | 9269.27 | 1177197.29 |  | 25400 | 0 | 176579.59 |  |  | 117719.729 | 1496896.609 | 11600 | 1473200 | 1379176.88 | 10859.6605 | 740.3395 | 117719.729 | 1496896.609 | MUM-ROW000000098 |  |  |  | 2025-05-06 | 2025-05-07 | 2025-05-07 |  | -45784 |  | -45784
37 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MA2181 | MU-MA2181 | Co-build | New-build | Non-Strategic |  | 10004772 | 400 | NA | MUMU25R050 | MUMU25NL010 | MUMU25NL010NIMI | MUMU25NL010NIMI250418D3C3L0021 | MIDC-DIV-2/OSP/2025-26/AIRTEL/PLOT NO-PAP-R-343/375 MTRS | 375 | 2024-04-18 |  |  | MIDC | MIDC | Yes | No.EE/Dn.II/MHP/Eoffice/I/I113925 | 375 | 19-05-2025 | Legal | Open Trench |  |  | Hard Side Shoulder |  | 181500 |  | 1200 | 0 | 0 |  | 32886 | 50000 | 265586 | 11849 | 4443375 | 182700 | 487.2 | 11361.8 | 50000 | 265586 | MUM-ROW000000076 |  |  |  | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-27 | 7
38 | DC Route | LMC | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB3667 | MU-MB3667 | Co-build | New-build | Non-Strategic |  | 10004772 | 280 | NA | MUMU25R050 | MUMU25NL011 | MUMU25NL011NIMI | MUMU25NL011NIMI250418D3C3L0022 | MIDC-DIV-2/OSP/2025-26/AIRTEL/MB-3667/130 MTRS | 130 | 2024-04-18 |  |  | MIDC | MIDC | Yes | No.EE/Dn.II/MHP/Eoffice/I/I113922 | 130 | 19-05-2025 | Legal | Open Trench |  |  | Hard Side Shoulder |  | 63000 |  | 400 | 0 | 0 |  | 11412 | 25000 | 99812 | 11107 | 1443910 | 63400 | 487.6923 | 10619.3077 | 25000 | 99812 | MUM-ROW000000104 |  |  |  | 2025-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-27 | 7
40 | LMC routes (stand alone) | Fibmax | Co-Built | Airtel | Mumbai Fiber Refresh Project | MB1608 | MU-MB1608 | Co-Build | New-build | Non-Strategic |  | 10004869 | 56 | NA | NA | MUMU25FL012 | MUMU25FL012MBMB | MUMU25FL012MBMB250411D3C3L0001 | Airtel / MBMC /OSP/2025-26/OT/ Arihant “B” CHSL /124 Mtrs | 124 | 2024-04-11 | Radha Krishna Hotel | Arihant “B” CHSL | MBMC | MBMC | Yes | NO.MBMC/PWD/1014/64/2025-26 | 124 | 2025-04-30 | Legal | Open Trench |  |  | Asphalt Road | 9600 | 1190400 |  | 24800 | 0 | 0 |  | 218736 | 119040 | 1552976 | 4500 | 558000 | 1215200 | 9800 | -5300 | 119040 | 1552976 | [8 empty] | 0
Formulas:
Ticket raised date = [Internal approval end date]
Ticket raised date = [Internal approval end date]+4
Internal approval end date = [Internal approval start date]+1